## Sheet1
Activity ID | Activity Status | WBS Code | (*)Activity Type | Activity Name | (*)Planned Start | (*)Planned Finish | Actual Start | Actual Finish | ML Planned Date | ML Actual Date | Activity % Complete(%) | (*)Actual Duration(d) | Remaining Duration(d) | Original Duration(d) | (*)Total Float(d) | (*)Remaining Float(d) | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | (*)Predecessor Details | (*)Successor Details | (*)Resources | (*)Budgeted Labor Units(h) | (*)Budgeted Nonlabor Units(h) | Delete This Row | Predecessor Details | Successor Details
1 | Completed | MDC1-BL.1 | Start Milestone | Project Start | 2020-04-27 07:00 |  | 2020-02-24 |  | 2020-04-27 07:00 | 2020-02-24 | 100 | 0 | 0 | 0 |  |  | As Late As Possible |  |  |  |  | A1170: FS, MDC1-2029: FS, MDC1-2527: FS |  | 0 | 0 |  | [] | ['2: FS', '60: FS', '1325: FS']
2 | Completed | MDC1-BL.4.9.2 | Start Milestone | Phase 1A - Funding Release | 2020-02-24 07:00 |  | 2020-02-24 07:00 |  | 2020-02-24 07:00 | 2020-02-24 07:00 | 100 | 0 | 0 | 0 |  |  | Start On or After | 2020-02-24 |  |  | MDC1.M1000: FS | MDC1-1383: FS, MDC1-1977: FS, MDC1.C2.E1300: FS, MDC1.C2.E1310: FS, MDC1.C2.E1360: FS, MDC1.C2.E1410: FS, MDC1.C3.E1340: FS, MDC1.C3.E1360: FS, MDC1.C3.E1350: FS, MDC1.C3.E1370: FS, MDC1.C4.E1360: FS, MDC1.C4.E1380: FS, MDC1.C4.E1370: FS, MDC1.C4.E1390: FS, MDC1.C1.CS1110: FS, MDC1.C2.CS1090: FS, MDC1.C4.CS1090: FS, MDC1-2001: FS, MDC1-2002: FS, MDC1-2002: SS |  | 0 | 0 |  | ['1: FS'] | ['1338: FS', '1345: FS', '45: FS', '46: FS', '47: FS', '48: FS', '49: FS', '50: FS', '51: FS', '52: FS', '53: FS', '54: FS', '55: FS', '56: FS', '1241: FS', '1208: FS', '1062: FS', '57: FS', '58: FS', '58: SS']
3 | Not Started | MDC1-BL.4.10.3.1.1 | Start Milestone | MDC1 Deliery -MER ROJ COLO 1 CELL 1 | 2020-11-06 08:00 |  |  |  | 2020-11-06 08:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2020-11-06 |  |  | MDC1-2527: FS | MDC1.C1.C1250: FS |  | 0 | 0 |  | ['1325: FS'] | ['1051: FS']
4 | Completed | MDC1-BL.3.1 | Start Milestone | Mobilize on Site | 2020-04-27 07:00 |  | 2020-04-06 |  | 2020-04-27 07:00 | 2020-04-06 | 100 | 0 | 0 | 0 | [6 empty] | MDC1.S.1000: SS -1 | MDC1-P1020: FS |  | 0 | 0 |  | ['1347: SS -1'] | ['5: FS']
5 | Completed | MDC1-BL.3.1 | Start Milestone | Break Ground | 2020-04-27 07:00 |  | 2020-04-22 |  | 2020-04-27 07:00 | 2020-04-22 | 100 | 0 | 0 | 0 |  |  | Start On or After | 2020-03-16 |  |  | MDC1.P1010: FS | MDC1.AD.CS1000: FS, MDC1-C1.P1000: FS |  | 0 | 0 |  | ['4: FS'] | ['1350: FS', '6: FS']
6 | Completed | MDC1-BL.3.2 | Start Milestone | Foundation Start - Admin/COLO 1 | 2020-04-27 07:00 |  | 2020-04-22 |  | 2020-04-27 07:00 | 2020-04-22 | 100 | 0 | 0 | 0 | [6 empty] | MDC1-P1020: FS, MDC1-2002: FS | MDC1.C1.CS1010: FS, MDC1.AD.CS1000: FS |  | 0 | 0 |  | ['5: FS', '58: FS'] | ['1333: FS', '1350: FS']
7 | Completed | MDC1-BL.3.2 | Start Milestone | Steel Erection - Admin/COLO 1 | 2020-07-27 07:00 |  | 2020-06-22 |  | 2020-07-27 07:00 | 2020-06-22 | 100 | 0 | 0 | 0 | [6 empty] | MDC1.S.1010: FS, MDC1.AD.CS1030: SS | MDC1.C1.CS1030: FS |  | 0 | 0 |  | ['1337: FS', '1327: SS'] | ['1328: FS']
8 | Not Started | MDC1-BL.3.2 | Start Milestone | Fit out Start - Admin/COLO 1 | 2020-09-02 07:00 |  |  |  | 2020-09-02 07:00 |  | 0 | 0 | 0 | 0 | 11 | 11 |  |  |  |  | MDC1.AD.CS1100: FS | MDC1.C1.C1120: FS, MDC1.C1.C1030: FS, MDC1.C1.C3010: FS, MDC1.C1.C2030: FS, MDC1.C1.C4010: FS, MDC1.C1.C1170: FS, MDC1AD-1017: FS |  | 0 | 0 |  | ['1279: FS'] | ['1198: FS', '1268: FS', '1257: FS', '1269: FS', '1258: FS', '1144: FS', '1203: FS']
9 | Not Started | MDC1-BL.3.2 | Start Milestone | SOG- ADMIN/ COLO1 Start | 2020-08-14 07:00 |  |  |  | 2020-08-14 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 |  |  |  |  | MDC1.AD.CS1080: FS, MDC1.AD.CS1060: FS | MDC1.AD.CS1100: FS, MDC1.AD.CS1090: FS |  | 0 | 0 |  | ['1300: FS', '1314: FS'] | ['1279: FS', '1294: FS']
10 | Completed | MDC1-BL.3.3 | Start Milestone | Foundation Start - COLO 2 | 2020-06-12 07:00 |  | 2020-05-04 |  | 2020-06-12 07:00 | 2020-05-04 | 100 | 0 | 0 | 0 | [6 empty] | MDC1.C1.CS1000: FS, MDC1.C1.CS1020: FS | MDC1.C2.CS1010: FS, MDC1.C2.CS1000: FS |  | 0 | 0 |  | ['1343: FS', '1341: FS'] | ['1320: FS', '1329: FS']
11 | Not Started | MDC1-BL.3.3 | Start Milestone | Steel Erection - COLO 2 | 2020-07-07 07:00 |  |  |  | 2020-07-07 07:00 |  | 0 | 0 | 0 | 0 | 6 | 6 |  |  |  |  | MDC1.C1.CS1030: FS | MDC1.C2.CS1020: FS |  | 0 | 0 |  | ['1328: FS'] | ['1319: FS']
12 | Not Started | MDC1-BL.3.3 | Start Milestone | Fit out Start - COLO 2 | 2020-10-05 07:00 |  |  |  | 2020-10-05 07:00 |  | 0 | 0 | 0 | 0 | 16 | 16 |  |  |  |  | MDC1.C2.CS1090: FS | MDC1.C2.C1050: FS |  | 0 | 0 |  | ['1208: FS'] | ['1170: FS']
13 | Not Started | MDC1-BL.3.3 | Start Milestone | SOG- COLO 2 Start | 2020-09-22 07:00 |  |  |  | 2020-09-22 07:00 |  | 0 | 0 | 0 | 0 | 14 | 14 |  |  |  |  | MDC1.C2.CS1070: FS, MDC1.C2.CS1050: FS, MDC1.C2.CS1020: FS | MDC1.C2.CS1090: FS, MDC1.C2.CS1080: FS |  | 0 | 0 |  | ['1242: FS', '1296: FS', '1319: FS'] | ['1208: FS', '1219: FS']
14 | Completed | MDC1-BL.3.4 | Start Milestone | Foundation Start - COLO 3 | 2020-06-22 07:00 |  | 2020-05-29 |  | 2020-06-22 07:00 | 2020-05-29 | 100 | 0 | 0 | 0 | [6 empty] | MDC1.C2.CS1000: FS | MDC1.C3.CS1000: FS |  | 0 | 0 |  | ['1329: FS'] | ['1321: FS']
15 | Not Started | MDC1-BL.3.4 | Start Milestone | Steel Erection -COLO 3 | 2020-07-23 07:00 |  |  |  | 2020-07-23 07:00 |  | 0 | 0 | 0 | 0 | 7 | 7 |  |  |  |  | MDC1.C2.CS1020: FS | MDC1.C3.CS1020: FS |  | 0 | 0 |  | ['1319: FS'] | ['1304: FS']
16 | Not Started | MDC1-BL.3.4 | Start Milestone | Fit out Start - COLO 3 | 2020-10-22 07:00 |  |  |  | 2020-10-22 07:00 |  | 0 | 0 | 0 | 0 | 49 | 49 |  |  |  |  | MDC1.C3.CS1090: FS | MDC1.C3.C1090: FS |  | 0 | 0 |  | ['1140: FS'] | ['996: FS']
17 | Not Started | MDC1-BL.3.4 | Start Milestone | SOG- COLO 3 Start | 2020-10-10 07:00 |  |  |  | 2020-10-10 07:00 |  | 0 | 0 | 0 | 0 | 49 | 49 |  |  |  |  | MDC1.C3.CS1070: FS | MDC1.C3.CS1090: FS, MDC1.C3.CS1080: FS |  | 0 | 0 |  | ['1189: FS'] | ['1140: FS', '1163: FS']
18 | Not Started | MDC1-BL.3.5 | Start Milestone | Foundation Start - COLO 4 | 2020-07-20 07:00 |  |  |  | 2020-07-20 07:00 |  | 0 | 0 | 0 | 0 | 11 | 11 |  |  |  |  | MDC1.C3.CS1010: FS | MDC1.C4.CS1010: FS, MDC1.C4.CS1000: FS |  | 0 | 0 |  | ['1330: FS'] | ['1305: FS', '1317: FS']
19 | Not Started | MDC1-BL.3.5 | Start Milestone | Steel Erection - COLO 4 | 2020-08-08 07:00 |  |  |  | 2020-08-08 07:00 |  | 0 | 0 | 0 | 0 | 10 | 10 |  |  |  |  | MDC1.C3.CS1020: FS | MDC1.C4.CS1020: FS |  | 0 | 0 |  | ['1304: FS'] | ['1291: FS']
20 | Not Started | MDC1-BL.3.5 | Start Milestone | Fit out Start - COLO 4 | 2020-11-10 07:00 |  |  |  | 2020-11-10 07:00 |  | 0 | 0 | 0 | 0 | 68 | 68 |  |  |  |  | MDC1.C4.CS1090: FS | MDC1.C4.C1140: FS |  | 0 | 0 |  | ['1062: FS'] | ['627: FS']
21 | Not Started | MDC1-BL.3.5 | Start Milestone | SOG- COLO 4 Start | 2020-10-29 07:00 |  |  |  | 2020-10-29 07:00 |  | 0 | 0 | 0 | 0 | 68 | 68 |  |  |  |  | MDC1.C4.CS1070: FS | MDC1.C4.CS1090: FS |  | 0 | 0 |  | ['1120: FS'] | ['1062: FS']
22 | Not Started | MDC1-BL.3.2 | Start Milestone | Insulated Metal Panel Start- Admin/COLO 1 | 2020-07-07 07:00 |  |  |  | 2020-07-07 07:00 |  | 0 | 0 | 0 | 0 | 9 | 9 |  |  |  |  | MDC1.AD.CS1030: SS 12 | MDC1.C1.CS1050: FS, MDC1AD-1010: FS, MDC1.AD.CS1060: FF, MDC1.AD.CS1070: FS, MDC1.C1.CS1060: FS, MDC1-1965: FS, MDC1-1972: FS, MDC1-C1.P1300: FS |  | 0 | 0 |  | ['1327: SS 12'] | ['1323: FS', '589: FS', '1314: FF', '1303: FS', '1324: FS', '1286: FS', '1287: FS', '23: FS']
23 | Not Started | MDC1-BL.3.2 | Start Milestone | Roof Panel Start -Admin/COLO 1 | 2020-07-15 07:00 |  |  |  | 2020-07-15 07:00 |  | 0 | 0 | 0 | 0 | 3 | 3 |  |  |  |  | MDC1.AD.CS1040: FS, MDC1.AD.CS1050: SS 2, MDC1-C1.P1200: FS | MDC1.AD.CS1060: FS |  | 0 | 0 |  | ['1326: FS', '1318: SS 2', '22: FS'] | ['1314: FS']
24 | Not Started | MDC1-BL.3.3 | Start Milestone | Insulated Metal Panel Start- COLO 2 | 2020-07-20 07:00 |  |  |  | 2020-07-20 07:00 |  | 0 | 0 | 0 | 0 | 18 | 18 |  |  |  |  | MDC1.C1.CS1050: FS | MDC1.C2.CS1040: FS |  | 0 | 0 |  | ['1323: FS'] | ['1299: FS']
25 | Not Started | MDC1-BL.3.3 | Start Milestone | Roof Panel Start -COLO 2 | 2020-07-27 07:00 |  |  |  | 2020-07-27 07:00 |  | 0 | 0 | 0 | 0 | 10 | 10 |  |  |  |  | MDC1.C1.CS1070: FS | MDC1.C2.CS1050: FS |  | 0 | 0 |  | ['1315: FS'] | ['1296: FS']
26 | Not Started | MDC1-BL.3.4 | Start Milestone | Insulated Metal Panel Start- COLO 3 | 2020-08-15 07:00 |  |  |  | 2020-08-15 07:00 |  | 0 | 0 | 0 | 0 | 12 | 12 |  |  |  |  | MDC1.C2.CS1040: FS, MDC1.C2.CS1040: SS, MDC1.C1.CS1060: FS, MDC1.C2.CS1030: FS | MDC1.C3.CS1040: FS, MDC1.C3.CS1060: FS, MDC1.C3.CS1050: FF, MDC1-C4.P1200: FS, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF |  | 0 | 0 |  | ['1299: FS', '1299: SS', '1324: FS', '1311: FS'] | ['1283: FS', '1233: FS', '1276: FF', '28: FS', '1178: FS', '1238: FF']
27 | Not Started | MDC1-BL.3.4 | Start Milestone | Roof Panel Start -COLO 3 | 2020-08-18 07:00 |  |  |  | 2020-08-18 07:00 |  | 0 | 0 | 0 | 0 | 6 | 6 |  |  |  |  | MDC1.C2.CS1050: FS | MDC1.C3.CS1050: FS |  | 0 | 0 |  | ['1296: FS'] | ['1276: FS']
28 | Not Started | MDC1-BL.3.5 | Start Milestone | Insulated Metal Panel Start- COLO 4 | 2020-09-01 07:00 |  |  |  | 2020-09-01 07:00 |  | 0 | 0 | 0 | 0 | 11 | 11 |  |  |  |  | MDC1.C3.CS1040: FS, MDC1.C3.CS1040: SS, MDC1-C3.P1200: FS, MDC1.C2.CS1040: SS, MDC1.C1.CS1060: FS, MDC1.C2.CS1030: FS, MDC1.C2.CS1040: FS, MDC1.C3.CS1030: FS | MDC1.C4.CS1040: FS |  | 0 | 0 |  | ['1283: FS', '1283: SS', '26: FS', '1299: SS', '1324: FS', '1311: FS', '1299: FS', '1298: FS'] | ['1256: FS']
29 | Not Started | MDC1-BL.3.5 | Start Milestone | Roof Panel Start - COLO 4 | 2020-09-04 07:00 |  |  |  | 2020-09-04 07:00 |  | 0 | 0 | 0 | 0 | 6 | 6 |  |  |  |  | MDC1.C3.CS1050: FS | MDC1.C4.CS1050: FS |  | 0 | 0 |  | ['1276: FS'] | ['1238: FS']
30 | Not Started | MDC1-BL.3.2 | Start Milestone | Cx - Level 2 Start COLO 1 | 2021-01-25 08:00 |  |  |  | 2021-01-25 08:00 |  | 0 | 0 | 0 | 0 | 11 | 11 |  |  |  |  | MDC1.C1.C1040: FS, MDC1-P1050: FS, MDC1.C1.C1130: FS, MDC1.C1.C1420: FS, MDC1.C1.C1460: FS, MDC1.C1.C1400: FS, MDC1.C1.C1330: FS, MDC1.C1.C1440: FS, MDC1.C1.C1320: FS, MDC1.C1.C1340: FS, MDC1.C1.C1290: FS, MDC1.C1.C3340: FS, MDC1.C1.C1320: SS, MDC1.C1.C2260: FS, MDC1.C1.C4320: FS, MDC1-2529: FS | MDC1.C1.Cx2020: FS |  | 0 | 0 |  | ['1270: FS', '939: FS', '1188: FS', '818: FS', '689: FS', '861: FS', '964: FS', '716: FS', '963: FS', '965: FS', '1009: FS', '832: FS', '963: SS', '1011: FS', '833: FS', '1240: FS'] | ['595: FS']
31 | Not Started | MDC1-BL.3.3 | Start Milestone | Cx - Level 2 Start COLO 2 | 2021-03-19 07:00 |  |  |  | 2021-03-19 07:00 |  | 0 | 0 | 0 | 0 | 112 | 112 |  |  |  |  | MDC1.C2.C1450: FS, MDC1.C2.C3440: FS, MDC1.C2.C2230: FS, MDC1.C2.C2430: FS, MDC1.C2.C4100: FS, MDC1.C2.C4400: FS, MDC1.C2.C1220: FS, MDC1.C2.C1320: FS, MDC1.C2.C2210: FS, MDC1.C2.C2320: FS, MDC1.C2.C3200: FS, MDC1.C2.C3300: FS, MDC1.C2.C4160: FS, MDC1.C2.C4260: FS, MDC1.C2.C1240: FS, MDC1.C2.C1400: FS, MDC1.C2.C2240: FS, MDC1.C2.C2390: FS, MDC1.C2.C4200: FS, MDC1.C2.C4330: FS | MDC1.M3010: FS |  | 0 | 0 |  | ['568: FS', '535: FS', '887: FS', '590: FS', '971: FS', '502: FS', '925: FS', '784: FS', '929: FS', '787: FS', '838: FS', '708: FS', '841: FS', '711: FS', '854: FS', '671: FS', '855: FS', '673: FS', '738: FS', '617: FS'] | ['246: FS']
32 | Not Started | MDC1-BL.3.4 | Start Milestone | Cx - Level 2 Start COLO 3 | 2021-04-14 07:00 |  |  |  | 2021-04-14 07:00 |  | 0 | 0 | 0 | 0 | 2 | 2 |  |  |  |  | MDC1.C3.Cx2000: SS, MDC1.C3.C1200: FS, MDC1.C3.C1400: FS, MDC1.C3.C1150: FS, MDC1.C3.C1190: FS, MDC1.C3.C1340: FS, MDC1.C3.C1440: FS, MDC1.C3.C1260: FS, MDC1.C3.C2270: FS | MDC1.C3.Cx2030: FS, MDC1.C3.Cx2010: FS, MDC1.C3.Cx2050: FS |  | 0 | 0 |  | ['389: SS', '768: FS', '476: FS', '907: FS', '778: FS', '546: FS', '427: FS', '619: FS', '620: FS'] | ['352: FS', '380: FS', '354: FS']
33 | Not Started | MDC1-BL.3.5 | Start Milestone | Cx - Level 2 Start COLO 4 | 2021-05-21 07:00 |  |  |  | 2021-05-21 07:00 |  | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | MDC1.C4.Cx2000: SS, MDC1.C4.C1390: FS, MDC1.C4.C1410: FS, MDC1.C4.C1090: FS, MDC1.C4.C1210: FS, MDC1.C4.C1330: FS, MDC1.C4.C1430: FS | MDC1.C4.Cx2030: FS, MDC1.C4.Cx2010: FS, MDC1.C4.Cx2050: FS |  | 0 | 0 |  | ['312: SS', '375: FS', '343: FS', '802: FS', '552: FS', '431: FS', '330: FS'] | ['287: FS', '298: FS', '285: FS']
34 | Not Started | MDC1-BL.3.2 | Start Milestone | Ready to Set Exterior MER | 2020-09-15 07:00 |  |  |  | 2020-09-15 07:00 |  | 0 | 0 | 0 | 0 | 43 | 43 |  |  |  |  | MDC1.C1.C1050: FS | MDC1.C1.C1250: FS |  | 0 | 0 |  | ['1261: FS'] | ['1051: FS']
35 | Not Started | MDC1-BL.3.2 | Start Milestone | Ready to Set Exterior Mechanical Equipment | 2020-09-15 07:00 |  |  |  | 2020-09-15 07:00 |  | 0 | 0 | 0 | 0 | 52 | 52 |  |  |  |  | MDC1.C1.C1060: FS | MDC1.C1.C1110: FS |  | 0 | 0 |  | ['1262: FS'] | ['1207: FS']
36 | Not Started | MDC1-BL.3.3 | Start Milestone | Ready to Set MER | 2020-10-14 07:00 |  |  |  | 2020-10-14 07:00 |  | 0 | 0 | 0 | 0 | 47 | 47 |  |  |  |  | MDC1.C2.C1040: FS | MDC1.C2.C1250: FS |  | 0 | 0 |  | ['1181: FS'] | ['850: FS']
37 | Not Started | MDC1-BL.3.3 | Start Milestone | Ready to Set Exterior Mechanical Equipment | 2020-10-21 07:00 |  |  |  | 2020-10-21 07:00 |  | 0 | 0 | 0 | 0 | 54 | 54 |  |  |  |  | MDC1.C2.C1060: FS | MDC1.C2.C1120: FS |  | 0 | 0 |  | ['1151: FS'] | ['1064: FS']
38 | Not Started | MDC1-BL.3.4 | Start Milestone | Ready to Set Exterior MER | 2020-11-12 07:00 |  |  |  | 2020-11-12 07:00 |  | 0 | 0 | 0 | 0 | 57 | 57 |  |  |  |  | MDC1.C3.C1050: FS | MDC1.C3.C1230: FS |  | 0 | 0 |  | ['1054: FS'] | ['659: FS']
39 | Not Started | MDC1-BL.3.4 | Start Milestone | Ready to Set Exterior Mechanical Equipment | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 58 | 58 |  |  |  |  | MDC1.C3.C1060: FS | MDC1.C3.C1160: FS |  | 0 | 0 |  | ['1020: FS'] | ['888: FS']
40 | Not Started | MDC1-BL.3.5 | Start Milestone | Ready to Set Exterior MER | 2020-12-16 07:00 |  |  |  | 2020-12-16 07:00 |  | 0 | 0 | 0 | 0 | 67 | 67 |  |  |  |  | MDC1.C4.C1060: FS | MDC1.C4.C1230: FS |  | 0 | 0 |  | ['876: FS'] | ['511: FS']
41 | Not Started | MDC1-BL.3.5 | Start Milestone | Ready to Set Exterior Mechanical Equipment | 2020-12-23 07:00 |  |  |  | 2020-12-23 07:00 |  | 0 | 0 | 0 | 0 | 66 | 66 |  |  |  |  | MDC1.C4.C1070: FS | MDC1.C4.C1110: FS |  | 0 | 0 |  | ['842: FS'] | ['720: FS']
42 | Not Started | MDC1-BL.4.10.3.1.1 | Start Milestone | MDC1 Deliery -MER ROJ COLO 1 CELL 3 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2020-11-20 |  |  | MDC1-2029: FS, MDC1-2527: FS | MDC1.C1.C3210: FS |  | 0 | 0 |  | ['60: FS', '1325: FS'] | ['981: FS']
43 | Not Started | MDC1-BL.4.10.3.1.1 | Start Milestone | MDC1 Deliery -MER ROJ COLO 1 CELL 2 | 2020-11-13 07:00 |  |  |  | 2020-11-13 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2020-11-13 |  |  | MDC1-2527: FS | MDC1.C1.C2270: FS |  | 0 | 0 |  | ['1325: FS'] | ['1024: FS']
44 | Not Started | MDC1-BL.4.10.3.1.1 | Start Milestone | MDC1 Deliery -MER ROJ COLO 1 CELL 4 | 2020-12-04 07:00 |  |  |  | 2020-12-04 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2020-12-04 |  |  | MDC1-2029: FS, MDC1-2527: FS | MDC1.C1.C4270: FS |  | 0 | 0 |  | ['60: FS', '1325: FS'] | ['903: FS']
45 | Not Started | MDC1-BL.4.10.3.1.6 | Start Milestone | MDC1 Deliery -MER ROJ COLO 2 CELL 1 | 2020-12-15 08:00 |  |  |  | 2020-12-15 08:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2020-12-15 |  |  | A1170: FS, MDC1-2527: FS | MDC1.C2.C1250: FS |  | 0 | 0 |  | ['2: FS', '1325: FS'] | ['850: FS']
46 | Not Started | MDC1-BL.4.10.3.1.6 | Start Milestone | MDC1 Deliery -MER ROJ COLO 2 CELL 2 | 2020-12-22 07:00 |  |  |  | 2020-12-22 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2020-12-22 |  |  | A1170: FS, MDC1-2527: FS | MDC1.C2.C2290: FS |  | 0 | 0 |  | ['2: FS', '1325: FS'] | ['807: FS']
47 | Not Started | MDC1-BL.4.10.3.1.6 | Start Milestone | MDC1 Deliery -MER ROJ COLO 2 CELL 3 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 3 | 3 | Start On or After | 2020-12-28 |  |  | A1170: FS, MDC1-2527: FS | MDC1.C2.C3230: FS |  | 0 | 0 |  | ['2: FS', '1325: FS'] | ['770: FS']
48 | Not Started | MDC1-BL.4.10.3.1.6 | Start Milestone | MDC1 Deliery -MER ROJ COLO 2 CELL 4 | 2021-01-05 07:00 |  |  |  | 2021-01-05 07:00 |  | 0 | 0 | 0 | 0 | 5 | 5 | Start On or After | 2021-01-05 |  |  | A1170: FS, MDC1-2527: FS | MDC1.C2.C4220: FS |  | 0 | 0 |  | ['2: FS', '1325: FS'] | ['734: FS']
49 | Not Started | MDC1-BL.4.10.3.1.7 | Start Milestone | MDC1 Deliery -MER ROJ COLO 3 CELL 1 | 2021-01-29 07:00 |  |  |  | 2021-01-29 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 | Start On or After | 2021-01-29 |  |  | A1170: FS, MDC1-2527: FS | MDC1.C3.C1230: FS |  | 0 | 0 |  | ['2: FS', '1325: FS'] | ['659: FS']
50 | Not Started | MDC1-BL.4.10.3.1.7 | Start Milestone | MDC1 Deliery -MER ROJ COLO 3 CELL 3 | 2021-02-12 07:00 |  |  |  | 2021-02-12 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 | Start On or After | 2021-02-12 |  |  | A1170: FS, MDC1-2527: FS | MDC1.C3.C3200: FS |  | 0 | 0 |  | ['2: FS', '1325: FS'] | ['612: FS']
51 | Not Started | MDC1-BL.4.10.3.1.7 | Start Milestone | MDC1 Deliery -MER ROJ COLO 3 CELL 2 | 2021-02-05 07:00 |  |  |  | 2021-02-05 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2021-02-05 |  |  | A1170: FS, MDC1-2527: FS | MDC1.C3.C2260: FS |  | 0 | 0 |  | ['2: FS', '1325: FS'] | ['635: FS']
52 | Not Started | MDC1-BL.4.10.3.1.7 | Start Milestone | MDC1 Deliery -MER ROJ COLO 3 CELL 4 | 2021-02-19 07:00 |  |  |  | 2021-02-19 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2021-02-19 |  |  | A1170: FS, MDC1-2527: FS | MDC1.C3.C4270: FS |  | 0 | 0 |  | ['2: FS', '1325: FS'] | ['582: FS']
53 | Not Started | MDC1-BL.4.10.3.1.5 | Start Milestone | MDC1 Deliery -MER ROJ COLO 4 CELL 1 | 2021-03-12 07:00 |  |  |  | 2021-03-12 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 | Start On or After | 2021-03-12 |  |  | A1170: FS, MDC1-2527: FS | MDC1.C4.C1230: FS |  | 0 | 0 |  | ['2: FS', '1325: FS'] | ['511: FS']
54 | Not Started | MDC1-BL.4.10.3.1.5 | Start Milestone | MDC1 Deliery -MER ROJ COLO 4 CELL 3 | 2021-03-26 07:00 |  |  |  | 2021-03-26 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 | Start On or After | 2021-03-26 |  |  | A1170: FS, MDC1-2527: FS | MDC1.C4.C3210: FS |  | 0 | 0 |  | ['2: FS', '1325: FS'] | ['465: FS']
55 | Not Started | MDC1-BL.4.10.3.1.5 | Start Milestone | MDC1 Deliery -MER ROJ COLO 4 CELL 2 | 2021-03-19 07:00 |  |  |  | 2021-03-19 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2021-03-19 |  |  | A1170: FS, MDC1-2527: FS | MDC1.C4.C2270: FS |  | 0 | 0 |  | ['2: FS', '1325: FS'] | ['483: FS']
56 | Not Started | MDC1-BL.4.10.3.1.5 | Start Milestone | MDC1 Deliery -MER ROJ COLO 4 CELL 4 | 2021-04-02 07:00 |  |  |  | 2021-04-02 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2021-04-02 |  |  | A1170: FS, MDC1-2527: FS | MDC1.C4.C4250: FS |  | 0 | 0 |  | ['2: FS', '1325: FS'] | ['441: FS']
57 | Completed | MDC1-BL.4.9.2 | Start Milestone | PEMB Release | 2020-02-24 07:00 |  | 2020-02-24 07:00 |  | 2020-02-24 07:00 | 2020-02-24 07:00 | 100 | 0 | 0 | 0 |  |  | Start On or After | 2020-02-24 |  |  | A1170: FS | MDC1-1383: FS |  | 0 | 0 |  | ['2: FS'] | ['1338: FS']
58 | Completed | MDC1-BL.4.9.2 | Start Milestone | Phase 1B - Funding Release | 2020-03-30 07:00 |  | 2020-03-30 07:00 |  | 2020-03-30 07:00 | 2020-03-30 07:00 | 100 | 0 | 0 | 0 |  |  | Start On or After | 2020-03-30 |  |  | A1170: FS, A1170: SS | MDC1-1977: FS, MDC1-1998: FS 7, MDC1.AD.CS1030: FS, MDC1.AD.CS1000: FS, MDC1.AD.CS1020: FS, MDC1-2011: FS 7, MDC1-2013: FS 7, MDC1-1994: FS, MDC1.S.1000: FS, MDC1-2016: FS 7, MDC1-1997: FS 7, MDC1-2003: FS, MDC1-C1.P1000: FS, MDC1-2000: FS, MDC1-2111: FS, MDC1-1996: FS, MDC1-2140.1: FS |  | 0 | 0 |  | ['2: FS', '2: SS'] | ['1345: FS', '1349: FS 7', '1327: FS', '1350: FS', '1339: FS', '1335: FS 7', '1336: FS 7', '1348: FS', '1347: FS', '1077: FS 7', '1346: FS 7', '59: FS', '6: FS', '1334: FS', '1332: FS', '1134: FS', '1344: FS']
59 | Not Started | MDC1-BL.4.9.2 | Start Milestone | Phase 1C - Funding Release | 2020-06-30 08:00 |  |  |  | 2020-06-30 08:00 |  | 0 | 0 | 0 | 0 | 11 | 11 | Start On or After | 2020-06-30 08:00 |  |  | MDC1-2002: FS | MDC1-2008: FS, MDC1.AD.CS1090: FS, MDC1-2010: FS, MDC1-2012: FS, MDC1.C1.CS1050: FS, MDC1.AD.CS1050: FS, MDC1-1995: FS, MDC1-2101: FS, MDC1-2102: FS, MDC1-2103: FS, MDC1-2104: FS, MDC1-2105: FS, MDC1-2106: FS, MDC1.AD.CS1050: FF |  | 0 | 0 |  | ['58: FS'] | ['1216: FS', '1294: FS', '1247: FS', '1295: FS', '1323: FS', '1318: FS', '1284: FS', '1313: FS', '1312: FS', '1308: FS', '1290: FS', '1227: FS', '1169: FS', '1318: FF']
60 | Completed | MDC1-BL.4.9.2 | Start Milestone | Schneider Electric ROJ Received from MDC1 | 2020-04-27 07:00 |  | 2020-04-13 |  | 2020-04-27 07:00 | 2020-04-13 | 100 | 0 | 0 | 0 |  |  | Start On or After | 2020-04-13 |  |  | MDC1.M1000: FS | MDC1.C1.E1380: FS, MDC1.C1.E1470: FS |  | 0 | 0 |  | ['1: FS'] | ['42: FS', '44: FS']
61 | Not Started | MDC1-BL.4.10.2.5.1 | Start Milestone | AHU - ROJ COLO-1 Cell- 1 | 2020-10-21 07:00 |  |  |  | 2020-10-21 07:00 |  | 0 | 0 | 0 | 0 | 57 | 57 |  |  |  |  | MDC1.C1.C1170: FS | MDC1.C1.C1230: FS |  | 0 | 0 |  | ['1144: FS'] | ['1083: FS']
62 | Not Started | MDC1-BL.4.10.2.5.1 | Start Milestone | AHU - ROJ COLO-1 Cell- 3 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 33 | 33 |  |  |  |  | MDC1.C1.C3200: FS | MDC1.C1.C3290: FS |  | 0 | 0 |  | ['1010: FS'] | ['919: FS']
63 | Not Started | MDC1-BL.4.10.2.5.1 | Start Milestone | AHU - ROJ COLO-1 Cell- 2 | 2020-10-21 07:00 |  |  |  | 2020-10-21 07:00 |  | 0 | 0 | 0 | 0 | 57 | 57 |  |  |  |  | MDC1.C1.C2160: FS | MDC1.C1.C2210: FS |  | 0 | 0 |  | ['1148: FS'] | ['1089: FS']
64 | Not Started | MDC1-BL.4.10.2.5.1 | Start Milestone | AHU - ROJ COLO-1 Cell- 4 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 33 | 33 |  |  |  |  | MDC1.C1.C4190: FS | MDC1.C1.C4250: FS |  | 0 | 0 |  | ['1012: FS'] | ['922: FS']
65 | Not Started | MDC1-BL.4.10.2.5.2 | Start Milestone | AHU - ROJ COLO-2 Cell- 1 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 66 | 66 |  |  |  |  | MDC1.C2.C1160: FS | MDC1.C2.C1210: FS |  | 0 | 0 |  | ['1014: FS'] | ['924: FS']
66 | Not Started | MDC1-BL.4.10.3.2.2 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-2 Cell- 3 | 2020-12-23 07:00 |  |  |  | 2020-12-23 07:00 |  | 0 | 0 | 0 | 0 | 52 | 52 | Start On or After | 2020-12-23 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C3250: FS |  | 0 | 0 |  | ['1325: FS'] | ['752: FS']
67 | Not Started | MDC1-BL.4.10.2.5.2 | Start Milestone | AHU - ROJ COLO-2 Cell- 2 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 66 | 66 |  |  |  |  | MDC1.C2.C2140: FS | MDC1.C2.C2200: FS |  | 0 | 0 |  | ['1017: FS'] | ['928: FS']
68 | Not Started | MDC1-BL.4.10.2.5.2 | Start Milestone | AHU - ROJ COLO-2 Cell- 4 | 2020-12-23 07:00 |  |  |  | 2020-12-23 07:00 |  | 0 | 0 | 0 | 0 | 52 | 52 |  |  |  |  | MDC1.C2.C4150: FS | MDC1.C2.C4190: FS |  | 0 | 0 |  | ['840: FS'] | ['754: FS']
69 | Not Started | MDC1-BL.4.10.2.5.3 | Start Milestone | AHU - ROJ COLO-3 Cell- 1 | 2020-11-21 07:00 |  |  |  | 2020-11-21 07:00 |  | 0 | 0 | 0 | 0 | 97 | 97 |  |  |  |  | MDC1.C3.C1070: FS | MDC1.C3.C1140: FS |  | 0 | 0 |  | ['1003: FS'] | ['906: FS']
70 | Not Started | MDC1-BL.4.10.2.5.3 | Start Milestone | AHU - ROJ COLO-3 Cell- 3 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 |  |  |  |  | MDC1.C3.C3090: FS | MDC1.C3.C3140: FS |  | 0 | 0 |  | ['823: FS'] | ['741: FS']
71 | Not Started | MDC1-BL.4.10.2.5.3 | Start Milestone | AHU - ROJ COLO-3 Cell- 2 | 2020-11-21 07:00 |  |  |  | 2020-11-21 07:00 |  | 0 | 0 | 0 | 0 | 97 | 97 |  |  |  |  | MDC1.C3.C2070: FS | MDC1.C3.C2140: FS |  | 0 | 0 |  | ['1006: FS'] | ['911: FS']
72 | Not Started | MDC1-BL.4.10.2.5.3 | Start Milestone | AHU - ROJ COLO-3 Cell- 4 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 |  |  |  |  | MDC1.C3.C4110: FS | MDC1.C3.C4170: FS |  | 0 | 0 |  | ['826: FS'] | ['744: FS']
73 | Not Started | MDC1-BL.4.10.3.2.4 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-4 Cell- 1 | 2021-01-28 07:00 |  |  |  | 2021-01-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 | Start On or After | 2021-01-28 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C1170: FS |  | 0 | 0 |  | ['1325: FS'] | ['630: FS']
74 | Not Started | MDC1-BL.4.10.2.5.4 | Start Milestone | AHU - ROJ COLO-4 Cell- 3 | 2021-02-26 07:00 |  |  |  | 2021-02-26 07:00 |  | 0 | 0 | 0 | 0 | 69 | 69 |  |  |  |  | MDC1.C4.C3140: FS | MDC1.C4.C3170: FS |  | 0 | 0 |  | ['573: FS'] | ['531: FS']
75 | Not Started | MDC1-BL.4.10.2.5.4 | Start Milestone | AHU - ROJ COLO-4 Cell- 2 | 2021-01-28 07:00 |  |  |  | 2021-01-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 |  |  |  |  | MDC1.C4.C2130: FS | MDC1.C4.C2170: FS |  | 0 | 0 |  | ['683: FS'] | ['634: FS']
76 | Not Started | MDC1-BL.4.10.2.5.4 | Start Milestone | AHU - ROJ COLO-4 Cell- 4 | 2021-02-26 07:00 |  |  |  | 2021-02-26 07:00 |  | 0 | 0 | 0 | 0 | 69 | 69 |  |  |  |  | MDC1.C4.C4140: FS | MDC1.C4.C4170: FS |  | 0 | 0 |  | ['575: FS'] | ['534: FS']
77 | Not Started | MDC1-BL.4.10.3.2.1 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-1 Cell- 1 | 2020-10-21 07:00 |  |  |  | 2020-10-21 07:00 |  | 0 | 0 | 0 | 0 | 57 | 57 | Start On or After | 2020-10-21 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C1230: FS |  | 0 | 0 |  | ['1325: FS'] | ['1083: FS']
78 | Not Started | MDC1-BL.4.10.3.2.1 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-1 Cell- 3 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 33 | 33 | Start On or After | 2020-11-20 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C3290: FS |  | 0 | 0 |  | ['1325: FS'] | ['919: FS']
79 | Not Started | MDC1-BL.4.10.3.2.1 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-1 Cell- 2 | 2020-10-21 07:00 |  |  |  | 2020-10-21 07:00 |  | 0 | 0 | 0 | 0 | 57 | 57 | Start On or After | 2020-10-21 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C2210: FS |  | 0 | 0 |  | ['1325: FS'] | ['1089: FS']
80 | Not Started | MDC1-BL.4.10.3.2.1 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-1 Cell- 4 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 33 | 33 | Start On or After | 2020-11-20 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C4250: FS |  | 0 | 0 |  | ['1325: FS'] | ['922: FS']
81 | Not Started | MDC1-BL.4.10.3.2.2 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-2 Cell- 1 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 66 | 66 | Start On or After | 2020-11-20 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C1210: FS |  | 0 | 0 |  | ['1325: FS'] | ['924: FS']
82 | Not Started | MDC1-BL.4.10.2.5.2 | Start Milestone | AHU - ROJ COLO-2 Cell- 3 | 2020-12-23 07:00 |  |  |  | 2020-12-23 07:00 |  | 0 | 0 | 0 | 0 | 52 | 52 |  |  |  |  | MDC1.C2.C3090: FS, MDC1.C2.C3190: FS | MDC1.C2.C3250: FS |  | 0 | 0 |  | ['1042: FS', '837: FS'] | ['752: FS']
83 | Not Started | MDC1-BL.4.10.3.2.2 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-2 Cell- 2 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 66 | 66 | Start On or After | 2020-11-20 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C2200: FS |  | 0 | 0 |  | ['1325: FS'] | ['928: FS']
84 | Not Started | MDC1-BL.4.10.3.2.2 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-2 Cell- 4 | 2020-12-23 07:00 |  |  |  | 2020-12-23 07:00 |  | 0 | 0 | 0 | 0 | 52 | 52 | Start On or After | 2020-12-23 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C4190: FS |  | 0 | 0 |  | ['1325: FS'] | ['754: FS']
85 | Not Started | MDC1-BL.4.10.3.2.3 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-3 Cell- 1 | 2020-11-21 07:00 |  |  |  | 2020-11-21 07:00 |  | 0 | 0 | 0 | 0 | 97 | 97 | Start On or After | 2020-11-21 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C1140: FS |  | 0 | 0 |  | ['1325: FS'] | ['906: FS']
86 | Not Started | MDC1-BL.4.10.3.2.3 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-3 Cell- 3 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 | Start On or After | 2020-12-28 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C3140: FS |  | 0 | 0 |  | ['1325: FS'] | ['741: FS']
87 | Not Started | MDC1-BL.4.10.3.2.3 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-3 Cell- 2 | 2020-11-21 07:00 |  |  |  | 2020-11-21 07:00 |  | 0 | 0 | 0 | 0 | 97 | 97 | Start On or After | 2020-11-21 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C2140: FS |  | 0 | 0 |  | ['1325: FS'] | ['911: FS']
88 | Not Started | MDC1-BL.4.10.3.2.3 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-3 Cell- 4 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 | Start On or After | 2020-12-28 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C4170: FS |  | 0 | 0 |  | ['1325: FS'] | ['744: FS']
89 | Not Started | MDC1-BL.4.10.2.5.4 | Start Milestone | AHU - ROJ COLO-4 Cell- 1 | 2021-01-28 07:00 |  |  |  | 2021-01-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 |  |  |  |  | MDC1.C4.C1130: FS | MDC1.C4.C1170: FS |  | 0 | 0 |  | ['682: FS'] | ['630: FS']
90 | Not Started | MDC1-BL.4.10.3.2.4 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-4 Cell- 3 | 2021-02-26 07:00 |  |  |  | 2021-02-26 07:00 |  | 0 | 0 | 0 | 0 | 69 | 69 | Start On or After | 2021-02-26 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C3170: FS |  | 0 | 0 |  | ['1325: FS'] | ['531: FS']
91 | Not Started | MDC1-BL.4.10.3.2.4 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-4 Cell- 2 | 2021-01-28 07:00 |  |  |  | 2021-01-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 | Start On or After | 2021-01-28 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C2170: FS |  | 0 | 0 |  | ['1325: FS'] | ['634: FS']
92 | Not Started | MDC1-BL.4.10.3.2.4 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-4 Cell- 4 | 2021-02-26 07:00 |  |  |  | 2021-02-26 07:00 |  | 0 | 0 | 0 | 0 | 69 | 69 | Start On or After | 2021-02-26 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C4170: FS |  | 0 | 0 |  | ['1325: FS'] | ['534: FS']
93 | Not Started | MDC1-BL.4.10.2.2.1 | Start Milestone | UPM ROJ COLO-1 Cell-1 | 2020-09-03 07:00 |  |  |  | 2020-09-03 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 |  |  |  |  | MDC1.C1.C1010: FS | MDC1.C1.C1040: FS |  | 0 | 0 |  | ['1277: FS'] | ['1270: FS']
94 | Not Started | MDC1-BL.4.10.3.3.1 | Start Milestone | MDC1 Deliery -UPM ROJ COLO-1 Cell-1 | 2020-09-03 07:00 |  |  |  | 2020-09-03 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 | Start On or After | 2020-09-03 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C1040: FS |  | 0 | 0 |  | ['1325: FS'] | ['1270: FS']
95 | Not Started | MDC1-BL.4.10.2.2.1 | Start Milestone | UPM ROJ COLO-1 Cell-3 | 2020-09-19 07:00 |  |  |  | 2020-09-19 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MDC1.C1.C3020: FS | MDC1.C1.C3040: FS |  | 0 | 0 |  | ['1253: FS'] | ['1235: FS']
96 | Not Started | MDC1-BL.4.10.3.3.1 | Start Milestone | MDC1 Deliery -UPM ROJ COLO-1 Cell-3 | 2020-09-19 07:00 |  |  |  | 2020-09-19 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2020-09-19 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C3040: FS |  | 0 | 0 |  | ['1325: FS'] | ['1235: FS']
97 | Not Started | MDC1-BL.4.10.3.3.1 | Start Milestone | MDC1 Deliery -UPM ROJ COLO-1 Cell-2 | 2020-09-03 07:00 |  |  |  | 2020-09-03 07:00 |  | 0 | 0 | 0 | 0 | 55 | 55 | Start On or After | 2020-09-03 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C2040: FS |  | 0 | 0 |  | ['1325: FS'] | ['1271: FS']
98 | Not Started | MDC1-BL.4.10.2.2.1 | Start Milestone | UPM ROJ COLO-1 Cell-2 | 2020-09-03 07:00 |  |  |  | 2020-09-03 07:00 |  | 0 | 0 | 0 | 0 | 55 | 55 |  |  |  |  | MDC1.C1.C2010: FS | MDC1.C1.C2040: FS |  | 0 | 0 |  | ['1278: FS'] | ['1271: FS']
99 | Not Started | MDC1-BL.4.10.2.2.1 | Start Milestone | UPM ROJ COLO-1 Cell-4 | 2020-09-19 07:00 |  |  |  | 2020-09-19 07:00 |  | 0 | 0 | 0 | 0 | 39 | 39 |  |  |  |  | MDC1.C1.C4020: FS | MDC1.C1.C4040: FS |  | 0 | 0 |  | ['1254: FS'] | ['1236: FS']
100 | Not Started | MDC1-BL.4.10.3.3.1 | Start Milestone | MDC1 Deliery -UPM ROJ COLO-1 Cell-4 | 2020-09-19 07:00 |  |  |  | 2020-09-19 07:00 |  | 0 | 0 | 0 | 0 | 39 | 39 | Start On or After | 2020-09-19 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C4040: FS |  | 0 | 0 |  | ['1325: FS'] | ['1236: FS']
101 | Not Started | MDC1-BL.4.10.2.2.2 | Start Milestone | UPM - ROJ - COLO2- Cell-1 | 2020-10-05 07:00 |  |  |  | 2020-10-05 07:00 |  | 0 | 0 | 0 | 0 | 33 | 33 |  |  |  |  | MDC1.C2.C1020: FS | MDC1.C2.C1030: FS |  | 0 | 0 |  | ['1209: FS'] | ['1194: FS']
102 | Not Started | MDC1-BL.4.10.3.3.2 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO2- Cell-1 | 2020-10-05 07:00 |  |  |  | 2020-10-05 07:00 |  | 0 | 0 | 0 | 0 | 33 | 33 | Start On or After | 2020-10-05 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C1030: FS |  | 0 | 0 |  | ['1325: FS'] | ['1194: FS']
103 | Not Started | MDC1-BL.4.10.2.2.2 | Start Milestone | UPM - ROJ - COLO2- Cell-3 | 2020-10-19 07:00 |  |  |  | 2020-10-19 07:00 |  | 0 | 0 | 0 | 0 | 21 | 21 |  |  |  |  | MDC1.C2.C3020: FS | MDC1.C2.C3040: FS |  | 0 | 0 |  | ['1160: FS'] | ['1138: FS']
104 | Not Started | MDC1-BL.4.10.3.3.2 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO2- Cell-3 | 2020-10-19 07:00 |  |  |  | 2020-10-19 07:00 |  | 0 | 0 | 0 | 0 | 21 | 21 | Start On or After | 2020-10-19 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C3040: FS |  | 0 | 0 |  | ['1325: FS'] | ['1138: FS']
105 | Not Started | MDC1-BL.4.10.3.3.2 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO2- Cell-2 | 2020-10-05 07:00 |  |  |  | 2020-10-05 07:00 |  | 0 | 0 | 0 | 0 | 37 | 37 | Start On or After | 2020-10-05 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C2020: FS |  | 0 | 0 |  | ['1325: FS'] | ['1195: FS']
106 | Not Started | MDC1-BL.4.10.2.2.2 | Start Milestone | UPM - ROJ - COLO2- Cell-2 | 2020-10-05 07:00 |  |  |  | 2020-10-05 07:00 |  | 0 | 0 | 0 | 0 | 37 | 37 |  |  |  |  | MDC1.C2.C2010: FS | MDC1.C2.C2020: FS |  | 0 | 0 |  | ['1210: FS'] | ['1195: FS']
107 | Not Started | MDC1-BL.4.10.2.2.2 | Start Milestone | UPM - ROJ - COLO2- Cell-4 | 2020-10-19 07:00 |  |  |  | 2020-10-19 07:00 |  | 0 | 0 | 0 | 0 | 25 | 25 |  |  |  |  | MDC1.C2.C4010: FS | MDC1.C2.C4030: FS |  | 0 | 0 |  | ['1161: FS'] | ['1139: FS']
108 | Not Started | MDC1-BL.4.10.3.3.2 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO2- Cell-4 | 2020-10-19 07:00 |  |  |  | 2020-10-19 07:00 |  | 0 | 0 | 0 | 0 | 25 | 25 | Start On or After | 2020-10-19 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C4030: FS |  | 0 | 0 |  | ['1325: FS'] | ['1139: FS']
109 | Not Started | MDC1-BL.4.10.2.2.3 | Start Milestone | UPM - ROJ - COLO3- Cell-1 | 2020-11-03 07:00 |  |  |  | 2020-11-03 07:00 |  | 0 | 0 | 0 | 0 | 13 | 13 |  |  |  |  | MDC1.C3.C1020: FS | MDC1.C3.C1040: FS |  | 0 | 0 |  | ['1105: FS'] | ['1074: FS']
110 | Not Started | MDC1-BL.4.10.3.3.3 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO3- Cell-1 | 2020-11-03 07:00 |  |  |  | 2020-11-03 07:00 |  | 0 | 0 | 0 | 0 | 13 | 13 | Start On or After | 2020-11-03 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C1040: FS |  | 0 | 0 |  | ['1325: FS'] | ['1074: FS']
111 | Not Started | MDC1-BL.4.10.2.2.3 | Start Milestone | UPM - ROJ - COLO3- Cell-3 | 2020-11-18 07:00 |  |  |  | 2020-11-18 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 |  |  |  |  | MDC1.C3.C3020: FS | MDC1.C3.C3040: FS |  | 0 | 0 |  | ['1036: FS'] | ['998: FS']
112 | Not Started | MDC1-BL.4.10.3.3.3 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO3- Cell-3 | 2020-11-18 07:00 |  |  |  | 2020-11-18 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 | Start On or After | 2020-11-18 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C3040: FS |  | 0 | 0 |  | ['1325: FS'] | ['998: FS']
113 | Not Started | MDC1-BL.4.10.2.2.3 | Start Milestone | UPM - ROJ - COLO3- Cell-2 | 2020-11-03 07:00 |  |  |  | 2020-11-03 07:00 |  | 0 | 0 | 0 | 0 | 19 | 19 |  |  |  |  | MDC1.C3.C2010: FS | MDC1.C3.C2040: FS |  | 0 | 0 |  | ['1106: FS'] | ['1075: FS']
114 | Not Started | MDC1-BL.4.10.3.3.3 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO3- Cell-2 | 2020-11-03 07:00 |  |  |  | 2020-11-03 07:00 |  | 0 | 0 | 0 | 0 | 19 | 19 | Start On or After | 2020-11-03 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C2040: FS |  | 0 | 0 |  | ['1325: FS'] | ['1075: FS']
115 | Not Started | MDC1-BL.4.10.2.2.3 | Start Milestone | UPM - ROJ - COLO3- Cell-4 | 2020-11-18 07:00 |  |  |  | 2020-11-18 07:00 |  | 0 | 0 | 0 | 0 | 3 | 3 |  |  |  |  | MDC1.C3.C4010: FS | MDC1.C3.C4040: FS |  | 0 | 0 |  | ['1037: FS'] | ['999: FS']
116 | Not Started | MDC1-BL.4.10.3.3.3 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO3- Cell-4 | 2020-11-18 07:00 |  |  |  | 2020-11-18 07:00 |  | 0 | 0 | 0 | 0 | 3 | 3 | Start On or After | 2020-11-18 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C4040: FS |  | 0 | 0 |  | ['1325: FS'] | ['999: FS']
117 | Not Started | MDC1-BL.4.10.2.2.4 | Start Milestone | UPM - ROJ - COLO-4 Cell- 1 | 2020-12-07 07:00 |  |  |  | 2020-12-07 07:00 |  | 0 | 0 | 0 | 0 | 12 | 12 |  |  |  |  | MDC1.C4.C1030: FS | MDC1.C4.C1040: FS |  | 0 | 0 |  | ['942: FS'] | ['901: FS']
118 | Not Started | MDC1-BL.4.10.3.3.4 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO-4 Cell- 1 | 2020-12-07 07:00 |  |  |  | 2020-12-07 07:00 |  | 0 | 0 | 0 | 0 | 12 | 12 | Start On or After | 2020-12-07 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C1040: FS |  | 0 | 0 |  | ['1325: FS'] | ['901: FS']
119 | Not Started | MDC1-BL.4.10.2.2.4 | Start Milestone | UPM - ROJ - COLO-4 Cell- 3 | 2020-12-21 07:00 |  |  |  | 2020-12-21 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MDC1.C4.C3030: FS | MDC1.C4.C3040: FS |  | 0 | 0 |  | ['852: FS'] | ['819: FS']
120 | Not Started | MDC1-BL.4.10.3.3.4 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO-4 Cell- 3 | 2020-12-21 07:00 |  |  |  | 2020-12-21 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2020-12-21 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C3040: FS |  | 0 | 0 |  | ['1325: FS'] | ['819: FS']
121 | Not Started | MDC1-BL.4.10.3.3.4 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO-4 Cell- 2 | 2020-12-07 07:00 |  |  |  | 2020-12-07 07:00 |  | 0 | 0 | 0 | 0 | 12 | 12 | Start On or After | 2020-12-07 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C2040: FS |  | 0 | 0 |  | ['1325: FS'] | ['902: FS']
122 | Not Started | MDC1-BL.4.10.2.2.4 | Start Milestone | UPM - ROJ - COLO-4 Cell- 2 | 2020-12-07 07:00 |  |  |  | 2020-12-07 07:00 |  | 0 | 0 | 0 | 0 | 12 | 12 |  |  |  |  | MDC1.C4.C2030: FS | MDC1.C4.C2040: FS |  | 0 | 0 |  | ['943: FS'] | ['902: FS']
123 | Not Started | MDC1-BL.4.10.2.2.4 | Start Milestone | UPM - ROJ - COLO-4 Cell- 4 | 2020-12-21 07:00 |  |  |  | 2020-12-21 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MDC1.C4.C4030: FS | MDC1.C4.C4040: FS |  | 0 | 0 |  | ['853: FS'] | ['820: FS']
124 | Not Started | MDC1-BL.4.10.3.3.4 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO-4 Cell- 4 | 2020-12-21 07:00 |  |  |  | 2020-12-21 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2020-12-21 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C4040: FS |  | 0 | 0 |  | ['1325: FS'] | ['820: FS']
125 | Not Started | MDC1-BL.4.10.2.3.1 | Start Milestone | Fluid Cooler - ROJ COLO -1 Cell- 1 | 2020-09-19 07:00 |  |  |  | 2020-09-19 07:00 |  | 0 | 0 | 0 | 0 | 48 | 48 |  |  |  |  | MDC1.C1.C1070: FS | MDC1.C1.C1110: FS |  | 0 | 0 |  | ['1252: FS'] | ['1207: FS']
126 | Not Started | MDC1-BL.4.10.3.4.1 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -1 Cell- 1 | 2020-09-19 07:00 |  |  |  | 2020-09-19 07:00 |  | 0 | 0 | 0 | 0 | 48 | 48 | Start On or After | 2020-09-19 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C1110: FS |  | 0 | 0 |  | ['1325: FS'] | ['1207: FS']
127 | Not Started | MDC1-BL.4.10.2.3.1 | Start Milestone | Fluid Cooler - ROJ COLO -1 Cell- 3 | 2020-10-15 07:00 |  |  |  | 2020-10-15 07:00 |  | 0 | 0 | 0 | 0 | 38 | 38 |  |  |  |  | MDC1.C1.C3100: FS | MDC1.C1.C3130: FS |  | 0 | 0 |  | ['1174: FS'] | ['1117: FS']
128 | Not Started | MDC1-BL.4.10.3.4.1 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -1 Cell- 3 | 2020-10-15 07:00 |  |  |  | 2020-10-15 07:00 |  | 0 | 0 | 0 | 0 | 38 | 38 | Start On or After | 2020-10-15 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C3130: FS |  | 0 | 0 |  | ['1325: FS'] | ['1117: FS']
129 | Not Started | MDC1-BL.4.10.2.3.1 | Start Milestone | Fluid Cooler - ROJ COLO -1 Cell- 2 | 2020-09-26 07:00 |  |  |  | 2020-09-26 07:00 |  | 0 | 0 | 0 | 0 | 49 | 49 |  |  |  |  | MDC1.C1.C2070: FS | MDC1.C1.C2120: FS |  | 0 | 0 |  | ['1232: FS'] | ['1185: FS']
130 | Not Started | MDC1-BL.4.10.3.4.1 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -1 Cell- 2 | 2020-09-26 07:00 |  |  |  | 2020-09-26 07:00 |  | 0 | 0 | 0 | 0 | 49 | 49 | Start On or After | 2020-09-26 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C2120: FS |  | 0 | 0 |  | ['1325: FS'] | ['1185: FS']
131 | Not Started | MDC1-BL.4.10.2.3.1 | Start Milestone | Fluid Cooler - ROJ COLO -1 Cell- 4 | 2020-10-12 07:00 |  |  |  | 2020-10-12 07:00 |  | 0 | 0 | 0 | 0 | 48 | 48 |  |  |  |  | MDC1.C1.C4080: FS | MDC1.C1.C4120: FS |  | 0 | 0 |  | ['1186: FS'] | ['1132: FS']
132 | Not Started | MDC1-BL.4.10.3.4.1 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -1 Cell- 4 | 2020-10-12 07:00 |  |  |  | 2020-10-12 07:00 |  | 0 | 0 | 0 | 0 | 48 | 48 | Start On or After | 2020-10-12 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C4120: FS |  | 0 | 0 |  | ['1325: FS'] | ['1132: FS']
133 | Not Started | MDC1-BL.4.10.2.3.2 | Start Milestone | Fluid Cooler - ROJ COLO -2 Cell-1 | 2020-10-27 07:00 |  |  |  | 2020-10-27 07:00 |  | 0 | 0 | 0 | 0 | 50 | 50 |  |  |  |  | MDC1.C2.C1070: FS | MDC1.C2.C1120: FS |  | 0 | 0 |  | ['1133: FS'] | ['1064: FS']
134 | Not Started | MDC1-BL.4.10.3.4.2 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -2 Cell-1 | 2020-10-27 07:00 |  |  |  | 2020-10-27 07:00 |  | 0 | 0 | 0 | 0 | 50 | 50 | Start On or After | 2020-10-27 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C1120: FS |  | 0 | 0 |  | ['1325: FS'] | ['1064: FS']
135 | Not Started | MDC1-BL.4.10.2.3.2 | Start Milestone | Fluid Cooler - ROJ COLO -2 Cell-3 | 2020-11-10 07:00 |  |  |  | 2020-11-10 07:00 |  | 0 | 0 | 0 | 0 | 49 | 49 |  |  |  |  | MDC1.C2.C3070: FS | MDC1.C2.C3120: FS |  | 0 | 0 |  | ['1065: FS'] | ['986: FS']
136 | Not Started | MDC1-BL.4.10.3.4.2 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -2 Cell-3 | 2020-11-10 07:00 |  |  |  | 2020-11-10 07:00 |  | 0 | 0 | 0 | 0 | 49 | 49 | Start On or After | 2020-11-10 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C3120: FS |  | 0 | 0 |  | ['1325: FS'] | ['986: FS']
137 | Not Started | MDC1-BL.4.10.2.3.2 | Start Milestone | Fluid Cooler - ROJ COLO -2 Cell-2 | 2020-11-10 07:00 |  |  |  | 2020-11-10 07:00 |  | 0 | 0 | 0 | 0 | 34 | 34 |  |  |  |  | MDC1.C2.C2110: FS | MDC1.C2.C2170: FS |  | 0 | 0 |  | ['1066: FS'] | ['987: FS']
138 | Not Started | MDC1-BL.4.10.3.4.2 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -2 Cell-2 | 2020-11-10 07:00 |  |  |  | 2020-11-10 07:00 |  | 0 | 0 | 0 | 0 | 34 | 34 | Start On or After | 2020-11-10 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C2170: FS |  | 0 | 0 |  | ['1325: FS'] | ['987: FS']
139 | Not Started | MDC1-BL.4.10.2.3.3 | Start Milestone | Fluid Cooler - ROJ COLO -3 Cell-1 | 2020-11-25 07:00 |  |  |  | 2020-11-25 07:00 |  | 0 | 0 | 0 | 0 | 54 | 54 |  |  |  |  | MDC1.C3.C1100: FS | MDC1.C3.C1160: FS |  | 0 | 0 |  | ['988: FS'] | ['888: FS']
140 | Not Started | MDC1-BL.4.10.3.4.3 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -3 Cell-1 | 2020-11-25 07:00 |  |  |  | 2020-11-25 07:00 |  | 0 | 0 | 0 | 0 | 54 | 54 | Start On or After | 2020-11-25 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C1160: FS |  | 0 | 0 |  | ['1325: FS'] | ['888: FS']
141 | Not Started | MDC1-BL.4.10.2.3.3 | Start Milestone | Fluid Cooler - ROJ COLO -3 Cell-2 | 2020-11-25 07:00 |  |  |  | 2020-11-25 07:00 |  | 0 | 0 | 0 | 0 | 54 | 54 |  |  |  |  | MDC1.C3.C2100: FS | MDC1.C3.C2160: FS |  | 0 | 0 |  | ['989: FS'] | ['889: FS']
142 | Not Started | MDC1-BL.4.10.3.4.3 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -3 Cell-2 | 2020-11-25 07:00 |  |  |  | 2020-11-25 07:00 |  | 0 | 0 | 0 | 0 | 54 | 54 | Start On or After | 2020-11-25 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C2160: FS |  | 0 | 0 |  | ['1325: FS'] | ['889: FS']
143 | Not Started | MDC1-BL.4.10.3.4.3 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -3 Cell-4 | 2020-12-14 07:00 |  |  |  | 2020-12-14 07:00 |  | 0 | 0 | 0 | 0 | 62 | 62 | Start On or After | 2020-12-14 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C4130: FS |  | 0 | 0 |  | ['1325: FS'] | ['800: FS']
144 | Not Started | MDC1-BL.4.10.2.3.3 | Start Milestone | Fluid Cooler - ROJ COLO -3 Cell-4 | 2020-12-14 07:00 |  |  |  | 2020-12-14 07:00 |  | 0 | 0 | 0 | 0 | 62 | 62 |  |  |  |  | MDC1.C3.C4090: FS | MDC1.C3.C4130: FS |  | 0 | 0 |  | ['890: FS'] | ['800: FS']
145 | Not Started | MDC1-BL.4.10.2.3.4 | Start Milestone | Fluid Cooler - ROJ COLO -4 Cell-1 | 2021-01-02 07:00 |  |  |  | 2021-01-02 07:00 |  | 0 | 0 | 0 | 0 | 62 | 62 |  |  |  |  | MDC1.C4.C1080: FS | MDC1.C4.C1110: FS |  | 0 | 0 |  | ['801: FS'] | ['720: FS']
146 | Not Started | MDC1-BL.4.10.3.4.4 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -4 Cell-1 | 2021-01-02 07:00 |  |  |  | 2021-01-02 07:00 |  | 0 | 0 | 0 | 0 | 62 | 62 | Start On or After | 2021-01-02 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C1110: FS |  | 0 | 0 |  | ['1325: FS'] | ['720: FS']
147 | Not Started | MDC1-BL.4.10.2.3.4 | Start Milestone | Fluid Cooler - ROJ COLO -4 Cell-3 | 2021-01-18 07:00 |  |  |  | 2021-01-18 07:00 |  | 0 | 0 | 0 | 0 | 75 | 75 |  |  |  |  | MDC1.C4.C3080: FS | MDC1.C4.C3110: FS |  | 0 | 0 |  | ['721: FS'] | ['667: FS']
148 | Not Started | MDC1-BL.4.10.3.4.4 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -4 Cell-3 | 2021-01-18 07:00 |  |  |  | 2021-01-18 07:00 |  | 0 | 0 | 0 | 0 | 75 | 75 | Start On or After | 2021-01-18 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C3110: FS |  | 0 | 0 |  | ['1325: FS'] | ['667: FS']
149 | Not Started | MDC1-BL.4.10.2.3.4 | Start Milestone | Fluid Cooler - ROJ COLO -4 Cell-2 | 2021-01-02 07:00 |  |  |  | 2021-01-02 07:00 |  | 0 | 0 | 0 | 0 | 62 | 62 |  |  |  |  | MDC1.C4.C2080: FS | MDC1.C4.C2110: FS |  | 0 | 0 |  | ['804: FS'] | ['723: FS']
150 | Not Started | MDC1-BL.4.10.3.4.4 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -4 Cell-2 | 2021-01-02 07:00 |  |  |  | 2021-01-02 07:00 |  | 0 | 0 | 0 | 0 | 62 | 62 | Start On or After | 2021-01-02 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C2110: FS |  | 0 | 0 |  | ['1325: FS'] | ['723: FS']
151 | Not Started | MDC1-BL.4.10.2.3.4 | Start Milestone | Fluid Cooler - ROJ COLO -4 Cell-4 | 2021-01-18 07:00 |  |  |  | 2021-01-18 07:00 |  | 0 | 0 | 0 | 0 | 75 | 75 |  |  |  |  | MDC1.C4.C4080: FS | MDC1.C4.C4110: FS |  | 0 | 0 |  | ['724: FS'] | ['668: FS']
152 | Not Started | MDC1-BL.4.10.3.4.4 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -4 Cell-4 | 2021-01-18 07:00 |  |  |  | 2021-01-18 07:00 |  | 0 | 0 | 0 | 0 | 75 | 75 | Start On or After | 2021-01-18 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C4110: FS |  | 0 | 0 |  | ['1325: FS'] | ['668: FS']
153 | Not Started | MDC1-BL.4.10.2.4.1 | Start Milestone | Generator ROJ COLO 1- Cell-1 | 2020-09-15 07:00 |  |  |  | 2020-09-15 07:00 |  | 0 | 0 | 0 | 0 | 52 | 52 |  |  |  |  | MDC1.C1.C1050: FS | MDC1.C1.C1090: FS |  | 0 | 0 |  | ['1261: FS'] | ['1218: FS']
154 | Not Started | MDC1-BL.4.10.3.5.1 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 1- Cell-1 | 2020-09-15 07:00 |  |  |  | 2020-09-15 07:00 |  | 0 | 0 | 0 | 0 | 52 | 52 | Start On or After | 2020-09-15 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C1090: FS |  | 0 | 0 |  | ['1325: FS'] | ['1218: FS']
155 | Not Started | MDC1-BL.4.10.2.4.1 | Start Milestone | Generator ROJ COLO 1- Cell-3 | 2020-09-29 07:00 |  |  |  | 2020-09-29 07:00 |  | 0 | 0 | 0 | 0 | 41 | 41 |  |  |  |  | MDC1.C1.C3050: FS | MDC1.C1.C3080: FS |  | 0 | 0 |  | ['1220: FS'] | ['1179: FS']
156 | Not Started | MDC1-BL.4.10.3.5.1 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 1- Cell-3 | 2020-09-29 07:00 |  |  |  | 2020-09-29 07:00 |  | 0 | 0 | 0 | 0 | 41 | 41 | Start On or After | 2020-09-29 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C3080: FS |  | 0 | 0 |  | ['1325: FS'] | ['1179: FS']
157 | Not Started | MDC1-BL.4.10.2.4.1 | Start Milestone | Generator ROJ COLO 1- Cell-2 | 2020-09-15 07:00 |  |  |  | 2020-09-15 07:00 |  | 0 | 0 | 0 | 0 | 59 | 59 |  |  |  |  | MDC1.C1.C2050: FS | MDC1.C1.C2090: FS |  | 0 | 0 |  | ['1264: FS'] | ['1221: FS']
158 | Not Started | MDC1-BL.4.10.3.5.1 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 1- Cell-2 | 2020-09-15 07:00 |  |  |  | 2020-09-15 07:00 |  | 0 | 0 | 0 | 0 | 59 | 59 | Start On or After | 2020-09-15 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C2090: FS |  | 0 | 0 |  | ['1325: FS'] | ['1221: FS']
159 | Not Started | MDC1-BL.4.10.2.4.1 | Start Milestone | Generator ROJ COLO 1- Cell-4 | 2020-09-29 07:00 |  |  |  | 2020-09-29 07:00 |  | 0 | 0 | 0 | 0 | 58 | 58 |  |  |  |  | MDC1.C1.C4050: FS | MDC1.C1.C4090: FS |  | 0 | 0 |  | ['1222: FS'] | ['1180: FS']
160 | Not Started | MDC1-BL.4.10.3.5.1 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 1- Cell-4 | 2020-09-29 07:00 |  |  |  | 2020-09-29 07:00 |  | 0 | 0 | 0 | 0 | 58 | 58 | Start On or After | 2020-09-29 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C4090: FS |  | 0 | 0 |  | ['1325: FS'] | ['1180: FS']
161 | Not Started | MDC1-BL.4.10.3.5.2 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 2- Cell - 1 | 2020-10-14 07:00 |  |  |  | 2020-10-14 07:00 |  | 0 | 0 | 0 | 0 | 60 | 60 | Start On or After | 2020-10-14 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C1080: FS |  | 0 | 0 |  | ['1325: FS'] | ['1122: FS']
162 | Not Started | MDC1-BL.4.10.2.4.2 | Start Milestone | Generator ROJ COLO 2- Cell - 1 | 2020-10-14 07:00 |  |  |  | 2020-10-14 07:00 |  | 0 | 0 | 0 | 0 | 60 | 60 |  |  |  |  | MDC1.C2.C1040: FS | MDC1.C2.C1080: FS |  | 0 | 0 |  | ['1181: FS'] | ['1122: FS']
163 | Not Started | MDC1-BL.4.10.2.4.2 | Start Milestone | Generator ROJ COLO 2- Cell - 3 | 2020-10-29 07:00 |  |  |  | 2020-10-29 07:00 |  | 0 | 0 | 0 | 0 | 59 | 59 |  |  |  |  | MDC1.C2.C3050: FS | MDC1.C2.C3080: FS |  | 0 | 0 |  | ['1123: FS'] | ['1052: FS']
164 | Not Started | MDC1-BL.4.10.3.5.2 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 2- Cell - 3 | 2020-10-29 07:00 |  |  |  | 2020-10-29 07:00 |  | 0 | 0 | 0 | 0 | 59 | 59 | Start On or After | 2020-10-29 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C3080: FS |  | 0 | 0 |  | ['1325: FS'] | ['1052: FS']
165 | Not Started | MDC1-BL.4.10.2.4.2 | Start Milestone | Generator ROJ COLO 2- Cell - 2 | 2020-10-14 07:00 |  |  |  | 2020-10-14 07:00 |  | 0 | 0 | 0 | 0 | 56 | 56 |  |  |  |  | MDC1.C2.C2030: FS | MDC1.C2.C2060: FS |  | 0 | 0 |  | ['1183: FS'] | ['1124: FS']
166 | Not Started | MDC1-BL.4.10.3.5.2 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 2- Cell - 2 | 2020-10-14 07:00 |  |  |  | 2020-10-14 07:00 |  | 0 | 0 | 0 | 0 | 56 | 56 | Start On or After | 2020-10-14 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C2060: FS |  | 0 | 0 |  | ['1325: FS'] | ['1124: FS']
167 | Not Started | MDC1-BL.4.10.2.4.2 | Start Milestone | Generator ROJ COLO 2- Cell - 4 | 2020-10-29 07:00 |  |  |  | 2020-10-29 07:00 |  | 0 | 0 | 0 | 0 | 64 | 64 |  |  |  |  | MDC1.C2.C4040: FS | MDC1.C2.C4060: FS |  | 0 | 0 |  | ['1125: FS'] | ['1053: FS']
168 | Not Started | MDC1-BL.4.10.3.5.2 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 2- Cell - 4 | 2020-10-29 07:00 |  |  |  | 2020-10-29 07:00 |  | 0 | 0 | 0 | 0 | 64 | 64 | Start On or After | 2020-10-29 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C4060: FS |  | 0 | 0 |  | ['1325: FS'] | ['1053: FS']
169 | Not Started | MDC1-BL.4.10.2.4.3 | Start Milestone | Generator ROJ COLO 3- Cell - 1 | 2020-11-12 07:00 |  |  |  | 2020-11-12 07:00 |  | 0 | 0 | 0 | 0 | 64 | 64 |  |  |  |  | MDC1.C3.C1050: FS | MDC1.C3.C1110: FS |  | 0 | 0 |  | ['1054: FS'] | ['972: FS']
170 | Not Started | MDC1-BL.4.10.3.5.3 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 3- Cell - 1 | 2020-11-12 07:00 |  |  |  | 2020-11-12 07:00 |  | 0 | 0 | 0 | 0 | 64 | 64 | Start On or After | 2020-11-12 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C1110: FS |  | 0 | 0 |  | ['1325: FS'] | ['972: FS']
171 | Not Started | MDC1-BL.4.10.2.4.3 | Start Milestone | Generator ROJ COLO 3- Cell - 3 | 2020-12-01 07:00 |  |  |  | 2020-12-01 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 |  |  |  |  | MDC1.C3.C3050: FS | MDC1.C3.C3080: FS |  | 0 | 0 |  | ['973: FS'] | ['874: FS']
172 | Not Started | MDC1-BL.4.10.3.5.3 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 3- Cell - 3 | 2020-12-01 07:00 |  |  |  | 2020-12-01 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 | Start On or After | 2020-12-01 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C3080: FS |  | 0 | 0 |  | ['1325: FS'] | ['874: FS']
173 | Not Started | MDC1-BL.4.10.2.4.3 | Start Milestone | Generator ROJ COLO 3- Cell - 2 | 2020-11-12 07:00 |  |  |  | 2020-11-12 07:00 |  | 0 | 0 | 0 | 0 | 64 | 64 |  |  |  |  | MDC1.C3.C2050: FS | MDC1.C3.C2110: FS |  | 0 | 0 |  | ['1056: FS'] | ['974: FS']
174 | Not Started | MDC1-BL.4.10.3.5.3 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 3- Cell - 2 | 2020-11-12 07:00 |  |  |  | 2020-11-12 07:00 |  | 0 | 0 | 0 | 0 | 64 | 64 | Start On or After | 2020-11-12 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C2110: FS |  | 0 | 0 |  | ['1325: FS'] | ['974: FS']
175 | Not Started | MDC1-BL.4.10.2.4.3 | Start Milestone | Generator ROJ COLO 3- Cell - 4 | 2020-12-01 07:00 |  |  |  | 2020-12-01 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 |  |  |  |  | MDC1.C3.C4050: FS | MDC1.C3.C4100: FS |  | 0 | 0 |  | ['975: FS'] | ['875: FS']
176 | Not Started | MDC1-BL.4.10.3.5.3 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 3- Cell - 4 | 2020-12-01 07:00 |  |  |  | 2020-12-01 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 | Start On or After | 2020-12-01 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C4100: FS |  | 0 | 0 |  | ['1325: FS'] | ['875: FS']
177 | Not Started | MDC1-BL.4.10.2.4.4 | Start Milestone | Generator ROJ COLO 4- Cell - 3 | 2021-01-05 07:00 |  |  |  | 2021-01-05 07:00 |  | 0 | 0 | 0 | 0 | 82 | 82 |  |  |  |  | MDC1.C4.C3060: FS | MDC1.C4.C3100: FS |  | 0 | 0 |  | ['790: FS'] | ['712: FS']
178 | Not Started | MDC1-BL.4.10.3.5.4 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 4- Cell - 3 | 2021-01-05 07:00 |  |  |  | 2021-01-05 07:00 |  | 0 | 0 | 0 | 0 | 82 | 82 | Start On or After | 2021-01-05 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C3100: FS |  | 0 | 0 |  | ['1325: FS'] | ['712: FS']
179 | Not Started | MDC1-BL.4.10.2.4.4 | Start Milestone | Generator ROJ COLO 4- Cell - 2 | 2020-12-16 07:00 |  |  |  | 2020-12-16 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 |  |  |  |  | MDC1.C4.C2060: FS | MDC1.C4.C2100: FS |  | 0 | 0 |  | ['878: FS'] | ['791: FS']
180 | Not Started | MDC1-BL.4.10.3.5.4 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 4- Cell - 2 | 2020-12-16 07:00 |  |  |  | 2020-12-16 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 | Start On or After | 2020-12-16 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C2100: FS |  | 0 | 0 |  | ['1325: FS'] | ['791: FS']
181 | Not Started | MDC1-BL.4.10.2.4.4 | Start Milestone | Generator ROJ COLO 4- Cell - 4 | 2021-01-05 07:00 |  |  |  | 2021-01-05 07:00 |  | 0 | 0 | 0 | 0 | 84 | 84 |  |  |  |  | MDC1.C4.C4060: FS | MDC1.C4.C4100: FS |  | 0 | 0 |  | ['792: FS'] | ['713: FS']
182 | Not Started | MDC1-BL.4.10.3.5.4 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 4- Cell - 4 | 2021-01-05 07:00 |  |  |  | 2021-01-05 07:00 |  | 0 | 0 | 0 | 0 | 84 | 84 | Start On or After | 2021-01-05 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C4100: FS |  | 0 | 0 |  | ['1325: FS'] | ['713: FS']
183 | Not Started | MDC1-BL.4.10.2.4.4 | Start Milestone | Generator ROJ COLO 4- Cell - 1 | 2020-12-16 07:00 |  |  |  | 2020-12-16 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 |  |  |  |  | MDC1.C4.C1060: FS | MDC1.C4.C1100: FS |  | 0 | 0 |  | ['876: FS'] | ['789: FS']
184 | Not Started | MDC1-BL.4.10.3.5.4 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 4- Cell - 1 | 2020-12-16 07:00 |  |  |  | 2020-12-16 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 | Start On or After | 2020-12-16 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C1100: FS |  | 0 | 0 |  | ['1325: FS'] | ['789: FS']
185 | Not Started | MDC1-BL.4.10.2.6.1 | Start Milestone | PDU ROJ COLO-1 Cell-1 | 2020-11-13 07:00 |  |  |  | 2020-11-13 07:00 |  | 0 | 0 | 0 | 0 | 27 | 27 |  |  |  |  | MDC1.C1.C1260: FS | MDC1.C1.C1270: FS |  | 0 | 0 |  | ['1049: FS'] | ['1034: FS']
186 | Not Started | MDC1-BL.4.10.3.6.1 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-1 Cell-1 | 2020-11-13 07:00 |  |  |  | 2020-11-13 07:00 |  | 0 | 0 | 0 | 0 | 27 | 27 | Start On or After | 2020-11-13 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C1270: FS |  | 0 | 0 |  | ['1325: FS'] | ['1034: FS']
187 | Not Started | MDC1-BL.4.10.2.6.1 | Start Milestone | PDU ROJ COLO-1 Cell-3 | 2020-11-30 07:00 |  |  |  | 2020-11-30 07:00 |  | 0 | 0 | 0 | 0 | 28 | 28 |  |  |  |  | MDC1.C1.C3220: FS | MDC1.C1.C3240: FS |  | 0 | 0 |  | ['982: FS'] | ['954: FS']
188 | Not Started | MDC1-BL.4.10.3.6.1 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-1 Cell-3 | 2020-11-30 07:00 |  |  |  | 2020-11-30 07:00 |  | 0 | 0 | 0 | 0 | 28 | 28 | Start On or After | 2020-11-30 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C3240: FS |  | 0 | 0 |  | ['1325: FS'] | ['954: FS']
189 | Not Started | MDC1-BL.4.10.2.6.1 | Start Milestone | PDU ROJ COLO-1 Cell-2 | 2020-11-13 07:00 |  |  |  | 2020-11-13 07:00 |  | 0 | 0 | 0 | 0 | 32 | 32 |  |  |  |  | MDC1.C1.C2240: FS | MDC1.C1.C2250: FS |  | 0 | 0 |  | ['1050: FS'] | ['1035: FS']
190 | Not Started | MDC1-BL.4.10.3.6.1 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-1 Cell-2 | 2020-11-13 07:00 |  |  |  | 2020-11-13 07:00 |  | 0 | 0 | 0 | 0 | 32 | 32 | Start On or After | 2020-11-13 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C2250: FS |  | 0 | 0 |  | ['1325: FS'] | ['1035: FS']
191 | Not Started | MDC1-BL.4.10.2.6.1 | Start Milestone | PDU ROJ COLO-1 Cell-4 | 2020-12-02 07:00 |  |  |  | 2020-12-02 07:00 |  | 0 | 0 | 0 | 0 | 30 | 30 |  |  |  |  | MDC1.C1.C4210: FS | MDC1.C1.C4220: FS |  | 0 | 0 |  | ['960: FS'] | ['941: FS']
192 | Not Started | MDC1-BL.4.10.3.6.1 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-1 Cell-4 | 2020-12-02 07:00 |  |  |  | 2020-12-02 07:00 |  | 0 | 0 | 0 | 0 | 30 | 30 | Start On or After | 2020-12-02 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C4220: FS |  | 0 | 0 |  | ['1325: FS'] | ['941: FS']
193 | Not Started | MDC1-BL.4.10.2.6.2 | Start Milestone | PDU ROJ COLO-2 Cell-1 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 31 | 31 |  |  |  |  | MDC1.C2.C1270: FS | MDC1.C2.C1300: FS |  | 0 | 0 |  | ['829: FS'] | ['797: FS']
194 | Not Started | MDC1-BL.4.10.3.6.2 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-2 Cell-1 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 31 | 31 | Start On or After | 2020-12-28 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C1300: FS |  | 0 | 0 |  | ['1325: FS'] | ['797: FS']
195 | Not Started | MDC1-BL.4.10.2.6.2 | Start Milestone | PDU ROJ COLO-2 Cell-3 | 2021-01-13 07:00 |  |  |  | 2021-01-13 07:00 |  | 0 | 0 | 0 | 0 | 13 | 13 |  |  |  |  | MDC1.C2.C3260: FS | MDC1.C2.C3290: FS |  | 0 | 0 |  | ['748: FS'] | ['717: FS']
196 | Not Started | MDC1-BL.4.10.3.6.2 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-2 Cell-3 | 2021-01-13 07:00 |  |  |  | 2021-01-13 07:00 |  | 0 | 0 | 0 | 0 | 13 | 13 | Start On or After | 2021-01-13 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C3290: FS |  | 0 | 0 |  | ['1325: FS'] | ['717: FS']
197 | Not Started | MDC1-BL.4.10.2.6.2 | Start Milestone | PDU ROJ COLO-2 Cell-2 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 25 | 25 |  |  |  |  | MDC1.C2.C2260: FS | MDC1.C2.C2280: FS |  | 0 | 0 |  | ['830: FS'] | ['798: FS']
198 | Not Started | MDC1-BL.4.10.3.6.2 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-2 Cell-2 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 25 | 25 | Start On or After | 2020-12-28 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C2280: FS |  | 0 | 0 |  | ['1325: FS'] | ['798: FS']
199 | Not Started | MDC1-BL.4.10.2.6.2 | Start Milestone | PDU ROJ COLO-2 Cell-4 | 2021-01-13 07:00 |  |  |  | 2021-01-13 07:00 |  | 0 | 0 | 0 | 0 | 13 | 13 |  |  |  |  | MDC1.C2.C4210: FS | MDC1.C2.C4240: FS |  | 0 | 0 |  | ['749: FS'] | ['718: FS']
200 | Not Started | MDC1-BL.4.10.3.6.2 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-2 Cell-4 | 2021-01-13 07:00 |  |  |  | 2021-01-13 07:00 |  | 0 | 0 | 0 | 0 | 13 | 13 | Start On or After | 2021-01-13 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C4240: FS |  | 0 | 0 |  | ['1325: FS'] | ['718: FS']
201 | Not Started | MDC1-BL.4.10.2.6.3 | Start Milestone | PDU ROJ COLO-3 Cell-1 | 2021-03-12 07:00 |  |  |  | 2021-03-12 07:00 |  | 0 | 0 | 0 | 0 | 4 | 4 |  |  |  |  | MDC1.C3.C1350: FS | MDC1.C3.C1390: FS |  | 0 | 0 |  | ['536: FS'] | ['515: FS']
202 | Not Started | MDC1-BL.4.10.3.6.3 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-3 Cell-1 | 2021-03-12 07:00 |  |  |  | 2021-03-12 07:00 |  | 0 | 0 | 0 | 0 | 4 | 4 | Start On or After | 2021-03-12 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C1390: FS |  | 0 | 0 |  | ['1325: FS'] | ['515: FS']
203 | Not Started | MDC1-BL.4.10.2.6.3 | Start Milestone | PDU ROJ COLO-3 Cell-3 | 2021-03-27 07:00 |  |  |  | 2021-03-27 07:00 |  | 0 | 0 | 0 | 0 | 2 | 2 |  |  |  |  | MDC1.C3.C3310: FS | MDC1.C3.C3340: FS |  | 0 | 0 |  | ['481: FS'] | ['467: FS']
204 | Not Started | MDC1-BL.4.10.3.6.3 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-3 Cell-3 | 2021-03-27 07:00 |  |  |  | 2021-03-27 07:00 |  | 0 | 0 | 0 | 0 | 2 | 2 | Start On or After | 2021-03-27 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C3340: FS |  | 0 | 0 |  | ['1325: FS'] | ['467: FS']
205 | Not Started | MDC1-BL.4.10.2.6.3 | Start Milestone | PDU ROJ COLO-3 Cell-2 | 2021-03-12 07:00 |  |  |  | 2021-03-12 07:00 |  | 0 | 0 | 0 | 0 | 4 | 4 |  |  |  |  | MDC1.C3.C2340: FS | MDC1.C3.C2370: FS |  | 0 | 0 |  | ['537: FS'] | ['516: FS']
206 | Not Started | MDC1-BL.4.10.3.6.3 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-3 Cell-2 | 2021-03-12 07:00 |  |  |  | 2021-03-12 07:00 |  | 0 | 0 | 0 | 0 | 4 | 4 | Start On or After | 2021-03-12 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C2370: FS |  | 0 | 0 |  | ['1325: FS'] | ['516: FS']
207 | Not Started | MDC1-BL.4.10.2.6.3 | Start Milestone | PDU ROJ COLO-3 Cell-4 | 2021-03-27 07:00 |  |  |  | 2021-03-27 07:00 |  | 0 | 0 | 0 | 0 | 2 | 2 |  |  |  |  | MDC1.C3.C4340: FS | MDC1.C3.C4360: FS |  | 0 | 0 |  | ['482: FS'] | ['468: FS']
208 | Not Started | MDC1-BL.4.10.3.6.3 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-3 Cell-4 | 2021-03-27 07:00 |  |  |  | 2021-03-27 07:00 |  | 0 | 0 | 0 | 0 | 2 | 2 | Start On or After | 2021-03-27 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C4360: FS |  | 0 | 0 |  | ['1325: FS'] | ['468: FS']
209 | Not Started | MDC1-BL.4.10.2.6.4 | Start Milestone | PDU ROJ COLO-4 Cell-1 | 2021-04-19 07:00 |  |  |  | 2021-04-19 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 |  |  |  |  | MDC1.C4.C1350: FS | MDC1.C4.C1370: FS |  | 0 | 0 |  | ['416: FS'] | ['401: FS']
210 | Not Started | MDC1-BL.4.10.3.6.4 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-4 Cell-1 | 2021-04-19 07:00 |  |  |  | 2021-04-19 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 | Start On or After | 2021-04-19 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C1370: FS |  | 0 | 0 |  | ['1325: FS'] | ['401: FS']
211 | Not Started | MDC1-BL.4.10.2.6.4 | Start Milestone | PDU ROJ COLO-4 Cell-3 | 2021-05-04 07:00 |  |  |  | 2021-05-04 07:00 |  | 0 | 0 | 0 | 0 | 6 | 6 |  |  |  |  | MDC1.C4.C3340: FS | MDC1.C4.C3360: FS |  | 0 | 0 |  | ['373: FS'] | ['359: FS']
212 | Not Started | MDC1-BL.4.10.3.6.4 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-4 Cell-3 | 2021-05-04 07:00 |  |  |  | 2021-05-04 07:00 |  | 0 | 0 | 0 | 0 | 6 | 6 | Start On or After | 2021-05-04 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C3360: FS |  | 0 | 0 |  | ['1325: FS'] | ['359: FS']
213 | Not Started | MDC1-BL.4.10.2.6.4 | Start Milestone | PDU ROJ COLO-4 Cell-2 | 2021-04-19 07:00 |  |  |  | 2021-04-19 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 |  |  |  |  | MDC1.C4.C2320: FS | MDC1.C4.C2350: FS |  | 0 | 0 |  | ['417: FS'] | ['402: FS']
214 | Not Started | MDC1-BL.4.10.3.6.4 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-4 Cell-2 | 2021-04-19 07:00 |  |  |  | 2021-04-19 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 | Start On or After | 2021-04-19 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C2350: FS |  | 0 | 0 |  | ['1325: FS'] | ['402: FS']
215 | Not Started | MDC1-BL.4.10.2.6.4 | Start Milestone | PDU ROJ COLO-4 Cell-4 | 2021-05-04 07:00 |  |  |  | 2021-05-04 07:00 |  | 0 | 0 | 0 | 0 | 6 | 6 |  |  |  |  | MDC1.C4.C4320: FS | MDC1.C4.C4350: FS |  | 0 | 0 |  | ['374: FS'] | ['360: FS']
216 | Not Started | MDC1-BL.4.10.3.6.4 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-4 Cell-4 | 2021-05-04 07:00 |  |  |  | 2021-05-04 07:00 |  | 0 | 0 | 0 | 0 | 6 | 6 | Start On or After | 2021-05-04 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C4350: FS |  | 0 | 0 |  | ['1325: FS'] | ['360: FS']
217 | Not Started | MDC1-BL.4.10.2.7 | Start Milestone | UMS - ROJ | 2020-11-04 07:00 |  |  |  | 2020-11-04 07:00 |  | 0 | 0 | 0 | 0 | 49 | 49 |  |  |  |  | MDC1.S.1370: FS | MDC1.S.1570: FS |  | 0 | 0 |  | ['1103: FS'] | ['1072: FS']
218 | Not Started | MDC1-BL.4.10.2.7 | Start Milestone | URS - ROJ | 2020-10-19 07:00 |  |  |  | 2020-10-19 07:00 |  | 0 | 0 | 0 | 0 | 21 | 21 |  |  |  |  | MDC1.S.1250: FS | MDC1.S.1310: FS |  | 0 | 0 |  | ['1162: FS'] | ['1114: FS']
219 | Completed | MDC1-BL.4.10.2.7 | Start Milestone | ATS- ROJ | 2020-06-29 07:00 |  | 2020-06-27 |  | 2020-06-29 07:00 | 2020-06-27 | 100 | 0 | 0 | 0 | [6 empty] | MDC1AD-1016: FS | MDC1AD-1019: FS |  | 0 | 0 |  | ['1129: FS'] | ['882: FS']
220 | Not Started | MDC1-BL.4.10.2.7 | Start Milestone | MSB - ROJ | 2020-10-28 07:00 |  |  |  | 2020-10-28 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 |  |  |  |  | MDC1AD-1016: FS | MDC1AD-1019: FS |  | 0 | 0 |  | ['1129: FS'] | ['882: FS']
221 | Not Started | MDC1-BL.4.10.2.7 | Start Milestone | TCP - ROJ | 2020-10-28 07:00 |  |  |  | 2020-10-28 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 |  |  |  |  | MDC1AD-1016: FS | MDC1AD-1019: FS |  | 0 | 0 |  | ['1129: FS'] | ['882: FS']
222 | Not Started | MDC1-BL.4.10.2.7 | Start Milestone | UPS- ROJ | 2020-10-28 07:00 |  |  |  | 2020-10-28 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 |  |  |  |  | MDC1AD-1016: FS | MDC1AD-1019: FS |  | 0 | 0 |  | ['1129: FS'] | ['882: FS']
223 | Not Started | MDC1-BL.4.10.3.7 | Start Milestone | MDC1 Deliery -UMS - ROJ | 2020-10-05 07:00 |  |  |  | 2020-10-05 07:00 |  | 0 | 0 | 0 | 0 | 74 | 74 | Start On or After | 2020-11-04 07:00 |  |  | MDC1-2527: FS | MDC1.S.1570: FS |  | 0 | 0 |  | ['1325: FS'] | ['1072: FS']
224 | Not Started | MDC1-BL.4.10.3.7 | Start Milestone | MDC1 Deliery -URS - ROJ | 2020-09-26 07:00 |  |  |  | 2020-09-26 07:00 |  | 0 | 0 | 0 | 0 | 39 | 39 | Start On or After | 2020-09-26 07:00 |  |  | MDC1-2527: FS | MDC1.S.1310: FS |  | 0 | 0 |  | ['1325: FS'] | ['1114: FS']
225 | Completed | MDC1-BL.4.10.3.7 | Start Milestone | MDC1 Deliery -ATS- ROJ | 2020-06-29 07:00 |  | 2020-06-27 |  | 2020-06-29 07:00 | 2020-06-27 | 100 | 0 | 0 | 0 |  |  | Start On or After | 2020-06-27 |  |  | MDC1-2527: FS, MDC1-2527: SS | MDC1AD-1019: FS |  | 0 | 0 |  | ['1325: FS', '1325: SS'] | ['882: FS']
226 | Not Started | MDC1-BL.4.10.3.7 | Start Milestone | MDC1 Deliery -MSB - ROJ | 2020-10-12 07:00 |  |  |  | 2020-10-12 07:00 |  | 0 | 0 | 0 | 0 | 21 | 21 | Start On or After | 2020-10-28 |  |  | MDC1-2527: FS | MDC1AD-1019: FS |  | 0 | 0 |  | ['1325: FS'] | ['882: FS']
227 | Not Started | MDC1-BL.4.10.3.7 | Start Milestone | MDC1 Deliery -TCP - ROJ | 2020-10-28 07:00 |  |  |  | 2020-10-28 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 | Start On or After | 2020-10-28 07:00 |  |  | MDC1-2527: FS | MDC1AD-1019: FS |  | 0 | 0 |  | ['1325: FS'] | ['882: FS']
228 | Not Started | MDC1-BL.4.10.3.7 | Start Milestone | MDC1 Deliery -UPS- ROJ | 2020-10-28 07:00 |  |  |  | 2020-10-28 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 | Start On or After | 2020-10-28 07:00 |  |  | MDC1-2527: FS | MDC1AD-1019: FS |  | 0 | 0 |  | ['1325: FS'] | ['882: FS']
229 | Not Started | MDC1-BL.1 | Finish Milestone | Project Completion |  | 2021-10-29 16:00 |  |  | 2021-10-29 16:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MDC1.C3.Cx4020: FS, MDC1.C2.Cx4020: FS, MDC1.C1.Cx4020: FS, MDC1-C1.P2200: FS, MDC1.C2.Cx4020: FF, MDC1.C3.Cx4020: FF, MDC1-C1.P2200: FF, MDC1-C2.P2200: FS, MDC1-C3.P2200: FS, MDC1-C4.P2200: FS, MDC1.M1010: FS, MDC1.M4010: FS |  |  | 0 | 0 |  | ['238: FS', '249: FS', '267: FS', '256: FS', '249: FF', '238: FF', '256: FF', '250: FS', '239: FS', '231: FS', '344: FS', '235: FS'] | []
230 | Not Started | MDC1-BL.5.2.12.5 | Task Dependent | Punch List/ Lock down COLO-4 | 2021-10-09 08:00 | 2021-10-29 16:00 |  |  |  |  | 0 | 0 | 21 | 21 | 0 | 0 |  |  |  |  | MDC1.C4.Cx4000: FS, MDC1.C4.Cx4000: FF, MDC1-C4.P2100: FS | MDC1-C4.P2200: FS | VECA Electricians | 2240 | 0 |  | ['232: FS', '232: FF', '233: FS'] | ['231: FS']
231 | Not Started | MDC1-BL.3.5 | Finish Milestone | Ready for Lock down COLO 4 |  | 2021-10-29 16:00 |  |  | 2021-10-29 16:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MDC1.C4.Cx4020: FS, MDC1.C4.Cx4010: FS | MDC1.M6010: FS |  | 0 | 0 |  | ['230: FS', '234: FS'] | ['229: FS']
232 | Not Started | MDC1-BL.5.2.12.5 | Task Dependent | COLO 4 Level 4 & Level 5 IST | 2021-09-18 08:00 | 2021-10-08 16:00 |  |  |  |  | 0 | 0 | 21 | 21 | 0 | 0 |  |  |  |  | MDC1.C4.C4460: FS, MDC1.C4.C2460: FS, MDC1.C4.C3460: FS, MDC1.C4.C1460: FS, MDC1.C4.Cx3040: FS, MDC1.M4010: FS | MDC1.C4.Cx4020: FS, MDC1.C4.Cx4020: FF, MDC1-C4.P2100: FS | VECA Electricians | 2240 | 0 |  | ['270: FS', '294: FS', '269: FS', '293: FS', '240: FS', '235: FS'] | ['230: FS', '230: FF', '233: FS']
233 | Not Started | MDC1-BL.3.5 | Finish Milestone | Ready for Network Install |  | 2021-10-08 16:00 |  |  | 2021-10-08 16:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MDC1.C4.Cx4000: FS | MDC1.C4.Cx4020: FS |  | 0 | 0 |  | ['232: FS'] | ['230: FS']
234 | Not Started | MDC1-BL.5.2.12.5 | Task Dependent | Security Commissioning | 2021-09-13 08:00 | 2021-09-22 16:00 |  |  |  |  | 0 | 0 | 10 | 10 | 37 | 37 |  |  |  |  | MDC1.C4.Cx3030: FS, MDC1.C4.Cx3040: FS | MDC1-C4.P2200: FS | VECA Electricians | 2240 | 0 |  | ['243: FS', '240: FS'] | ['231: FS']
235 | Not Started | MDC1-BL.1 | Finish Milestone | MDC1 COLO4 - LV3 Cx Complete |  | 2021-09-18 08:00 |  |  | 2021-09-18 08:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Finish On or Before | 2021-09-17 17:00 |  |  | MDC1.S.1910: FS, MDC1.C4.Cx3040: FS, MDC1.C4.Cx3050: FS, MDC1-C4.P1900: FS, MDC1-1958: FS, MDC1-C4.P1900: FF | MDC1.C4.Cx4000: FS, MDC1.M6010: FS |  | 0 | 0 |  | ['260: FS', '240: FS', '237: FS', '292: FS', '236: FS', '292: FF'] | ['232: FS', '229: FS']
236 | Not Started | MDC1-BL.2 | Level of Effort | MDC1 COLO4 - Fitout Summary | 2020-11-12 07:00 | 2021-09-18 08:00 |  |  |  |  | 0 | 0 | 241 | 241 | 0 | 0 |  |  |  |  | MDC1.C4.C1020: SS | MDC1.M4010: FS |  | 0 | 0 |  | ['976: SS'] | ['235: FS']
237 | Not Started | MDC1-BL.5.2.12.6 | Task Dependent | Weather (5 Days) | 2021-09-13 08:00 | 2021-09-18 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C4.Cx3040: FS | MDC1.M4010: FS |  | 0 | 0 |  | ['240: FS'] | ['235: FS']
238 | Not Started | MDC1-BL.5.2.1.5 | Task Dependent | Punch List/ Lock down COLO-3 | 2021-08-28 08:00 | 2021-09-17 16:00 |  |  |  |  | 0 | 0 | 21 | 21 | 42 | 42 |  |  |  |  | MDC1.C3.Cx4000: FS, MDC1-C3.P2100: FS | MDC1.M6010: FS, MDC1.M6010: FF, MDC1-C3.P2200: FS | VECA Electricians | 2240 | 0 |  | ['241: FS', '242: FS'] | ['229: FS', '229: FF', '239: FS']
239 | Not Started | MDC1-BL.3.4 | Finish Milestone | Ready for Lock down COLO-3 |  | 2021-09-17 16:00 |  |  | 2021-09-17 16:00 |  | 0 | 0 | 0 | 0 | 42 | 42 |  |  |  |  | MDC1.C3.Cx4020: FS, MDC1.C3.Cx4010: FS | MDC1.M6010: FS |  | 0 | 0 |  | ['238: FS', '245: FS'] | ['229: FS']
240 | Not Started | MDC1-BL.5.2.12.6 | Task Dependent | Level 3 Cx - COLO-4 | 2021-08-27 08:00 | 2021-09-13 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.Cx3030: FS, MDC1.C4.Cx2060: FS, MDC1.C4.Cx2140: FS, MDC1.C4.Cx2100: FS, MDC1.C4.Cx3020: FF 10 | MDC1.C4.Cx4000: FS, MDC1.M4010: FS, MDC1.C4.Cx3050: FS, MDC1.C4.Cx4010: FS | VECA Electricians | 1200 | 0 |  | ['243: FS', '278: FS', '265: FS', '271: FS', '244: FF 10'] | ['232: FS', '235: FS', '237: FS', '234: FS']
241 | Not Started | MDC1-BL.5.2.1.5 | Task Dependent | COLO 3 Level 4 & Level 5 IST | 2021-08-07 08:00 | 2021-08-27 16:00 |  |  |  |  | 0 | 0 | 21 | 21 | 42 | 42 |  |  |  |  | MDC1.C3.C4460: FS, MDC1.C3.C2460: FS, MDC1.C3.C3420: FS, MDC1.C3.C1460: FS, MDC1.C3.Cx3040: FS, MDC1.M3010: FS | MDC1.C3.Cx4020: FS, MDC1-C3.P2100: FS | VECA Electricians | 2240 | 0 |  | ['342: FS', '398: FS', '341: FS', '397: FS', '252: FS', '246: FS'] | ['238: FS', '242: FS']
242 | Not Started | MDC1-BL.3.4 | Finish Milestone | Ready for Network Install |  | 2021-08-27 16:00 |  |  | 2021-08-27 16:00 |  | 0 | 0 | 0 | 0 | 33 | 33 |  |  |  |  | MDC1.C3.Cx4000: FS | MDC1.C3.Cx4020: FS |  | 0 | 0 |  | ['241: FS'] | ['238: FS']
243 | Not Started | MDC1-BL.5.2.12.6 | Task Dependent | Load Bank & IR Scan | 2021-08-05 08:00 | 2021-08-27 08:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C4.Cx2170: FS, MDC1.C4.Cx2100: FS, MDC1.C4.Cx2140: FS, MDC1.C4.Cx2060: FS, MDC1.C4.Cx3010: FS, MDC1.C3.Cx3030: FS 15 | MDC1.C4.Cx3040: FS, MDC1.C4.Cx4010: FS | VECA Electricians | 3600 | 0 |  | ['258: FS', '271: FS', '265: FS', '278: FS', '251: FS', '261: FS 15'] | ['240: FS', '234: FS']
244 | Not Started | MDC1-BL.5.2.12.6 | Task Dependent | BAS Prefunctional Testing on Construction Server | 2021-07-21 07:00 | 2021-08-13 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 12 | 12 |  |  |  |  | MDC1.C4.Cx2090: FS, MDC1.C4.Cx2160: FS, MDC1.C4.Cx2130: FS, MDC1.C4.Cx2190: FS, MDC1.C3.Cx3020: FS, MDC1.C4.C1160: FS, MDC1.C4.C3160: FS, MDC1.C4.C2160: FS, MDC1.C4.C4160: FS, MDC1-C4.P2000: FS | MDC1.C4.Cx3040: FF 10 | LINX- TELECOM | 2000 | 0 |  | ['277: FS', '262: FS', '268: FS', '254: FS', '275: FS', '629: FS', '530: FS', '633: FS', '533: FS', '255: FS'] | ['240: FF 10']
245 | Not Started | MDC1-BL.5.2.1.5 | Task Dependent | Security Commissioning | 2021-08-02 08:00 | 2021-08-11 16:00 |  |  |  |  | 0 | 0 | 10 | 10 | 79 | 79 |  |  |  |  | MDC1.C3.Cx3040: FS | MDC1-C3.P2200: FS | VECA Electricians | 2240 | 0 |  | ['252: FS'] | ['239: FS']
246 | Not Started | MDC1-BL.1 | Finish Milestone | MDC1 COLO3 - LV3 Cx Complete |  | 2021-08-07 08:00 |  |  | 2021-08-07 08:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Finish On or Before | 2021-08-06 17:00 |  |  | MDC1.C3.Cx3040: FS, MDC1.C3.Cx2060: FS, MDC1.C3.Cx2140: FS, MDC1.C3.Cx2090: FS, MDC1.C3.Cx3050: FS, MDC1-C2.P1900: FS, MDC1-1957: FS, MDC1-C3.P1900: FS | MDC1.C3.Cx4000: FS |  | 0 | 0 |  | ['252: FS', '329: FS', '306: FS', '323: FS', '248: FS', '31: FS', '247: FS', '367: FS'] | ['241: FS']
247 | Not Started | MDC1-BL.2 | Level of Effort | MDC1 COLO3 - Fitout Summary | 2020-10-14 07:00 | 2021-08-07 08:00 |  |  |  |  | 0 | 0 | 232 | 232 | 0 | 0 |  |  |  |  | MDC1.C3.C1010: SS | MDC1.M3010: FS |  | 0 | 0 |  | ['1126: SS'] | ['246: FS']
248 | Not Started | MDC1-BL.5.2.1.6 | Task Dependent | Weather (5 days) | 2021-08-02 08:00 | 2021-08-07 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C3.Cx3040: FS | MDC1.M3010: FS |  | 0 | 0 |  | ['252: FS'] | ['246: FS']
249 | Not Started | MDC1-BL.5.2.2.5 | Task Dependent | Punch List/ Lock down COLO-2 | 2021-07-17 08:00 | 2021-08-06 16:00 |  |  |  |  | 0 | 0 | 21 | 21 | 84 | 84 |  |  |  |  | MDC1.C2.Cx4010: FS, MDC1.C2.Cx4010: FF, MDC1-C2.P2100: FS | MDC1.M6010: FS, MDC1.M6010: FF, MDC1-C2.P2200: FS | VECA Electricians | 2240 | 0 |  | ['263: FS', '263: FF', '264: FS'] | ['229: FS', '229: FF', '250: FS']
250 | Not Started | MDC1-BL.3.3 | Finish Milestone | Ready for Lock down COLO-2 |  | 2021-08-06 16:00 |  |  | 2021-08-06 16:00 |  | 0 | 0 | 0 | 0 | 84 | 84 |  |  |  |  | MDC1.C2.Cx4020: FS, MDC1.C2.Cx4000: FS | MDC1.M6010: FS |  | 0 | 0 |  | ['249: FS', '274: FS'] | ['229: FS']
251 | Not Started | MDC1-BL.5.2.12.6 | Task Dependent | Cooling Automation | 2021-07-21 07:00 | 2021-08-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.Cx3000: FS, MDC1.C4.Cx2070: FS, MDC1.C4.Cx2090: FS, MDC1.C4.Cx2150: FS, MDC1.C4.Cx2160: FS, MDC1.C4.Cx2120: FS, MDC1.C4.Cx2130: FS, MDC1.C4.Cx2180: FS, MDC1.C4.Cx2190: FS, MDC1.C3.Cx3010: FS | MDC1.C4.Cx3030: FS | TCM | 1200 | 0 |  | ['253: FS', '279: FS', '277: FS', '266: FS', '262: FS', '273: FS', '268: FS', '259: FS', '254: FS', '283: FS'] | ['243: FS']
252 | Not Started | MDC1-BL.5.2.1.6 | Task Dependent | Level 3 Cx- COLO-3 | 2021-07-17 08:00 | 2021-08-02 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.Cx3030: FS, MDC1.C3.Cx2060: FS, MDC1.C3.Cx2140: FS, MDC1.C3.Cx2090: FS, MDC1.C3.Cx3020: FF 10 | MDC1.C3.Cx4000: FS, MDC1.M3010: FS, MDC1.C3.Cx3050: FS, MDC1.C3.Cx4010: FS | VECA Electricians | 1200 | 0 |  | ['261: FS', '329: FS', '306: FS', '323: FS', '275: FF 10'] | ['241: FS', '246: FS', '248: FS', '245: FS']
253 | Not Started | MDC1-BL.5.2.12.6 | Task Dependent | Hydronic Pipe Flush (Open and closed Loop) | 2021-07-07 07:00 | 2021-07-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.Cx2070: SS 10, MDC1.C4.Cx2150: SS 10, MDC1.C4.Cx2120: SS 10, MDC1.C4.Cx2180: SS 10, MDC1.C3.Cx3000: FS | MDC1.C4.Cx3010: FS | TCM | 1200 | 0 |  | ['279: SS 10', '266: SS 10', '273: SS 10', '259: SS 10', '300: FS'] | ['251: FS']
254 | Not Started | MDC1-BL.5.2.12.7.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-07-07 07:00 | 2021-07-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.Cx2110: FS | MDC1.C4.Cx3010: FS, MDC1.C4.Cx3020: FS, MDC1-C4.P2000: FS | TCM | 640 | 0 |  | ['272: FS'] | ['251: FS', '244: FS', '255: FS']
255 | Not Started | MDC1-BL.3.5 | Finish Milestone | Construction Server- COLO-4 |  | 2021-07-20 17:00 |  |  | 2021-07-20 17:00 |  | 0 | 0 | 0 | 0 | 12 | 12 |  |  |  |  | MDC1.C4.Cx2090: FS, MDC1.C4.Cx2160: FS, MDC1.C4.Cx2130: FS, MDC1.C4.Cx2190: FS | MDC1.C4.Cx3020: FS |  | 0 | 0 |  | ['277: FS', '262: FS', '268: FS', '254: FS'] | ['244: FS']
256 | Not Started | MDC1-BL.3.2 | Finish Milestone | Ready for Lock down COLO-1 |  | 2021-07-18 08:00 |  |  | 2021-07-18 08:00 |  | 0 | 0 | 0 | 0 | 104 | 104 |  |  |  |  | MDC1.C1.Cx4000: FS, MDC1.S.1910: FS, MDC1.C1.Cx4020: FS, MDC1.C1.Cx4010: FS | MDC1.M6010: FS, MDC1.M6010: FF |  | 0 | 0 |  | ['295: FS', '260: FS', '267: FS', '335: FS'] | ['229: FS', '229: FF']
257 | Not Started | MDC1-BL.5.1.4 | Task Dependent | Site Lighting | 2021-05-15 07:00 | 2021-07-17 17:00 |  |  |  |  | 0 | 0 | 50 | 50 | 49 | 49 |  |  |  |  | MDC1.C3.C4290: FS, MDC1.C2.C4250: FS, MDC1.C1.C4280: FS, MDC1.S.1040: FS, MDC1.S.1300: FS, MDC1.S.1870: FS, MDC1.C4.CS1050: FS, MDC1.C4.CS1060: FS | MDC1.S.1910: FS | VECA Electricians | 4000 | 0 |  | ['563: FS', '710: FS', '871: FS', '1302: FS', '1113: FS', '348: FS', '1238: FS', '1178: FS'] | ['260: FS']
258 | Not Started | MDC1-BL.5.2.12.7.4 | Task Dependent | EPMS Checkout / Point to Point | 2021-07-07 07:00 | 2021-07-17 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C4.Cx2110: FS, MDC1.C4.Cx2100: FS | MDC1.C4.Cx3030: FS | LINX- TELECOM | 1200 | 0 |  | ['272: FS', '271: FS'] | ['243: FS']
259 | Not Started | MDC1-BL.5.2.12.7.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-06-23 07:00 | 2021-07-17 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C4.Cx2050: FS | MDC1.C4.Cx3000: SS 10, MDC1.C4.Cx3010: FS | VECA Electricians | 2000 | 0 |  | ['285: FS'] | ['253: SS 10', '251: FS']
260 | Not Started | MDC1-BL.5.1.4 | Finish Milestone | Site Work Complete |  | 2021-07-17 17:00 |  |  | 2021-07-17 17:00 |  | 0 | 0 | 0 | 0 | 49 | 49 |  |  |  |  | MDC1.S.1900: FS, MDC1.S.1160: FS, MDC1.S.1890: FS, MDC1.S.1120: FS, MDC1.S.1880: FS | MDC1.M4010: FS, MDC1-C1.P2200: FS |  | 0 | 0 |  | ['257: FS', '1215: FS', '288: FS', '1196: FS', '297: FS'] | ['235: FS', '256: FS']
261 | Not Started | MDC1-BL.5.2.1.6 | Task Dependent | Load Bank & IR Scan | 2021-06-24 08:00 | 2021-07-17 08:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C3.Cx2150: FS, MDC1.C3.Cx2090: FS, MDC1.C3.Cx2140: FS, MDC1.C3.Cx2060: FS, MDC1.C2.Cx3030: FS 15, MDC1.C3.Cx3010: FS | MDC1.C3.Cx3040: FS, MDC1.C4.Cx3030: FS 15 | VECA Electricians | 3600 | 0 |  | ['307: FS', '323: FS', '306: FS', '329: FS', '305: FS 15', '283: FS'] | ['252: FS', '243: FS 15']
262 | Not Started | MDC1-BL.5.2.12.7.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-07-01 07:00 | 2021-07-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 3 | 3 |  |  |  |  | MDC1.C4.Cx2080: FS | MDC1.C4.Cx3010: FS, MDC1.C4.Cx3020: FS, MDC1-C4.P2000: FS | TCM | 640 | 0 |  | ['276: FS'] | ['251: FS', '244: FS', '255: FS']
263 | Not Started | MDC1-BL.5.2.2.5 | Task Dependent | COLO 2 Level 4 & Level 5 IST (NIC) | 2021-06-26 08:00 | 2021-07-16 16:00 |  |  |  |  | 0 | 0 | 21 | 21 | 84 | 84 |  |  |  |  | MDC1.C2.C4420: FS, MDC1.C2.C2450: FS, MDC1.C2.C3460: FS, MDC1.C2.C1440: FS, MDC1.C1.C3460: FS, MDC1.C1.C2440: FS, MDC1.C1.C4460: FS, MDC1.C2.Cx3040: FS, MDC1.M2010: FS | MDC1.C2.Cx4020: FS, MDC1.C2.Cx4020: FF, MDC1-C2.P2100: FS | VECA Electricians | 2240 | 0 |  | ['475: FS', '558: FS', '484: FS', '571: FS', '665: FS', '735: FS', '644: FS', '286: FS', '280: FS'] | ['249: FS', '249: FF', '264: FS']
264 | Not Started | MDC1-BL.3.3 | Finish Milestone | Ready for Network Install |  | 2021-07-16 16:00 |  |  | 2021-07-16 16:00 |  | 0 | 0 | 0 | 0 | 67 | 67 |  |  |  |  | MDC1.C2.Cx4010: FS | MDC1.C2.Cx4020: FS |  | 0 | 0 |  | ['263: FS'] | ['249: FS']
265 | Not Started | MDC1-BL.5.2.12.7.2 | Task Dependent | EPMS Checkout / Point to Point | 2021-07-01 07:00 | 2021-07-14 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 17 | 17 |  |  |  |  | MDC1.C4.Cx2080: FS, MDC1.C4.Cx2060: FS | MDC1.C4.Cx3030: FS, MDC1.C4.Cx3040: FS | LINX- TELECOM | 1200 | 0 |  | ['276: FS', '278: FS'] | ['243: FS', '240: FS']
266 | Not Started | MDC1-BL.5.2.12.7.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-06-19 07:00 | 2021-07-14 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 3 | 3 |  |  |  |  | MDC1.C4.Cx2030: FS | MDC1.C4.Cx3000: SS 10, MDC1.C4.Cx3010: FS | VECA Electricians | 2000 | 0 |  | ['287: FS'] | ['253: SS 10', '251: FS']
267 | Not Started | MDC1-BL.5.2.3.5 | Task Dependent | Punch List/ Lockdown- Admin/COLO 1 | 2021-06-12 08:00 | 2021-07-10 17:00 |  |  |  |  | 0 | 0 | 28 | 28 | 111 | 111 |  |  |  |  | MDC1.C1.Cx4000: FS, MDC1.C1.Cx3040: FS, MDC1-C4.P1900: FS, MDC1-C3.P1900: FS, MDC1-C2.P1800: FS, MDC1.C1.C4400: FS, MDC1-C1.P2100: FS | MDC1.M6010: FS, MDC1-C1.P2200: FS |  | 0 | 0 |  | ['295: FS', '355: FS', '292: FS', '367: FS', '594: FS', '747: FS', '296: FS'] | ['229: FS', '256: FS']
268 | Not Started | MDC1-BL.5.2.12.7.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-06-23 07:00 | 2021-07-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 10 | 10 |  |  |  |  | MDC1.C4.Cx2040: FS | MDC1.C4.Cx3010: FS, MDC1.C4.Cx3020: FS, MDC1-C4.P2000: FS | TCM | 640 | 0 |  | ['284: FS'] | ['251: FS', '244: FS', '255: FS']
269 | Not Started | MDC1-BL.5.3.6.4.10.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-06-14 07:00 | 2021-07-08 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C4.C1460: FS, MDC1.C4.C3400: FS | MDC1.C4.Cx4000: FS | LINX- TELECOM | 1440 | 0 |  | ['293: FS', '331: FS'] | ['232: FS']
270 | Not Started | MDC1-BL.5.3.6.4.13.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-06-14 07:00 | 2021-07-08 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C4.C2460: FS, MDC1.C4.C4400: FS | MDC1.C4.Cx4000: FS | LINX- TELECOM | 1440 | 0 |  | ['294: FS', '333: FS'] | ['232: FS']
271 | Not Started | MDC1-BL.5.2.12.7.3 | Task Dependent | EPMS Checkout / Point to Point | 2021-06-23 07:00 | 2021-07-06 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C4.Cx2040: FS | MDC1.C4.Cx3030: FS, MDC1.C4.Cx3040: FS, MDC1.C4.Cx2170: FS | LINX- TELECOM | 1200 | 0 |  | ['284: FS'] | ['243: FS', '240: FS', '258: FS']
272 | Not Started | MDC1-BL.5.2.12.7.4 | Task Dependent | Network Startup | 2021-06-23 07:00 | 2021-07-06 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C4400: FS, MDC1.C4.Cx2050: FS, MDC1.C4.Cx2040: FS | MDC1.C4.Cx2170: FS, MDC1.C4.Cx2190: FS | LINX- TELECOM | 600 | 0 |  | ['333: FS', '285: FS', '284: FS'] | ['258: FS', '254: FS']
273 | Not Started | MDC1-BL.5.2.12.7.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-06-10 07:00 | 2021-07-06 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 10 | 10 |  |  |  |  | MDC1.C4.Cx2010: FS | MDC1.C4.Cx3000: SS 10, MDC1.C4.Cx3010: FS | VECA Electricians | 2000 | 0 |  | ['298: FS'] | ['253: SS 10', '251: FS']
274 | Not Started | MDC1-BL.5.2.2.5 | Task Dependent | Security Commissioning | 2021-06-21 08:00 | 2021-07-02 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 95 | 95 |  |  |  |  | MDC1.C2.Cx3040: FS | MDC1-C2.P2200: FS |  | 0 | 0 |  | ['286: FS'] | ['250: FS']
275 | Not Started | MDC1-BL.5.2.1.6 | Task Dependent | BAS Prefunctional Testing on Construction Server | 2021-06-08 07:00 | 2021-07-01 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 13 | 13 |  |  |  |  | MDC1.C3.Cx2110: FS, MDC1.C3.Cx2180: FS, MDC1.C3.Cx2130: FS, MDC1.C3.Cx2190: FS, MDC1.C2.Cx3020: FS, MDC1.C3.C1130: FS, MDC1.C3.C3130: FS, MDC1.C3.C2130: FS, MDC1.C3.C4160: FS, MDC1-C3.P2000: FS | MDC1.C3.Cx3040: FF 10, MDC1.C4.Cx3020: FS | LINX- TELECOM | 2000 | 0 |  | ['326: FS', '301: FS', '319: FS', '302: FS', '321: FS', '905: FS', '740: FS', '910: FS', '743: FS', '303: FS'] | ['252: FF 10', '244: FS']
276 | Not Started | MDC1-BL.5.2.12.7.2 | Task Dependent | Network Startup | 2021-06-19 07:00 | 2021-06-30 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.C4.C3400: FS, MDC1.C4.Cx2030: FS, MDC1.C4.Cx2020: FS | MDC1.C4.Cx2140: FS, MDC1.C4.Cx2160: FS | LINX- TELECOM | 600 | 0 |  | ['331: FS', '287: FS', '289: FS'] | ['265: FS', '262: FS']
277 | Not Started | MDC1-BL.5.2.12.7.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-06-17 07:00 | 2021-06-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 15 | 15 |  |  |  |  | MDC1.C4.Cx2020: FS | MDC1.C4.Cx3010: FS, MDC1.C4.Cx3020: FS, MDC1-C4.P2000: FS | TCM | 640 | 0 |  | ['289: FS'] | ['251: FS', '244: FS', '255: FS']
278 | Not Started | MDC1-BL.5.2.12.7.1 | Task Dependent | EPMS Checkout / Point to Point | 2021-06-17 07:00 | 2021-06-28 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 19 | 19 |  |  |  |  | MDC1.C4.Cx2020: FS | MDC1.C4.Cx3030: FS, MDC1.C4.Cx3040: FS, MDC1.C4.Cx2140: FS | LINX- TELECOM | 1200 | 0 |  | ['289: FS'] | ['243: FS', '240: FS', '265: FS']
279 | Not Started | MDC1-BL.5.2.12.7.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-06-04 07:00 | 2021-06-28 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 15 | 15 |  |  |  |  | MDC1.C4.Cx2000: FS | MDC1.C4.Cx3000: SS 10, MDC1.C4.Cx3010: FS | VECA Electricians | 2000 | 0 |  | ['312: FS'] | ['253: SS 10', '251: FS']
280 | Not Started | MDC1-BL.1 | Finish Milestone | MDC1 COLO2 - LV3 Cx Complete |  | 2021-06-26 08:00 |  |  | 2021-06-26 08:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Finish On or Before | 2021-06-25 17:00 |  |  | MDC1.C2.Cx3040: FS, MDC1.C2.Cx2060: FS, MDC1.C2.Cx2160: FS, MDC1.C2.Cx2090: FS, MDC1.C2.C3150: FS, MDC1.C1.Cx3040: FS, MDC1.C2.Cx3050: FS, MDC1-1956: FS | MDC1.C2.Cx4010: FS |  | 0 | 0 |  | ['286: FS', '425: FS', '386: FS', '422: FS', '948: FS', '355: FS', '282: FS', '281: FS'] | ['263: FS']
281 | Not Started | MDC1-BL.2 | Level of Effort | MDC1 COLO2 - Fitout Summary | 2020-09-15 07:00 | 2021-06-26 08:00 |  |  |  |  | 0 | 0 | 223 | 223 | 0 | 0 |  |  |  |  | MDC1.C2.C1010: SS | MDC1.M2010: FS |  | 0 | 0 |  | ['1223: SS'] | ['280: FS']
282 | Not Started | MDC1-BL.5.2.2.1 | Task Dependent | Weather (5 days) | 2021-06-21 08:00 | 2021-06-26 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C2.Cx3040: FS | MDC1.M2010: FS |  | 0 | 0 |  | ['286: FS'] | ['280: FS']
283 | Not Started | MDC1-BL.5.2.1.6 | Task Dependent | Cooling Automation | 2021-06-09 07:00 | 2021-06-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.Cx3000: FS, MDC1.C3.Cx2070: FS, MDC1.C3.Cx2110: FS, MDC1.C3.Cx2160: FS, MDC1.C3.Cx2180: FS, MDC1.C3.Cx2120: FS, MDC1.C3.Cx2130: FS, MDC1.C3.Cx2170: FS, MDC1.C3.Cx2190: FS, MDC1.C2.Cx3010: FS | MDC1.C3.Cx3030: FS, MDC1.C4.Cx3010: FS | TCM | 1200 | 0 |  | ['300: FS', '334: FS', '326: FS', '310: FS', '301: FS', '327: FS', '319: FS', '311: FS', '302: FS', '349: FS'] | ['261: FS', '251: FS']
284 | Not Started | MDC1-BL.5.2.12.7.3 | Task Dependent | Network Startup | 2021-06-10 07:00 | 2021-06-22 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C2390: FS, MDC1.C4.Cx2010: FS | MDC1.C4.Cx2100: FS, MDC1.C4.Cx2130: FS, MDC1.C4.Cx2110: FS | LINX- TELECOM | 600 | 0 |  | ['365: FS', '298: FS'] | ['271: FS', '268: FS', '272: FS']
285 | Not Started | MDC1-BL.5.2.12.7.4 | Task Dependent | Equipment Yellow Tagging | 2021-06-10 07:00 | 2021-06-22 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C4200: FF, MDC1.C4.C4420: FS, MDC1.C4.C4400: FS, MDC1.C4.C4430: FS, MDC1.C4.C4410: FS, MDC1.C4.C4240: FS, MDC1.C4.C4370: FS, MDC1.C4.C4440: FS, MDC1.C4.C4120: FS, MDC1.C4.Cx2010: FS, MDC1-C4.P1800: FS | MDC1.C4.Cx2110: FS, MDC1.C4.Cx2180: FS | VECA Electricians | 1200 | 0 |  | ['479: FF', '314: FS', '333: FS', '309: FS', '315: FS', '452: FS', '339: FS', '299: FS', '651: FS', '298: FS', '33: FS'] | ['272: FS', '259: FS']
286 | Not Started | MDC1-BL.5.2.2.1 | Task Dependent | Level 3 Cx- COLO-2 | 2021-06-05 08:00 | 2021-06-21 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.Cx3030: FS, MDC1.C2.Cx2060: FS, MDC1.C2.Cx2160: FS, MDC1.C2.Cx2090: FS, MDC1.C2.C3150: FS, MDC1.C2.Cx3020: FF 10 | MDC1.C2.Cx4010: FS, MDC1.M2010: FS, MDC1.C2.Cx3050: FS, MDC1.C2.Cx4000: FS | VECA Electricians | 1200 | 0 |  | ['305: FS', '425: FS', '386: FS', '422: FS', '948: FS', '321: FF 10'] | ['263: FS', '280: FS', '282: FS', '274: FS']
287 | Not Started | MDC1-BL.5.2.12.7.2 | Task Dependent | Equipment Yellow Tagging | 2021-06-07 07:00 | 2021-06-18 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.C4.C3390: FS, MDC1.C4.C3200: FF, MDC1.C4.C3420: FS, MDC1.C4.C3400: FS, MDC1.C4.C3430: FS, MDC1.C4.C3410: FS, MDC1.C4.C3250: FS, MDC1.C4.C3380: FS, MDC1.C4.C3440: FS, MDC1.C4.C3120: FS, MDC1.C4.Cx2000: FS, MDC1-C4.P1800: FS | MDC1.C4.Cx2080: FS, MDC1.C4.Cx2150: FS | VECA Electricians | 1200 | 0 |  | ['351: FS', '478: FF', '313: FS', '331: FS', '308: FS', '325: FS', '450: FS', '350: FS', '304: FS', '650: FS', '312: FS', '33: FS'] | ['276: FS', '266: FS']
288 | Not Started | MDC1-BL.5.1.5 | Task Dependent | Landscape and Site Specialties | 2021-04-16 07:00 | 2021-06-17 17:00 |  |  |  |  | 0 | 0 | 50 | 50 | 73 | 73 |  |  |  |  | MDC1.S.1880: FF 6 | MDC1.S.1910: FS | Advantage | 2500 | 0 |  | ['297: FF 6'] | ['260: FS']
289 | Not Started | MDC1-BL.5.2.12.7.1 | Task Dependent | Network Startup | 2021-06-04 07:00 | 2021-06-16 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 5 | 5 |  |  |  |  | MDC1.C4.C1400: FS, MDC1.C4.Cx2000: FS | MDC1.C4.Cx2060: FS, MDC1.C4.Cx2090: FS, MDC1.C4.Cx2080: FS | LINX- TELECOM | 600 | 0 |  | ['363: FS', '312: FS'] | ['278: FS', '277: FS', '276: FS']
290 | Not Started | MDC1-BL.5.3.6.4.10.1 | Task Dependent | Light Fixtures Installation | 2021-06-05 07:00 | 2021-06-11 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 77 | 77 |  |  |  |  | MDC1.C4.C3420: FS, MDC1.C4.C3430: FS, MDC1.C4.C3360: FS | MDC1-C4.P1900: FS, MDC1-C4.P1900: SS | VECA Electricians | 480 | 0 |  | ['313: FS', '308: FS', '359: FS'] | ['292: FS', '292: SS']
291 | Not Started | MDC1-BL.5.3.6.4.13.1 | Task Dependent | Light Fixtures Installation | 2021-06-05 07:00 | 2021-06-11 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 77 | 77 |  |  |  |  | MDC1.C4.C4430: FS, MDC1.C4.C4350: FS | MDC1-C4.P1900: FS | VECA Electricians | 480 | 0 |  | ['309: FS', '360: FS'] | ['292: FS']
292 | Not Started | MDC1-BL.3.5 | Finish Milestone | COLO 4 CSA complete |  | 2021-06-11 17:00 |  |  | 2021-06-11 17:00 |  | 0 | 0 | 0 | 0 | 77 | 77 |  |  |  |  | MDC1.C4.C3220: FS, MDC1.C4.C1260: FS, MDC1.C4.C2250: FS, MDC1.C4.C1200: FS, MDC1.C4.C1300: FS, MDC1.C4.C1240: FS, MDC1.C4.C1250: FS, MDC1.C4.C3280: FS, MDC1.C4.C3290: FS, MDC1.C4.C3300: FS, MDC1.C4.C2370: FS, MDC1.C4.C2230: FS, MDC1.C4.C2240: FS, MDC1.C4.C4380: FS, MDC1.C4.C4270: FS, MDC1.C4.C4330: FS, MDC1.C4.C3450: FS, MDC1.C4.C2450: FS, MDC1.C4.C4450: FS, MDC1.C4.C1450: FS, MDC1.C4.C3450: SS, MDC1.C4.C2450: SS | MDC1.C1.Cx4020: FS, MDC1.M4010: FS, MDC1.M4010: FF |  | 0 | 0 |  | ['456: FS', '488: FS', '489: FS', '551: FS', '455: FS', '494: FS', '495: FS', '410: FS', '411: FS', '412: FS', '370: FS', '496: FS', '497: FS', '340: FS', '413: FS', '369: FS', '290: FS', '318: FS', '291: FS', '316: FS', '290: SS', '318: SS'] | ['267: FS', '235: FS', '235: FF']
293 | Not Started | MDC1-BL.5.3.6.4.9.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-05-18 07:00 | 2021-06-11 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C3.C3420: FS, MDC1.C4.C1400: FS | MDC1.C4.Cx4000: FS, MDC1.C4.C3460: FS | LINX- TELECOM | 1440 | 0 |  | ['341: FS', '363: FS'] | ['232: FS', '269: FS']
294 | Not Started | MDC1-BL.5.3.6.4.11.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-05-18 07:00 | 2021-06-11 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C3.C4460: FS, MDC1.C4.C2390: FS | MDC1.C4.Cx4000: FS, MDC1.C4.C4460: FS | LINX- TELECOM | 1440 | 0 |  | ['342: FS', '365: FS'] | ['232: FS', '270: FS']
295 | Not Started | MDC1-BL.5.2.3.5 | Task Dependent | COLO 1 Level 4 & Level 5 IST | 2021-05-15 08:00 | 2021-06-11 16:00 |  |  |  |  | 0 | 0 | 28 | 28 | 0 | 0 | Finish On or Before | 2021-06-11 16:00 |  |  | MDC1.C1.C4460: FS, MDC1.C1.C2440: FS, MDC1.C1.C3460: FS, MDC1.C1.C1430: FS, MDC1.S.1830: FS, MDC1.M1010: FS | MDC1.C1.Cx4020: FS, MDC1-C1.P2200: FS, MDC1-C1.P2100: FS | VECA Electricians | 2240 | 0 |  | ['644: FS', '735: FS', '665: FS', '776: FS', '652: FS', '344: FS'] | ['267: FS', '256: FS', '296: FS']
296 | Not Started | MDC1-BL.3.2 | Finish Milestone | Ready for Network Install |  | 2021-06-11 16:00 |  |  | 2021-06-11 16:00 |  | 0 | 0 | 0 | 0 | 88 | 88 |  |  |  |  | MDC1.C1.Cx4000: FS | MDC1.C1.Cx4020: FS |  | 0 | 0 |  | ['295: FS'] | ['267: FS']
297 | Not Started | MDC1-BL.5.1.4 | Task Dependent | Pave HMA | 2021-05-15 07:00 | 2021-06-09 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 73 | 73 |  |  |  |  | MDC1.S.1870: FS, MDC1.S.1300: FS, MDC1.S.1860: FS, MDC1.S.1860: FF | MDC1.S.1890: FF 6, MDC1.S.1910: FS | Advantage | 2000 | 0 |  | ['348: FS', '1113: FS', '453: FS', '453: FF'] | ['288: FF 6', '260: FS']
298 | Not Started | MDC1-BL.5.2.12.7.3 | Task Dependent | Equipment Yellow Tagging | 2021-05-28 07:00 | 2021-06-09 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C2180: FF, MDC1.C4.C2410: FS, MDC1.C4.C2390: FS, MDC1.C4.C2420: FS, MDC1.C4.C2430: FS, MDC1.C4.C2210: FS, MDC1.C4.C2380: FS, MDC1.C4.C2440: FS, MDC1.C4.C2120: FS, MDC1-C4.P1800: FS | MDC1.C4.Cx2040: FS, MDC1.C4.Cx2120: FS, MDC1.C4.Cx2050: FS | VECA Electricians | 1200 | 0 |  | ['574: FF', '338: FS', '365: FS', '332: FS', '320: FS', '554: FS', '368: FS', '317: FS', '693: FS', '33: FS'] | ['284: FS', '273: FS', '285: FS']
299 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Pull Conductors into Building | 2021-05-18 07:00 | 2021-06-09 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C4.C4100: FS, MDC1.C4.C4370: FS | MDC1.C4.Cx2050: FS | VECA Electricians | 1440 | 0 |  | ['713: FS', '339: FS'] | ['285: FS']
300 | Not Started | MDC1-BL.5.2.1.6 | Task Dependent | Hydronic Pipe Flush (Open and closed Loop) | 2021-05-25 07:00 | 2021-06-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.Cx2070: SS 11, MDC1.C3.Cx2160: SS 11, MDC1.C3.Cx2120: SS 11, MDC1.C3.Cx2170: SS 11, MDC1.C2.Cx3000: FS 11 | MDC1.C3.Cx3010: FS, MDC1.C4.Cx3000: FS | TCM | 1200 | 0 |  | ['334: SS 11', '310: SS 11', '327: SS 11', '311: SS 11', '376: FS 11'] | ['283: FS', '253: FS']
301 | Not Started | MDC1-BL.5.2.1.7.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-05-24 07:00 | 2021-06-07 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 1 | 1 |  |  |  |  | MDC1.C3.Cx2080: FS | MDC1.C3.Cx3010: FS, MDC1.C3.Cx3020: FS, MDC1-C3.P2000: FS | TCM | 640 | 0 |  | ['322: FS'] | ['283: FS', '275: FS', '303: FS']
302 | Not Started | MDC1-BL.5.2.1.7.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-05-24 07:00 | 2021-06-07 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 1 | 1 |  |  |  |  | MDC1.C3.Cx2100: FS | MDC1.C3.Cx3010: FS, MDC1.C3.Cx3020: FS, MDC1-C3.P2000: FS | TCM | 640 | 0 |  | ['324: FS'] | ['283: FS', '275: FS', '303: FS']
303 | Not Started | MDC1-BL.3.4 | Finish Milestone | Construction Server- COLO-3 |  | 2021-06-07 17:00 |  |  | 2021-06-07 17:00 |  | 0 | 0 | 0 | 0 | 13 | 13 |  |  |  |  | MDC1.C3.Cx2190: FS, MDC1.C3.Cx2130: FS, MDC1.C3.Cx2180: FS, MDC1.C3.Cx2110: FS | MDC1.C3.Cx3020: FS |  | 0 | 0 |  | ['302: FS', '319: FS', '301: FS', '326: FS'] | ['275: FS']
304 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Pull Conductors into Building | 2021-05-12 07:00 | 2021-06-05 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 3 | 3 |  |  |  |  | MDC1.C4.C3100: FS, MDC1.C4.C3380: FS | MDC1.C4.Cx2030: FS | VECA Electricians | 1440 | 0 |  | ['712: FS', '350: FS'] | ['287: FS']
305 | Not Started | MDC1-BL.5.2.2.1 | Task Dependent | Load Bank & IR Scan | 2021-05-13 08:00 | 2021-06-05 08:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C2.Cx2140: FS, MDC1.C2.Cx2060: FS, MDC1.C2.Cx2160: FS, MDC1.C2.Cx2090: FS, MDC1.C2.C3150: FS, MDC1.C2.Cx3010: FS, MDC1.C1.Cx3030: FS 15, MDC1.C2.C4040: FS, MDC1.C2.C4050: FS, MDC1-2527: FS | MDC1.C2.Cx3040: FS, MDC1.C3.Cx3030: FS 15 | VECA Electricians | 3600 | 0 |  | ['388: FS', '425: FS', '386: FS', '422: FS', '948: FS', '349: FS', '394: FS 15', '1125: FS', '1096: FS', '1325: FS'] | ['286: FS', '261: FS 15']
306 | Not Started | MDC1-BL.5.2.1.7.2 | Task Dependent | EPMS Checkout / Point to Point | 2021-05-24 07:00 | 2021-06-04 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 15 | 15 |  |  |  |  | MDC1.C3.Cx2080: FS, MDC1.C3.Cx2060: FS | MDC1.M3010: FS, MDC1.C3.Cx3030: FS, MDC1.C3.Cx3040: FS | LINX- TELECOM | 1200 | 0 |  | ['322: FS', '329: FS'] | ['246: FS', '261: FS', '252: FS']
307 | Not Started | MDC1-BL.5.2.1.7.4 | Task Dependent | EPMS Checkout / Point to Point | 2021-05-24 07:00 | 2021-06-04 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 15 | 15 |  |  |  |  | MDC1.C3.Cx2100: FS, MDC1.C3.Cx2090: FS | MDC1.C3.Cx3030: FS | LINX- TELECOM | 1200 | 0 |  | ['324: FS', '323: FS'] | ['261: FS']
308 | Not Started | MDC1-BL.5.3.6.4.10.3 | Task Dependent | Controls Installation | 2021-05-20 07:00 | 2021-06-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C3310: FS, MDC1.C4.C3330: FS, MDC1.C4.C3400: FS | MDC1.C4.C3450: FS, MDC1.C4.Cx2030: FS | VECA Electricians | 720 | 0 |  | ['406: FS', '383: FS', '331: FS'] | ['290: FS', '287: FS']
309 | Not Started | MDC1-BL.5.3.6.4.13.3 | Task Dependent | Controls Installation | 2021-05-20 07:00 | 2021-06-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C4280: FS, MDC1.C4.C4300: FS, MDC1.C4.C4400: FS | MDC1.C4.C4450: FS, MDC1.C4.Cx2050: FS | VECA Electricians | 720 | 0 |  | ['408: FS', '371: FS', '333: FS'] | ['291: FS', '285: FS']
310 | Not Started | MDC1-BL.5.2.1.7.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-05-11 07:00 | 2021-06-04 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C3.Cx2030: FS | MDC1.C3.Cx3000: SS 11, MDC1.C3.Cx3010: FS | VECA Electricians | 2000 | 0 |  | ['352: FS'] | ['300: SS 11', '283: FS']
311 | Not Started | MDC1-BL.5.2.1.7.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-05-11 07:00 | 2021-06-04 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C3.Cx2050: FS | MDC1.C3.Cx3000: SS 11, MDC1.C3.Cx3010: FS | VECA Electricians | 2000 | 0 |  | ['354: FS'] | ['300: SS 11', '283: FS']
312 | Not Started | MDC1-BL.5.2.12.7.1 | Task Dependent | Equipment Yellow Tagging | 2021-05-21 07:00 | 2021-06-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 5 | 5 |  |  |  |  | MDC1.C4.C1180: FF, MDC1.C4.C1420: FS, MDC1.C4.C1400: FS, MDC1.C4.C1430: FS, MDC1.C4.C1410: FS, MDC1.C4.C1210: FS, MDC1.C4.C1380: FS, MDC1.C4.C1440: FS, MDC1.C4.C1120: FS | MDC1.C4.Cx2020: FS, MDC1-C4.P1800: SS, MDC1.C4.Cx2070: FS, MDC1.C4.Cx2030: FS | VECA Electricians | 1200 | 0 |  | ['572: FF', '337: FS', '363: FS', '330: FS', '343: FS', '552: FS', '385: FS', '328: FS', '692: FS'] | ['289: FS', '33: SS', '279: FS', '287: FS']
313 | Not Started | MDC1-BL.5.3.6.4.10.1 | Task Dependent | Pull / Term / Test Conductors | 2021-05-07 07:00 | 2021-06-02 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 6 | 6 |  |  |  |  | MDC1.C4.C3360: FS | MDC1.C4.C3450: FS, MDC1.C4.Cx2030: FS | VECA Electricians | 1680 | 0 |  | ['359: FS'] | ['290: FS', '287: FS']
314 | Not Started | MDC1-BL.5.3.6.4.13.1 | Task Dependent | Pull / Term / Test Conductors | 2021-05-07 07:00 | 2021-06-02 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 6 | 6 |  |  |  |  | MDC1.C4.C4350: FS, MDC1.C4.C4280: FS | MDC1.C4.Cx2050: FS | VECA Electricians | 1680 | 0 |  | ['360: FS', '408: FS'] | ['285: FS']
315 | Not Started | MDC1-BL.5.3.6.4.4.4 | Task Dependent | Controls Installation | 2021-05-15 07:00 | 2021-05-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 8 | 8 |  |  |  |  | MDC1.C4.C4100: FS, MDC1.C4.C4110: FS, MDC1.C4.C4360: FS | MDC1.C4.Cx2050: FS | VECA Electricians | 720 | 0 |  | ['713: FS', '668: FS', '347: FS'] | ['285: FS']
316 | Not Started | MDC1-BL.5.3.6.4.9.1 | Task Dependent | Light Fixtures Installation | 2021-05-20 07:00 | 2021-05-27 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 89 | 89 |  |  |  |  | MDC1.C4.C1420: FS, MDC1.C4.C1430: FS, MDC1.C4.C1370: FS | MDC1-C4.P1900: FS | VECA Electricians | 480 | 0 |  | ['337: FS', '330: FS', '401: FS'] | ['292: FS']
317 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Pull Conductors into Building | 2021-05-05 07:00 | 2021-05-27 17:00 |  |  |  |  | 0 | 0 | 19 | 19 | 0 | 0 |  |  |  |  | MDC1.C4.C2100: FS, MDC1.C4.C2380: FS | MDC1.C4.Cx2010: FS | VECA Electricians | 1440 | 0 |  | ['791: FS', '368: FS'] | ['298: FS']
318 | Not Started | MDC1-BL.5.3.6.4.11.1 | Task Dependent | Light Fixtures Installation | 2021-05-20 07:00 | 2021-05-27 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 89 | 89 |  |  |  |  | MDC1.C4.C2410: FS, MDC1.C4.C2420: FS, MDC1.C4.C2350: FS | MDC1-C4.P1900: FS, MDC1-C4.P1900: SS | VECA Electricians | 480 | 0 |  | ['338: FS', '332: FS', '402: FS'] | ['292: FS', '292: SS']
319 | Not Started | MDC1-BL.5.2.1.7.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-05-11 07:00 | 2021-05-25 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C3.Cx2040: FS | MDC1.C3.Cx3010: FS, MDC1.C3.Cx3020: FS, MDC1-C3.P2000: FS | TCM | 640 | 0 |  | ['353: FS'] | ['283: FS', '275: FS', '303: FS']
320 | Not Started | MDC1-BL.5.3.6.4.3.4 | Task Dependent | Controls Installation | 2021-05-10 07:00 | 2021-05-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 3 | 3 |  |  |  |  | MDC1.C4.C2100: FS, MDC1.C4.C2110: FS, MDC1.C4.C2400: FS | MDC1.C4.Cx2010: FS | VECA Electricians | 720 | 0 |  | ['791: FS', '723: FS', '356: FS'] | ['298: FS']
321 | Not Started | MDC1-BL.5.2.2.1 | Task Dependent | BAS Prefunctional Testing on Construction Server | 2021-04-28 08:00 | 2021-05-24 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 12 | 12 |  |  |  |  | MDC1.C2.Cx2130: FS, MDC1.C2.Cx2190: FS, MDC1.C2.Cx2120: FS, MDC1.C2.Cx2180: FS, MDC1.C1.Cx3020: FS, MDC1.C2.C1150: FS, MDC1.C2.C3140: FS, MDC1.C2.C2130: FS, MDC1.C2.C4120: FS, MDC1-C2.P2000: FS | MDC1.C2.Cx3040: FF 10, MDC1.C3.Cx3020: FS | LINX- TELECOM | 2000 | 0 |  | ['419: FS', '377: FS', '421: FS', '384: FS', '436: FS', '1029: FS', '947: FS', '1031: FS', '951: FS', '378: FS'] | ['286: FF 10', '275: FS']
322 | Not Started | MDC1-BL.5.2.1.7.2 | Task Dependent | Network Startup | 2021-05-11 07:00 | 2021-05-21 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 1 | 1 |  |  |  |  | MDC1.C3.C3360: FS, MDC1.C3.Cx2030: FS, MDC1.C3.Cx2020: FS | MDC1.C3.Cx2140: FS, MDC1.C3.Cx2180: FS | LINX- TELECOM | 600 | 0 |  | ['428: FS', '352: FS', '357: FS'] | ['306: FS', '301: FS']
323 | Not Started | MDC1-BL.5.2.1.7.3 | Task Dependent | EPMS Checkout / Point to Point | 2021-05-11 07:00 | 2021-05-21 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 15 | 15 |  |  |  |  | MDC1.C3.Cx2040: FS | MDC1.C3.Cx3030: FS, MDC1.C3.Cx3040: FS, MDC1.M3010: FS, MDC1.C3.Cx2150: FS | LINX- TELECOM | 1200 | 0 |  | ['353: FS'] | ['261: FS', '252: FS', '246: FS', '307: FS']
324 | Not Started | MDC1-BL.5.2.1.7.4 | Task Dependent | Network Startup | 2021-05-11 07:00 | 2021-05-21 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 1 | 1 |  |  |  |  | MDC1.C3.C4390: FS, MDC1.C3.Cx2050: FS, MDC1.C3.Cx2040: FS | MDC1.C3.Cx2150: FS, MDC1.C3.Cx2190: FS | LINX- TELECOM | 600 | 0 |  | ['430: FS', '354: FS', '353: FS'] | ['307: FS', '302: FS']
325 | Not Started | MDC1-BL.5.3.6.4.2.4 | Task Dependent | Controls Installation | 2021-05-08 07:00 | 2021-05-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 14 | 14 |  |  |  |  | MDC1.C4.C3100: FS, MDC1.C4.C3110: FS, MDC1.C4.C3370: FS | MDC1.C4.Cx2030: FS | VECA Electricians | 720 | 0 |  | ['712: FS', '667: FS', '358: FS'] | ['287: FS']
326 | Not Started | MDC1-BL.5.2.1.7.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-05-08 07:00 | 2021-05-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 13 | 13 |  |  |  |  | MDC1.C3.Cx2020: FS | MDC1.C3.Cx3010: FS, MDC1.C3.Cx3020: FS, MDC1-C3.P2000: FS | TCM | 640 | 0 |  | ['357: FS'] | ['283: FS', '275: FS', '303: FS']
327 | Not Started | MDC1-BL.5.2.1.7.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-04-28 07:00 | 2021-05-21 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 10 | 10 |  |  |  |  | MDC1.C3.Cx2010: FS | MDC1.C3.Cx3000: SS 11, MDC1.C3.Cx3010: FS | VECA Electricians | 2000 | 0 |  | ['380: FS'] | ['300: SS 11', '283: FS']
328 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Pull Conductors into Building | 2021-04-27 07:00 | 2021-05-20 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 5 | 5 |  |  |  |  | MDC1.C4.C1100: FS, MDC1.C4.C1380: FS | MDC1.C4.Cx2000: FS | VECA Electricians | 1440 | 0 |  | ['789: FS', '385: FS'] | ['312: FS']
329 | Not Started | MDC1-BL.5.2.1.7.1 | Task Dependent | EPMS Checkout / Point to Point | 2021-05-08 07:00 | 2021-05-19 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 17 | 17 |  |  |  |  | MDC1.C3.Cx2020: FS | MDC1.M3010: FS, MDC1.C3.Cx3030: FS, MDC1.C3.Cx3040: FS, MDC1.C3.Cx2140: FS | LINX- TELECOM | 1200 | 0 |  | ['357: FS'] | ['246: FS', '261: FS', '252: FS', '306: FS']
330 | Not Started | MDC1-BL.5.3.6.4.9.3 | Task Dependent | Controls Installation | 2021-05-06 07:00 | 2021-05-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C1310: FS, MDC1.C4.C1330: FS, MDC1.C4.C1400: FS | MDC1.C4.C1450: FS, MDC1.C4.Cx2000: FS, MDC1-C4.P1800: FS | VECA Electricians | 720 | 0 |  | ['446: FS', '431: FS', '363: FS'] | ['316: FS', '312: FS', '33: FS']
331 | Not Started | MDC1-BL.5.3.6.4.10.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-05-06 07:00 | 2021-05-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C3350: FS | MDC1.C4.C3460: FS, MDC1.C4.Cx2080: FS, MDC1.C4.Cx2030: FS, MDC1.C4.C3430: FS | LINX- TELECOM | 1440 | 0 |  | ['364: FS'] | ['269: FS', '276: FS', '287: FS', '308: FS']
332 | Not Started | MDC1-BL.5.3.6.4.11.3 | Task Dependent | Controls Installation | 2021-05-06 07:00 | 2021-05-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C2290: FS, MDC1.C4.C2310: FS, MDC1.C4.C2390: FS | MDC1.C4.C2450: FS, MDC1.C4.Cx2010: FS | VECA Electricians | 720 | 0 |  | ['448: FS', '433: FS', '365: FS'] | ['318: FS', '298: FS']
333 | Not Started | MDC1-BL.5.3.6.4.13.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-05-06 07:00 | 2021-05-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C4340: FS | MDC1.C4.C4460: FS, MDC1.C4.Cx2110: FS, MDC1.C4.Cx2050: FS, MDC1.C4.C4430: FS | LINX- TELECOM | 1440 | 0 |  | ['366: FS'] | ['270: FS', '272: FS', '285: FS', '309: FS']
334 | Not Started | MDC1-BL.5.2.1.7.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-04-26 07:00 | 2021-05-19 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 12 | 12 |  |  |  |  | MDC1.C3.Cx2000: FS | MDC1.C3.Cx3000: SS 11, MDC1.C3.Cx3010: FS | VECA Electricians | 2000 | 0 |  | ['389: FS'] | ['300: SS 11', '283: FS']
335 | Not Started | MDC1-BL.5.2.3.5 | Task Dependent | Security Commissioning | 2021-05-10 08:00 | 2021-05-19 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 162 | 162 |  |  |  |  | MDC1.C1.Cx3040: FS | MDC1-C1.P2200: FS |  | 0 | 0 |  | ['355: FS'] | ['256: FS']
336 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-04-24 07:00 | 2021-05-18 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 8 | 8 |  |  |  |  | MDC1.C4.C2360: FS, MDC1.C4.C4110: FS, MDC1.C4.C4100: FS, MDC1.C4.C4260: FS, MDC1.C4.C2360: FF | MDC1.C4.C4360: SS 5 | VECA Electricians | 1080 | 0 |  | ['396: FS', '668: FS', '713: FS', '434: FS', '396: FF'] | ['347: SS 5']
337 | Not Started | MDC1-BL.5.3.6.4.9.1 | Task Dependent | Pull / Term / Test Conductors | 2021-04-22 07:00 | 2021-05-17 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 8 | 8 |  |  |  |  | MDC1.C4.C1370: FS | MDC1.C4.C1450: FS, MDC1.C4.Cx2000: FS | VECA Electricians | 1680 | 0 |  | ['401: FS'] | ['316: FS', '312: FS']
338 | Not Started | MDC1-BL.5.3.6.4.11.1 | Task Dependent | Pull / Term / Test Conductors | 2021-04-22 07:00 | 2021-05-17 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 8 | 8 |  |  |  |  | MDC1.C4.C2350: FS | MDC1.C4.C2450: FS, MDC1.C4.Cx2010: FS | VECA Electricians | 1680 | 0 |  | ['402: FS'] | ['318: FS', '298: FS']
339 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-05-04 07:00 | 2021-05-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.C4310: FS, MDC1.C4.C4100: FS, MDC1.C4.C4260: FS | MDC1.C4.Cx2050: FS, MDC1.C4.C4440: FS | VECA Electricians | 960 | 0 |  | ['372: FS', '713: FS', '434: FS'] | ['285: FS', '299: FS']
340 | Not Started | MDC1-BL.5.3.6.4.8.1 | Task Dependent | Ligthing Installation | 2021-05-04 07:00 | 2021-05-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C4.C2370: FS, MDC1.C4.C4160: FS, MDC1.C4.C4230: FS | MDC1-C4.P1900: FS | VECA Electricians | 480 | 0 |  | ['370: FS', '533: FS', '451: FS'] | ['292: FS']
341 | Not Started | MDC1-BL.5.3.8.4.10.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-04-23 07:00 | 2021-05-17 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C3.C1460: FS, MDC1.C3.C3360: FS | MDC1.C3.Cx4000: FS, MDC1.C4.C1460: FS | LINX- TELECOM | 1440 | 0 |  | ['397: FS', '428: FS'] | ['241: FS', '293: FS']
342 | Not Started | MDC1-BL.5.3.8.4.13.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-04-23 07:00 | 2021-05-17 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C3.C2460: FS, MDC1.C3.C4390: FS | MDC1.C3.Cx4000: FS, MDC1.C4.C2460: FS | LINX- TELECOM | 1440 | 0 |  | ['398: FS', '430: FS'] | ['241: FS', '294: FS']
343 | Not Started | MDC1-BL.5.3.6.4.1.4 | Task Dependent | Controls Installation | 2021-05-03 07:00 | 2021-05-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 9 | 9 |  |  |  |  | MDC1.C4.C1100: FS, MDC1.C4.C1110: FS, MDC1.C4.C1390: FS | MDC1.C4.Cx2000: FS, MDC1-C4.P1800: FS | VECA Electricians | 720 | 0 |  | ['789: FS', '720: FS', '375: FS'] | ['312: FS', '33: FS']
344 | Not Started | MDC1-BL.1 | Finish Milestone | MDC1 Admin/COLO1 - LV3 Cx Complete |  | 2021-05-15 08:00 |  |  | 2021-05-15 08:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Finish On or Before | 2021-05-14 17:00 |  |  | MDC1.C1.Cx3040: FS, MDC1.C1.Cx2090: FS, MDC1.C1.Cx2150: FS, MDC1.C1.Cx2060: FS, MDC1.AD.Cx2000: FS, MDC1.AD.Cx2020: FS, MDC1.C1.C1350: FS, MDC1.C1.C2330: FS, MDC1.C1.C4310: FS, MDC1.C1.C4490: FS, MDC1.C1.C3320: FS, MDC1-C2.P1800: FS, MDC1.C1.Cx3050: FS, MDC1-1955: FS | MDC1.C1.Cx4000: FS, MDC1.M6010: FS |  | 0 | 0 |  | ['355: FS', '541: FS', '512: FS', '559: FS', '640: FS', '540: FS', '953: FS', '955: FS', '859: FS', '610: FS', '867: FS', '594: FS', '346: FS', '345: FS'] | ['295: FS', '229: FS']
345 | Not Started | MDC1-BL.2 | Level of Effort | MDC1 Admin/COLO1 - Fitout Summary | 2020-08-14 07:00 | 2021-05-15 08:00 |  |  |  |  | 0 | 0 | 214 | 214 | 0 | 0 |  |  |  |  | MDC1.C1.C1000: SS | MDC1.M1010: FS |  | 0 | 0 |  | ['1288: SS'] | ['344: FS']
346 | Not Started | MDC1-BL.5.2.3.7 | Task Dependent | Weather(5 Days) | 2021-05-10 08:00 | 2021-05-15 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C1.C4400: FS, MDC1.AD.Cx2000: FS, MDC1.AD.Cx2020: FS, MDC1.C1.Cx2060: FS, MDC1.C1.Cx2150: FS, MDC1.C1.Cx2090: FS, MDC1.C1.Cx3040: FS | MDC1.M1010: FS |  | 0 | 0 |  | ['747: FS', '640: FS', '540: FS', '559: FS', '512: FS', '541: FS', '355: FS'] | ['344: FS']
347 | Not Started | MDC1-BL.5.3.6.4.4.4 | Task Dependent | Fire Alarm Installation | 2021-04-30 07:00 | 2021-05-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 8 | 8 |  |  |  |  | MDC1.C4.C4110: FS, MDC1.C4.C4100: FS, MDC1.C4.C4390: SS 5 | MDC1.C4.C4410: FS | VECA Electricians | 240 | 0 |  | ['668: FS', '713: FS', '336: SS 5'] | ['315: FS']
348 | Not Started | MDC1-BL.5.1.4 | Task Dependent | Curb & Gutter | 2021-04-08 07:00 | 2021-05-14 17:00 |  |  |  |  | 0 | 0 | 30 | 30 | 49 | 49 |  |  |  |  | MDC1.S.1040: FS, MDC1.S.1300: FS, MDC1.C4.C4250: FS, MDC1.C4.CS1050: FS, MDC1.C4.CS1060: FS | MDC1.S.1880: FS, MDC1.S.1900: FS | Advantage | 1500 | 0 |  | ['1302: FS', '1113: FS', '441: FS', '1238: FS', '1178: FS'] | ['297: FS', '257: FS']
349 | Not Started | MDC1-BL.5.2.2.1 | Task Dependent | Cooling Automation | 2021-04-28 08:00 | 2021-05-13 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.Cx3000: FS, MDC1.C2.Cx2130: FS, MDC1.C2.Cx2170: FS, MDC1.C2.Cx2190: FS, MDC1.C2.Cx2080: FS, MDC1.C2.Cx2120: FS, MDC1.C2.Cx2150: FS, MDC1.C2.Cx2180: FS, MDC1.C1.Cx3010: FS | MDC1.C2.Cx3030: FS, MDC1.C3.Cx3010: FS | TCM | 1200 | 0 |  | ['376: FS', '419: FS', '387: FS', '377: FS', '435: FS', '421: FS', '392: FS', '384: FS', '460: FS'] | ['305: FS', '283: FS']
350 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-04-27 07:00 | 2021-05-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 3 | 3 |  |  |  |  | MDC1.C4.C3320: FS, MDC1.C4.C3100: FS, MDC1.C4.C3260: FS, MDC1.C4.C1380: FS | MDC1.C4.Cx2030: FS, MDC1.C4.C3440: FS | VECA Electricians | 960 | 0 |  | ['393: FS', '712: FS', '447: FS', '385: FS'] | ['287: FS', '304: FS']
351 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-04-17 07:00 | 2021-05-11 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 14 | 14 |  |  |  |  | MDC1.C4.C1340: FS, MDC1.C4.C3110: FS, MDC1.C4.C3100: FS, MDC1.C4.C3260: FS, MDC1.C4.C1340: FF | MDC1.C4.Cx2030: FS, MDC1.C4.C3370: SS 5 | VECA Electricians | 1080 | 0 |  | ['418: FS', '667: FS', '712: FS', '447: FS', '418: FF'] | ['287: FS', '358: SS 5']
352 | Not Started | MDC1-BL.5.2.1.7.2 | Task Dependent | Equipment Yellow Tagging | 2021-04-28 07:00 | 2021-05-10 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C3.C3150: FF, MDC1.C3.C3390: FS, MDC1.C3.C3360: FS, MDC1.C3.C3400: FS, MDC1.C3.C3370: FS, MDC1.C3.C3170: FS, MDC1.C3.C3330: FS, MDC1.C3.C3380: FS, MDC1.C3.Cx2000: FS, MDC1-C3.P1800: FS, MDC1.C3.C3050: SS, MDC1.C3.C3000: FS, MDC1-2527: FS | MDC1.C3.Cx2080: FS, MDC1.C3.Cx2160: FS | VECA Electricians | 1200 | 0 |  | ['680: FF', '390: FS', '428: FS', '379: FS', '399: FS', '656: FS', '466: FS', '395: FS', '389: FS', '32: FS', '973: SS', '1153: FS', '1325: FS'] | ['322: FS', '310: FS']
353 | Not Started | MDC1-BL.5.2.1.7.3 | Task Dependent | Network Startup | 2021-04-28 07:00 | 2021-05-10 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 1 | 1 |  |  |  |  | MDC1.C3.C2400: FS, MDC1.C3.Cx2010: FS | MDC1.C3.Cx2090: FS, MDC1.C3.Cx2130: FS, MDC1.C3.Cx2100: FS | LINX- TELECOM | 600 | 0 |  | ['473: FS', '380: FS'] | ['323: FS', '319: FS', '324: FS']
354 | Not Started | MDC1-BL.5.2.1.7.4 | Task Dependent | Equipment Yellow Tagging | 2021-04-28 07:00 | 2021-05-10 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C3.C4190: FF, MDC1.C3.C4420: FS, MDC1.C3.C4390: FS, MDC1.C3.C4440: FS, MDC1.C3.C4410: FS, MDC1.C3.C4210: FS, MDC1.C3.C4370: FS, MDC1.C3.C4430: FS, MDC1.C3.C4140: FS, MDC1.C3.Cx2010: FS, MDC1-C3.P1800: FS | MDC1.C3.Cx2100: FS, MDC1.C3.Cx2170: FS | VECA Electricians | 1200 | 0 |  | ['681: FF', '391: FS', '430: FS', '382: FS', '400: FS', '658: FS', '445: FS', '381: FS', '769: FS', '380: FS', '32: FS'] | ['324: FS', '311: FS']
355 | Not Started | MDC1-BL.5.2.3.7 | Task Dependent | Level 3 Cx - ADMIN AND COLO1 | 2021-04-24 08:00 | 2021-05-10 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.Cx3030: FS, MDC1.C1.Cx3020: FF 10, MDC1-C1.P1900: FS | MDC1.M1010: FS, MDC1.M2010: FS, MDC1.C1.Cx3050: FS, MDC1.C1.Cx4020: FS, MDC1.C1.Cx4010: FS | VECA Electricians | 1200 | 0 |  | ['394: FS', '436: FF 10', '566: FS'] | ['344: FS', '280: FS', '346: FS', '267: FS', '335: FS']
356 | Not Started | MDC1-BL.5.3.6.4.3.4 | Task Dependent | Fire Alarm Installation | 2021-04-24 07:00 | 2021-05-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 3 | 3 |  |  |  |  | MDC1.C4.C2110: FS, MDC1.C4.C2100: FS, MDC1.C4.C2360: FS | MDC1.C4.C2430: FS | VECA Electricians | 240 | 0 |  | ['723: FS', '791: FS', '396: FS'] | ['320: FS']
357 | Not Started | MDC1-BL.5.2.1.7.1 | Task Dependent | Network Startup | 2021-04-26 07:00 | 2021-05-07 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.C3.C1410: FS, MDC1.C3.Cx2000: FS | MDC1.C3.Cx2060: FS, MDC1.C3.Cx2110: FS, MDC1.C3.Cx2080: FS | LINX- TELECOM | 600 | 0 |  | ['471: FS', '389: FS'] | ['329: FS', '326: FS', '322: FS']
358 | Not Started | MDC1-BL.5.3.6.4.2.4 | Task Dependent | Fire Alarm Installation | 2021-04-23 07:00 | 2021-05-07 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 14 | 14 |  |  |  |  | MDC1.C4.C3110: FS, MDC1.C4.C3100: FS, MDC1.C4.C3390: SS 5 | MDC1.C4.C3410: FS | VECA Electricians | 240 | 0 |  | ['667: FS', '712: FS', '351: SS 5'] | ['325: FS']
359 | Not Started | MDC1-BL.5.3.6.4.10.1 | Task Dependent | PDU's Installation | 2021-05-04 07:00 | 2021-05-06 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 6 | 6 |  |  |  |  | MDC1.C4.C3340: FS, MDC1.C4.E1440: FS, MDC1.C4.E1450: FS | MDC1.C4.C3420: FS, MDC1.C4.C3450: FS | VECA Electricians | 180 | 0 |  | ['373: FS', '211: FS', '212: FS'] | ['313: FS', '290: FS']
360 | Not Started | MDC1-BL.5.3.6.4.13.1 | Task Dependent | PDU's Installation | 2021-05-04 07:00 | 2021-05-06 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 6 | 6 |  |  |  |  | MDC1.C4.C4320: FS, MDC1.C4.C4210: FS, MDC1.C4.E1460: FS, MDC1.C4.E1470: FS | MDC1.C4.C4420: FS, MDC1.C4.C4450: FS | VECA Electricians | 180 | 0 |  | ['374: FS', '457: FS', '215: FS', '216: FS'] | ['314: FS', '291: FS']
361 | Not Started | MDC1-BL.5.3.8.4.10.1 | Task Dependent | Light Fixtures Installation | 2021-04-28 07:00 | 2021-05-05 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 74 | 74 |  |  |  |  | MDC1.C3.C3390: FS, MDC1.C3.C3400: FS, MDC1.C3.C3340: FS | MDC1-C3.P1900: FS, MDC1-C3.P1900: SS | VECA Electricians | 480 | 0 |  | ['390: FS', '379: FS', '467: FS'] | ['367: FS', '367: SS']
362 | Not Started | MDC1-BL.5.3.8.4.13.1 | Task Dependent | Light Fixtures Installation | 2021-04-28 07:00 | 2021-05-05 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 74 | 74 |  |  |  |  | MDC1.C3.C4420: FS, MDC1.C3.C4440: FS, MDC1.C3.C4360: FS | MDC1-C3.P1900: FS, MDC1-C3.P1900: SS | VECA Electricians | 480 | 0 |  | ['391: FS', '382: FS', '468: FS'] | ['367: FS', '367: SS']
363 | Not Started | MDC1-BL.5.3.6.4.9.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-04-21 07:00 | 2021-05-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C1360: FS | MDC1.C4.C1460: FS, MDC1.C4.Cx2020: FS, MDC1.C4.Cx2000: FS, MDC1.C4.C1430: FS | LINX- TELECOM | 1440 | 0 |  | ['405: FS'] | ['293: FS', '289: FS', '312: FS', '330: FS']
364 | Not Started | MDC1-BL.5.3.6.4.10.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-04-21 07:00 | 2021-05-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C3310: FS | MDC1.C4.C3400: FS | LINX- TELECOM | 1440 | 0 |  | ['406: FS'] | ['331: FS']
365 | Not Started | MDC1-BL.5.3.6.4.11.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-04-21 07:00 | 2021-05-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C2340: FS | MDC1.C4.C2460: FS, MDC1.C4.Cx2040: FS, MDC1.C4.Cx2010: FS, MDC1.C4.C2420: FS | LINX- TELECOM | 1440 | 0 |  | ['407: FS'] | ['294: FS', '284: FS', '298: FS', '332: FS']
366 | Not Started | MDC1-BL.5.3.6.4.13.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-04-21 07:00 | 2021-05-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C4280: FS | MDC1.C4.C4400: FS | LINX- TELECOM | 1440 | 0 |  | ['408: FS'] | ['333: FS']
367 | Not Started | MDC1-BL.3.4 | Finish Milestone | COLO 3 CSA complete |  | 2021-05-05 17:00 |  |  | 2021-05-05 17:00 |  | 0 | 0 | 0 | 0 | 74 | 74 |  |  |  |  | MDC1.C3.C3240: FS, MDC1.C3.C4260: FS, MDC1.C3.C1250: FS, MDC1.C3.C3160: FS, MDC1.C3.C2200: FS, MDC1.C3.C4200: FS, MDC1.C3.C3290: FS, MDC1.C3.C2410: FS, MDC1.C3.C2230: FS, MDC1.C3.C4250: FS, MDC1.C3.C3410: FS, MDC1.C3.C2450: FS, MDC1.C3.C4450: FS, MDC1.C4.C1260: FS, MDC1.C4.C3220: FS, MDC1.C3.C1450: FS, MDC1.C3.C3410: SS, MDC1.C3.C2450: SS, MDC1.C3.C4450: SS, MDC1.C3.C1300: FS, MDC1.C3.C3220: FS, MDC1.C3.C1290: FS, MDC1.C3.C3210: FS, MDC1.C3.C2220: FS, MDC1.C3.C4240: FS | MDC1.C1.Cx4020: FS, MDC1.M3010: FS |  | 0 | 0 |  | ['580: FS', '581: FS', '637: FS', '655: FS', '779: FS', '657: FS', '504: FS', '454: FS', '698: FS', '600: FS', '361: FS', '404: FS', '362: FS', '488: FS', '456: FS', '403: FS', '361: SS', '404: SS', '362: SS', '579: FS', '598: FS', '578: FS', '597: FS', '697: FS', '599: FS'] | ['267: FS', '246: FS']
368 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-04-20 07:00 | 2021-05-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.C2330: FS, MDC1.C4.C2100: FS, MDC1.C4.C2280: FS | MDC1.C4.Cx2010: FS, MDC1.C4.C2440: FS | VECA Electricians | 960 | 0 |  | ['414: FS', '791: FS', '470: FS'] | ['298: FS', '317: FS']
369 | Not Started | MDC1-BL.5.3.6.4.8.3 | Task Dependent | Toilet Piping Installation / DW | 2021-04-20 07:00 | 2021-05-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 108 | 108 |  |  |  |  | MDC1.C4.C4270: FS, MDC1.C4.C4230: FS | MDC1-C4.P1900: FS | TCM | 480 | 0 |  | ['413: FS', '451: FS'] | ['292: FS']
370 | Not Started | MDC1-BL.5.3.6.4.7.1 | Task Dependent | Ligthing Installation | 2021-04-19 07:00 | 2021-05-03 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C3.C4400: FS, MDC1.C4.C2160: FS, MDC1.C4.C2200: FS | MDC1.C4.C4380: FS, MDC1-C4.P1900: FS | VECA Electricians | 480 | 0 |  | ['415: FS', '633: FS', '553: FS'] | ['340: FS', '292: FS']
371 | Not Started | MDC1-BL.5.3.6.4.13.3 | Task Dependent | Fire Alarm System | 2021-04-21 07:00 | 2021-05-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 18 | 18 |  |  |  |  | MDC1.C4.C4280: FS | MDC1.C4.C4430: FS | VECA Electricians | 600 | 0 |  | ['408: FS'] | ['309: FS']
372 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-04-21 07:00 | 2021-05-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C4260: FS, MDC1.C4.C4290: FS, MDC1.C4.C2330: FS | MDC1.C4.C4370: FS | VECA Electricians | 560 | 0 |  | ['434: FS', '409: FS', '414: FS'] | ['339: FS']
373 | Not Started | MDC1-BL.5.3.6.4.10.1 | Task Dependent | Power Bus Installation | 2021-04-21 07:00 | 2021-05-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 6 | 6 |  |  |  |  | MDC1.C4.C3310: FS | MDC1.C4.C3360: FS, MDC1.C4.E1440: FS | VECA Electricians | 1200 | 0 |  | ['406: FS'] | ['359: FS', '211: FS']
374 | Not Started | MDC1-BL.5.3.6.4.13.1 | Task Dependent | Power Bus Installation | 2021-04-21 07:00 | 2021-05-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 6 | 6 |  |  |  |  | MDC1.C4.C4280: FS | MDC1.C4.C4350: FS, MDC1.C4.E1460: FS | VECA Electricians | 1200 | 0 |  | ['408: FS'] | ['360: FS', '215: FS']
375 | Not Started | MDC1-BL.5.3.6.4.1.4 | Task Dependent | Fire Alarm Installation | 2021-04-17 07:00 | 2021-04-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 9 | 9 |  |  |  |  | MDC1.C4.C1110: FS, MDC1.C4.C1100: FS, MDC1.C4.C1340: FS, MDC1.C4.C1120: FS | MDC1.C4.C1410: FS, MDC1-C4.P1800: FS | VECA Electricians | 240 | 0 |  | ['720: FS', '789: FS', '418: FS', '692: FS'] | ['343: FS', '33: FS']
376 | Not Started | MDC1-BL.5.2.2.1 | Task Dependent | Hydronic Pipe Flush (Open and closed Loop) | 2021-04-14 08:00 | 2021-04-28 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.Cx2110: SS 10, MDC1.C2.Cx2170: SS 10, MDC1.C2.Cx2080: SS 10, MDC1.C2.Cx2150: SS 10, MDC1.C1.Cx3000: FS | MDC1.C2.Cx3010: FS, MDC1.C3.Cx3000: FS 11 | TCM | 1200 | 0 |  | ['424: SS 10', '387: SS 10', '435: SS 10', '392: SS 10', '507: FS'] | ['349: FS', '300: FS 11']
377 | Not Started | MDC1-BL.5.2.2.6.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-04-14 08:00 | 2021-04-28 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.Cx2100: FS | MDC1.C2.Cx3010: FS, MDC1.C2.Cx3020: FS, MDC1-C2.P2000: FS | TCM | 640 | 0 |  | ['423: FS'] | ['349: FS', '321: FS', '378: FS']
378 | Not Started | MDC1-BL.3.3 | Finish Milestone | Construction Server- COLO-2 |  | 2021-04-28 08:00 |  |  | 2021-04-28 08:00 |  | 0 | 0 | 0 | 0 | 12 | 12 |  |  |  |  | MDC1.C2.Cx2180: FS, MDC1.C2.Cx2120: FS, MDC1.C2.Cx2190: FS, MDC1.C2.Cx2130: FS | MDC1.C2.Cx3020: FS |  | 0 | 0 |  | ['384: FS', '421: FS', '377: FS', '419: FS'] | ['321: FS']
379 | Not Started | MDC1-BL.5.3.8.4.10.3 | Task Dependent | Controls Installation | 2021-04-14 07:00 | 2021-04-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C3270: FS, MDC1.C3.C3300: FS, MDC1.C3.C3360: FS | MDC1.C3.C3410: FS, MDC1.C3.Cx2030: FS | VECA Electricians | 720 | 0 |  | ['521: FS', '487: FS', '428: FS'] | ['361: FS', '352: FS']
380 | Not Started | MDC1-BL.5.2.1.7.3 | Task Dependent | Equipment Yellow Tagging | 2021-04-16 07:00 | 2021-04-27 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C3.C2180: FF, MDC1.C3.C2420: FS, MDC1.C3.C2400: FS, MDC1.C3.C2430: FS, MDC1.C3.C2390: FS, MDC1.C3.C2210: FS, MDC1.C3.C2380: FS, MDC1.C3.C2440: FS, MDC1.C3.C2170: FS, MDC1-C3.P1800: FS | MDC1.C3.Cx2040: FS, MDC1.C3.Cx2120: FS, MDC1.C3.Cx2050: FS | VECA Electricians | 1200 | 0 |  | ['825: FF', '439: FS', '473: FS', '429: FS', '477: FS', '780: FS', '485: FS', '420: FS', '857: FS', '32: FS'] | ['353: FS', '327: FS', '354: FS']
381 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Pull Conductors into Building | 2021-04-06 07:00 | 2021-04-27 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C3.C4100: FS, MDC1.C3.C4370: FS | MDC1.C3.Cx2050: FS | VECA Electricians | 1440 | 0 |  | ['875: FS', '445: FS'] | ['354: FS']
382 | Not Started | MDC1-BL.5.3.8.4.13.3 | Task Dependent | Controls Installation | 2021-04-14 07:00 | 2021-04-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C4310: FS, MDC1.C3.C4330: FS, MDC1.C3.C4390: FS | MDC1.C3.C4450: FS, MDC1.C3.Cx2050: FS | VECA Electricians | 720 | 0 |  | ['523: FS', '480: FS', '430: FS'] | ['362: FS', '354: FS']
383 | Not Started | MDC1-BL.5.3.6.4.10.3 | Task Dependent | Fire Alarm System | 2021-04-16 07:00 | 2021-04-27 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 22 | 22 |  |  |  |  | MDC1.C4.C3310: FF 6 | MDC1.C4.C3430: FS | VECA Electricians | 600 | 0 |  | ['406: FF 6'] | ['308: FS']
384 | Not Started | MDC1-BL.5.2.2.6.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-04-14 07:00 | 2021-04-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.Cx2070: FS | MDC1.C2.Cx3010: FS, MDC1.C2.Cx3020: FS, MDC1-C2.P2000: FS | TCM | 640 | 0 |  | ['426: FS'] | ['349: FS', '321: FS', '378: FS']
385 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-04-13 07:00 | 2021-04-26 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 3 | 3 |  |  |  |  | MDC1.C4.C1320: FS, MDC1.C4.C1100: FS, MDC1.C4.C1280: FS | MDC1.C4.Cx2000: FS, MDC1.C4.C1440: FS, MDC1.C4.C3380: FS | VECA Electricians | 960 | 0 |  | ['437: FS', '789: FS', '486: FS'] | ['312: FS', '328: FS', '350: FS']
386 | Not Started | MDC1-BL.5.2.2.6.2 | Task Dependent | EPMS Checkout / Point to Point | 2021-04-14 08:00 | 2021-04-26 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C2.Cx2100: FS, MDC1.C2.Cx2090: FS | MDC1.C2.Cx3030: FS, MDC1.C2.Cx3040: FS, MDC1.M2010: FS | LINX- TELECOM | 1200 | 0 |  | ['423: FS', '422: FS'] | ['305: FS', '286: FS', '280: FS']
387 | Not Started | MDC1-BL.5.2.2.6.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-04-01 08:00 | 2021-04-26 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C2.Cx2050: FS | MDC1.C2.Cx3000: SS 10, MDC1.C2.Cx3010: FS | VECA Electricians | 2000 | 0 |  | ['462: FS'] | ['376: SS 10', '349: FS']
388 | Not Started | MDC1-BL.5.2.2.6.4 | Task Dependent | EPMS Checkout / Point to Point | 2021-04-14 07:00 | 2021-04-24 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C2.Cx2070: FS, MDC1.C2.Cx2060: FS | MDC1.C2.Cx3030: FS | LINX- TELECOM | 1200 | 0 |  | ['426: FS', '425: FS'] | ['305: FS']
389 | Not Started | MDC1-BL.5.2.1.7.1 | Task Dependent | Equipment Yellow Tagging | 2021-04-14 07:00 | 2021-04-24 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C3.C1180: FF, MDC1.C3.C1430: FS, MDC1.C3.C1410: FS, MDC1.C3.C1440: FS, MDC1.C3.C1400: FS, MDC1.C3.C1190: FS, MDC1.C3.C1380: FS, MDC1.C3.C1420: FS, MDC1.C3.C1170: FS | MDC1.C3.Cx2020: FS, MDC1-C3.P1800: SS, MDC1.C3.Cx2070: FS, MDC1.C3.Cx2030: FS | VECA Electricians | 1200 | 0 |  | ['822: FF', '438: FS', '471: FS', '427: FS', '476: FS', '778: FS', '514: FS', '440: FS', '856: FS'] | ['357: FS', '32: SS', '334: FS', '352: FS']
390 | Not Started | MDC1-BL.5.3.8.4.10.1 | Task Dependent | Pull / Term / Test Conductors | 2021-03-31 07:00 | 2021-04-24 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 2 | 2 |  |  |  |  | MDC1.C3.C3340: FS | MDC1.C3.C3410: FS, MDC1.C3.Cx2030: FS | VECA Electricians | 1680 | 0 |  | ['467: FS'] | ['361: FS', '352: FS']
391 | Not Started | MDC1-BL.5.3.8.4.13.1 | Task Dependent | Pull / Term / Test Conductors | 2021-03-31 07:00 | 2021-04-24 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 2 | 2 |  |  |  |  | MDC1.C3.C4360: FS | MDC1.C3.C4450: FS, MDC1.C3.Cx2050: FS | VECA Electricians | 1680 | 0 |  | ['468: FS'] | ['362: FS', '354: FS']
392 | Not Started | MDC1-BL.5.2.2.6.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-04-01 07:00 | 2021-04-24 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C2.Cx2030: FS | MDC1.C2.Cx3000: SS 10, MDC1.C2.Cx3010: FS | VECA Electricians | 2000 | 0 |  | ['464: FS'] | ['376: SS 10', '349: FS']
393 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-04-14 07:00 | 2021-04-24 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C4.C3260: FS, MDC1.C4.C3270: FS, MDC1.C4.C1320: FS | MDC1.C4.C3380: FS | VECA Electricians | 560 | 0 |  | ['447: FS', '432: FS', '437: FS'] | ['350: FS']
394 | Not Started | MDC1-BL.5.2.3.7 | Task Dependent | Load Bank & IR Scan | 2021-04-02 08:00 | 2021-04-24 08:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2190: FS, MDC1.C1.Cx2090: FS, MDC1.C1.Cx2150: FS, MDC1.C1.Cx2060: FS, MDC1.AD.Cx2020: FS, MDC1.C1.Cx3010: FS, MDC1.S.1850: FS | MDC1.C1.Cx3040: FS, MDC1.C2.Cx3030: FS 15 | VECA Electricians | 3600 | 0 |  | ['493: FS', '541: FS', '512: FS', '559: FS', '540: FS', '460: FS', '601: FS'] | ['355: FS', '305: FS 15']
395 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Pull Conductors into Building | 2021-03-31 07:00 | 2021-04-23 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 3 | 3 |  |  |  |  | MDC1.C3.C3080: FS, MDC1.C3.C3330: FS | MDC1.C3.Cx2030: FS | VECA Electricians | 1440 | 0 |  | ['874: FS', '466: FS'] | ['352: FS']
396 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-03-31 07:00 | 2021-04-23 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 3 | 3 |  |  |  |  | MDC1.C4.C2110: FS, MDC1.C4.C2100: FS, MDC1.C4.C2280: FS | MDC1.C4.C4390: FS, MDC1.C4.C2400: FS, MDC1.C4.C4390: FF | VECA Electricians | 1080 | 0 |  | ['723: FS', '791: FS', '470: FS'] | ['336: FS', '356: FS', '336: FF']
397 | Not Started | MDC1-BL.5.3.8.4.9.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-03-30 07:00 | 2021-04-22 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C2.C3460: FS, MDC1.C3.C1410: FS | MDC1.C3.Cx4000: FS, MDC1.C3.C3420: FS | LINX- TELECOM | 1440 | 0 |  | ['484: FS', '471: FS'] | ['241: FS', '341: FS']
398 | Not Started | MDC1-BL.5.3.8.4.11.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-03-30 07:00 | 2021-04-22 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C2.C4420: FS, MDC1.C3.C2400: FS | MDC1.C3.Cx4000: FS, MDC1.C3.C4460: FS | LINX- TELECOM | 1440 | 0 |  | ['475: FS', '473: FS'] | ['241: FS', '342: FS']
399 | Not Started | MDC1-BL.5.3.8.4.2.4 | Task Dependent | Controls Installation | 2021-04-07 07:00 | 2021-04-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 5 | 5 |  |  |  |  | MDC1.C3.C3080: FS, MDC1.C3.C3110: FS, MDC1.C3.C3350: FS, MDC1.C3.C3050: SS, MDC1.C3.C3000: FS, MDC1-2527: FS | MDC1.C3.Cx2030: FS | VECA Electricians | 720 | 0 |  | ['874: FS', '788: FS', '442: FS', '973: SS', '1153: FS', '1325: FS'] | ['352: FS']
400 | Not Started | MDC1-BL.5.3.8.4.4.4 | Task Dependent | Controls Installation | 2021-04-07 07:00 | 2021-04-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 5 | 5 |  |  |  |  | MDC1.C3.C4100: FS, MDC1.C3.C4130: FS, MDC1.C3.C4180: FS, MDC1.C3.C4380: FS | MDC1.C3.Cx2050: FS | VECA Electricians | 720 | 0 |  | ['875: FS', '800: FS', '719: FS', '443: FS'] | ['354: FS']
401 | Not Started | MDC1-BL.5.3.6.4.9.1 | Task Dependent | PDU's Installation | 2021-04-19 07:00 | 2021-04-21 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 8 | 8 |  |  |  |  | MDC1.C4.C1350: FS, MDC1.C4.E1400: FS, MDC1.C4.E1410: FS | MDC1.C4.C1420: FS, MDC1.C4.C1450: FS | VECA Electricians | 180 | 0 |  | ['416: FS', '209: FS', '210: FS'] | ['337: FS', '316: FS']
402 | Not Started | MDC1-BL.5.3.6.4.11.1 | Task Dependent | PDU's Installation | 2021-04-19 07:00 | 2021-04-21 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 8 | 8 |  |  |  |  | MDC1.C4.C2320: FS, MDC1.C4.E1420: FS, MDC1.C4.E1430: FS | MDC1.C4.C2410: FS, MDC1.C4.C2450: FS | VECA Electricians | 180 | 0 |  | ['417: FS', '213: FS', '214: FS'] | ['338: FS', '318: FS']
403 | Not Started | MDC1-BL.5.3.8.4.9.1 | Task Dependent | Light Fixtures Installation | 2021-04-14 07:00 | 2021-04-20 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 86 | 86 |  |  |  |  | MDC1.C3.C1430: FS, MDC1.C3.C1440: FS, MDC1.C3.C1390: FS | MDC1-C3.P1900: FS | VECA Electricians | 480 | 0 |  | ['438: FS', '427: FS', '515: FS'] | ['367: FS']
404 | Not Started | MDC1-BL.5.3.8.4.11.1 | Task Dependent | Light Fixtures Installation | 2021-04-14 07:00 | 2021-04-20 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 86 | 86 |  |  |  |  | MDC1.C3.C2420: FS, MDC1.C3.C2430: FS, MDC1.C3.C2370: FS | MDC1-C3.P1900: FS, MDC1-C3.P1900: SS | VECA Electricians | 480 | 0 |  | ['439: FS', '429: FS', '516: FS'] | ['367: FS', '367: SS']
405 | Not Started | MDC1-BL.5.3.6.4.9.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-04-06 07:00 | 2021-04-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C1310: FS, MDC1.C4.C1330: FF 6 | MDC1.C4.C1400: FS | LINX- TELECOM | 1440 | 0 |  | ['446: FS', '431: FF 6'] | ['363: FS']
406 | Not Started | MDC1-BL.5.3.6.4.10.1 | Task Dependent | Cable Tray Installation | 2021-04-06 07:00 | 2021-04-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C1310: FS, MDC1.C4.C3230: FS | MDC1.C4.C3350: FS, MDC1.C4.C3340: FS, MDC1.C4.C3430: FS, MDC1.C4.C3330: FF 6 | VECA Electricians | 1440 | 0 |  | ['446: FS', '458: FS'] | ['364: FS', '373: FS', '308: FS', '383: FF 6']
407 | Not Started | MDC1-BL.5.3.6.4.11.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-04-06 07:00 | 2021-04-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C2290: FS | MDC1.C4.C2390: FS | LINX- TELECOM | 1440 | 0 |  | ['448: FS'] | ['365: FS']
408 | Not Started | MDC1-BL.5.3.6.4.13.1 | Task Dependent | Cable Tray Installation | 2021-04-06 07:00 | 2021-04-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C4220: FS, MDC1.C4.C2290: FS | MDC1.C4.C4340: FS, MDC1.C4.C4320: FS, MDC1.C4.C4420: FS, MDC1.C4.C4430: FS, MDC1.C4.C4300: FS | VECA Electricians | 1440 | 0 |  | ['459: FS', '448: FS'] | ['366: FS', '374: FS', '314: FS', '309: FS', '371: FS']
409 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-04-08 07:00 | 2021-04-20 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C4250: FS | MDC1.C4.C4310: FS |  | 0 | 0 |  | ['441: FS'] | ['372: FS']
410 | Not Started | MDC1-BL.5.3.6.4.6.1 | Task Dependent | Ligthing Installation | 2021-04-05 07:00 | 2021-04-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 120 | 120 |  |  |  |  | MDC1.C4.C1300: FS, MDC1.C4.C3160: FS, MDC1.C4.C3240: FS | MDC1-C4.P1900: FS | VECA Electricians | 480 | 0 |  | ['455: FS', '530: FS', '449: FS'] | ['292: FS']
411 | Not Started | MDC1-BL.5.3.6.4.6.3 | Task Dependent | Floor Drain System Installation | 2021-04-05 07:00 | 2021-04-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 120 | 120 |  |  |  |  | MDC1.C4.C3010: FS, MDC1.C4.C3240: FS | MDC1-C4.P1900: FS |  | 0 | 0 |  | ['892: FS', '449: FS'] | ['292: FS']
412 | Not Started | MDC1-BL.5.3.6.4.6.3 | Task Dependent | Toilet Piping Installation / DW | 2021-04-05 07:00 | 2021-04-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 120 | 120 |  |  |  |  | MDC1.C4.C3240: FS | MDC1-C4.P1900: FS | TCM | 480 | 0 |  | ['449: FS'] | ['292: FS']
413 | Not Started | MDC1-BL.5.3.6.4.8.3 | Task Dependent | Floor Drain System Installation | 2021-04-05 07:00 | 2021-04-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 108 | 108 |  |  |  |  | MDC1.C4.C4010: FS, MDC1.C4.C4230: FS | MDC1.C4.C4330: FS, MDC1-C4.P1900: FS |  | 0 | 0 |  | ['894: FS', '451: FS'] | ['369: FS', '292: FS']
414 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-04-07 07:00 | 2021-04-19 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C2280: FS, MDC1.C4.C2300: FS | MDC1.C4.C2380: FS, MDC1.C4.C4310: FS | VECA Electricians | 560 | 0 |  | ['470: FS', '444: FS'] | ['368: FS', '372: FS']
415 | Not Started | MDC1-BL.5.3.8.4.8.1 | Task Dependent | Ligthing Installation | 2021-04-03 07:00 | 2021-04-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C3.C2410: FS, MDC1.C3.C4160: FS, MDC1.C3.C4200: FS | MDC1.C4.C2370: FS | VECA Electricians | 480 | 0 |  | ['454: FS', '743: FS', '657: FS'] | ['370: FS']
416 | Not Started | MDC1-BL.5.3.6.4.9.1 | Task Dependent | Power Bus Installation | 2021-04-06 07:00 | 2021-04-17 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 8 | 8 |  |  |  |  | MDC1.C4.C1310: FS | MDC1.C4.C1370: FS, MDC1.C4.E1400: FS | VECA Electricians | 1200 | 0 |  | ['446: FS'] | ['401: FS', '209: FS']
417 | Not Started | MDC1-BL.5.3.6.4.11.1 | Task Dependent | Power Bus Installation | 2021-04-06 07:00 | 2021-04-17 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 8 | 8 |  |  |  |  | MDC1.C4.C2290: FS, MDC1.C4.C2260: FS | MDC1.C4.C2350: FS, MDC1.C4.E1420: FS | VECA Electricians | 1200 | 0 |  | ['448: FS', '492: FS'] | ['402: FS', '213: FS']
418 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-03-24 07:00 | 2021-04-16 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 9 | 9 |  |  |  |  | MDC1.C4.C1110: FS, MDC1.C4.C1100: FS, MDC1.C4.C1280: FS | MDC1.C4.C3390: FS, MDC1.C4.C1390: FS, MDC1.C4.C3390: FF | VECA Electricians | 1080 | 0 |  | ['720: FS', '789: FS', '486: FS'] | ['351: FS', '375: FS', '351: FF']
419 | Not Started | MDC1-BL.5.2.2.6.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-04-01 08:00 | 2021-04-16 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 10 | 10 |  |  |  |  | MDC1.C2.Cx2040: FS | MDC1.C2.Cx3020: FS, MDC1.C2.Cx3010: FS, MDC1-C2.P2000: FS | TCM | 640 | 0 |  | ['461: FS'] | ['321: FS', '349: FS', '378: FS']
420 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Pull Conductors into Building | 2021-03-24 07:00 | 2021-04-15 17:00 |  |  |  |  | 0 | 0 | 19 | 19 | 0 | 0 |  |  |  |  | MDC1.C3.C2110: FS, MDC1.C3.C2380: FS | MDC1.C3.Cx2010: FS | VECA Electricians | 1440 | 0 |  | ['974: FS', '485: FS'] | ['380: FS']
421 | Not Started | MDC1-BL.5.2.2.6.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-04-01 07:00 | 2021-04-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 10 | 10 |  |  |  |  | MDC1.C2.Cx2020: FS | MDC1.C2.Cx3010: FS, MDC1.C2.Cx3020: FS, MDC1-C2.P2000: FS | TCM | 640 | 0 |  | ['463: FS'] | ['349: FS', '321: FS', '378: FS']
422 | Not Started | MDC1-BL.5.2.2.6.1 | Task Dependent | EPMS Checkout / Point to Point | 2021-04-01 08:00 | 2021-04-14 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C2.Cx2040: FS | MDC1.C2.Cx3030: FS, MDC1.C2.Cx3040: FS, MDC1.M2010: FS, MDC1.C2.Cx2160: FS | LINX- TELECOM | 1200 | 0 |  | ['461: FS'] | ['305: FS', '286: FS', '280: FS', '386: FS']
423 | Not Started | MDC1-BL.5.2.2.6.2 | Task Dependent | Network Startup | 2021-04-01 08:00 | 2021-04-14 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C3330: FS, MDC1.C2.Cx2050: FS, MDC1.C2.Cx2040: FS | MDC1.C2.Cx2160: FS, MDC1.C2.Cx2190: FS | LINX- TELECOM | 600 | 0 |  | ['672: FS', '462: FS', '461: FS'] | ['386: FS', '377: FS']
424 | Not Started | MDC1-BL.5.2.2.6.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-03-19 08:00 | 2021-04-14 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 10 | 10 |  |  |  |  | MDC1.C2.Cx2010: FS | MDC1.C2.Cx3000: SS 10 | VECA Electricians | 2000 | 0 |  | ['498: FS'] | ['376: SS 10']
425 | Not Started | MDC1-BL.5.2.2.6.3 | Task Dependent | EPMS Checkout / Point to Point | 2021-04-01 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C2.Cx2020: FS | MDC1.C2.Cx3030: FS, MDC1.C2.Cx3040: FS, MDC1.M2010: FS, MDC1.C2.Cx2140: FS | LINX- TELECOM | 1200 | 0 |  | ['463: FS'] | ['305: FS', '286: FS', '280: FS', '388: FS']
426 | Not Started | MDC1-BL.5.2.2.6.4 | Task Dependent | Network Startup | 2021-04-01 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C4290: FS, MDC1.C2.Cx2030: FS, MDC1.C2.Cx2020: FS | MDC1.C2.Cx2140: FS, MDC1.C2.Cx2180: FS | LINX- TELECOM | 600 | 0 |  | ['674: FS', '464: FS', '463: FS'] | ['388: FS', '384: FS']
427 | Not Started | MDC1-BL.5.3.8.4.9.3 | Task Dependent | Controls Installation | 2021-03-30 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C1310: FS, MDC1.C3.C1340: FS, MDC1.C3.C1410: FS | MDC1.C3.C1450: FS, MDC1.C3.Cx2000: FS, MDC1-C3.P1800: FS | VECA Electricians | 720 | 0 |  | ['569: FS', '546: FS', '471: FS'] | ['403: FS', '389: FS', '32: FS']
428 | Not Started | MDC1-BL.5.3.8.4.10.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-03-30 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C3320: FS | MDC1.C3.C3420: FS, MDC1.C3.Cx2080: FS, MDC1.C3.Cx2030: FS, MDC1.C3.C3400: FS | LINX- TELECOM | 1440 | 0 |  | ['472: FS'] | ['341: FS', '322: FS', '352: FS', '379: FS']
429 | Not Started | MDC1-BL.5.3.8.4.11.3 | Task Dependent | Controls Installation | 2021-03-30 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C2310: FS, MDC1.C3.C2320: FS, MDC1.C3.C2400: FS | MDC1.C3.C2450: FS, MDC1.C3.Cx2010: FS | VECA Electricians | 720 | 0 |  | ['570: FS', '547: FS', '473: FS'] | ['404: FS', '380: FS']
430 | Not Started | MDC1-BL.5.3.8.4.13.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-03-30 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C4350: FS | MDC1.C3.C4460: FS, MDC1.C3.Cx2100: FS, MDC1.C3.Cx2050: FS, MDC1.C3.C4440: FS | LINX- TELECOM | 1440 | 0 |  | ['474: FS'] | ['342: FS', '324: FS', '354: FS', '382: FS']
431 | Not Started | MDC1-BL.5.3.6.4.9.3 | Task Dependent | Fire Alarm System | 2021-04-01 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 6 | 6 |  |  |  |  | MDC1.C4.C1310: FF 6 | MDC1.C4.C1360: FF 6, MDC1.C4.C1430: FS, MDC1-C4.P1800: FS | VECA Electricians | 600 | 0 |  | ['446: FF 6'] | ['405: FF 6', '330: FS', '33: FS']
432 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-04-01 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C4.C3210: FS | MDC1.C4.C3320: FS |  | 0 | 0 |  | ['465: FS'] | ['393: FS']
433 | Not Started | MDC1-BL.5.3.6.4.11.3 | Task Dependent | Fire Alarm System | 2021-04-01 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 24 | 24 |  |  |  |  | MDC1.C4.C2290: FF 6 | MDC1.C4.C2420: FS | VECA Electricians | 600 | 0 |  | ['448: FF 6'] | ['332: FS']
434 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-04-08 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 6 | 6 |  |  |  |  | MDC1.C4.C4060: FS, MDC1.C4.C4250: FS, MDC1.C4.C2280: FS | MDC1.C4.C4310: FS, MDC1.C4.C4370: FS, MDC1.C4.C4390: FS | SURE STEEL | 160 | 0 |  | ['792: FS', '441: FS', '470: FS'] | ['372: FS', '339: FS', '336: FS']
435 | Not Started | MDC1-BL.5.2.2.6.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-03-19 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 10 | 10 |  |  |  |  | MDC1.C2.Cx2000: FS | MDC1.C2.Cx3000: SS 10, MDC1.C2.Cx3010: FS | VECA Electricians | 2000 | 0 |  | ['500: FS'] | ['376: SS 10', '349: FS']
436 | Not Started | MDC1-BL.5.2.3.7 | Task Dependent | BAS Prefunctional Testing on Construction Server | 2021-03-18 08:00 | 2021-04-13 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 12 | 12 |  |  |  |  | MDC1.C1.Cx2170: FS, MDC1.C1.Cx2110: FS, MDC1.C1.Cx2180: FS, MDC1.C1.Cx2080: FS, MDC1.C1.C4240: FS, MDC1.C1.C2200: FS, MDC1.C1.C3280: FS, MDC1.C1.C1220: FS, MDC1-C1.P2000: FS | MDC1.C1.Cx3040: FF 10, MDC1.C2.Cx3020: FS | LINX- TELECOM | 2000 | 0 |  | ['510: FS', '538: FS', '508: FS', '550: FS', '921: FS', '1088: FS', '918: FS', '1082: FS', '509: FS'] | ['355: FF 10', '321: FS']
437 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-03-31 07:00 | 2021-04-12 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.C4.C1280: FS, MDC1.C4.C1290: FS | MDC1.C4.C1380: FS, MDC1.C4.C3320: FS | VECA Electricians | 560 | 0 |  | ['486: FS', '469: FS'] | ['385: FS', '393: FS']
438 | Not Started | MDC1-BL.5.3.8.4.9.1 | Task Dependent | Pull / Term / Test Conductors | 2021-03-16 07:00 | 2021-04-09 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 4 | 4 |  |  |  |  | MDC1.C3.C1390: FS | MDC1.C3.C1450: FS, MDC1.C3.Cx2000: FS | VECA Electricians | 1680 | 0 |  | ['515: FS'] | ['403: FS', '389: FS']
439 | Not Started | MDC1-BL.5.3.8.4.11.1 | Task Dependent | Pull / Term / Test Conductors | 2021-03-16 07:00 | 2021-04-09 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 4 | 4 |  |  |  |  | MDC1.C3.C2370: FS | MDC1.C3.C2450: FS, MDC1.C3.Cx2010: FS | VECA Electricians | 1680 | 0 |  | ['516: FS'] | ['404: FS', '380: FS']
440 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Pull Conductors into Building | 2021-03-16 07:00 | 2021-04-08 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 5 | 5 |  |  |  |  | MDC1.C3.C1110: FS, MDC1.C3.C1380: FS, MDC1.C3.C1360: FS | MDC1.C3.Cx2000: FS | VECA Electricians | 1440 | 0 |  | ['972: FS', '514: FS', '527: FS'] | ['389: FS']
441 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Lift & Set MER in Place | 2021-04-02 07:00 | 2021-04-07 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C4.E1390: FS, MDC1.C4.E1230: FS, MDC1.C4.C4060: FS, MDC1.C4.C3210: FS | MDC1.C4.C4260: FS, MDC1.C4.C4290: FS, MDC1.S.1870: FS | VECA Electricians | 120 | 0 |  | ['56: FS', '760: FS', '792: FS', '465: FS'] | ['434: FS', '409: FS', '348: FS']
442 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-03-13 07:00 | 2021-04-06 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 5 | 5 |  |  |  |  | MDC1.C3.C3080: FS, MDC1.C3.C3230: FS, MDC1.C3.C3260: FS, MDC1.C3.C1360: FS, MDC1.C3.C3050: SS, MDC1.C3.C3000: FS, MDC1-2527: FS | MDC1.C3.C3370: FS | VECA Electricians | 1080 | 0 |  | ['874: FS', '591: FS', '562: FS', '527: FS', '973: SS', '1153: FS', '1325: FS'] | ['399: FS']
443 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-03-13 07:00 | 2021-04-06 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 5 | 5 |  |  |  |  | MDC1.C3.C4130: FS, MDC1.C3.C4100: FS, MDC1.C3.C4290: FS, MDC1.C3.C4300: FS, MDC1.C3.C2350: FS | MDC1.C3.C4410: FS | VECA Electricians | 1080 | 0 |  | ['800: FS', '875: FS', '563: FS', '539: FS', '528: FS'] | ['400: FS']
444 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-03-26 07:00 | 2021-04-06 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C2270: FS | MDC1.C4.C2330: FS |  | 0 | 0 |  | ['483: FS'] | ['414: FS']
445 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-03-23 07:00 | 2021-04-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C4320: FS, MDC1.C3.C4100: FS, MDC1.C3.C4290: FS | MDC1.C3.Cx2050: FS, MDC1.C3.C4430: FS | VECA Electricians | 960 | 0 |  | ['490: FS', '875: FS', '563: FS'] | ['354: FS', '381: FS']
446 | Not Started | MDC1-BL.5.3.6.4.9.1 | Task Dependent | Cable Tray Installation | 2021-03-23 07:00 | 2021-04-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C3.C3270: FS, MDC1.C4.C1270: FS | MDC1.C4.C3310: FS, MDC1.C4.C1360: FS, MDC1.C4.C1350: FS, MDC1.C4.C1430: FS, MDC1.C4.C1330: FF 6 | VECA Electricians | 1440 | 0 |  | ['521: FS', '491: FS'] | ['406: FS', '405: FS', '416: FS', '330: FS', '431: FF 6']
447 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-04-01 07:00 | 2021-04-05 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 10 | 10 |  |  |  |  | MDC1.C4.C3060: FS, MDC1.C4.C3210: FS, MDC1.C4.C1280: FS | MDC1.C4.C3320: FS, MDC1.C4.C3380: FS, MDC1.C4.C3390: FS | SURE STEEL | 160 | 0 |  | ['790: FS', '465: FS', '486: FS'] | ['393: FS', '350: FS', '351: FS']
448 | Not Started | MDC1-BL.5.3.6.4.11.1 | Task Dependent | Cable Tray Installation | 2021-03-23 07:00 | 2021-04-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C3.C4310: FS, MDC1.C4.C2260: FS | MDC1.C4.C2340: FS, MDC1.C4.C2320: FS, MDC1.C4.C4280: FS, MDC1.C4.C2420: FS, MDC1.C4.C2310: FF 6 | VECA Electricians | 1440 | 0 |  | ['523: FS', '492: FS'] | ['407: FS', '417: FS', '408: FS', '332: FS', '433: FF 6']
449 | Not Started | MDC1-BL.5.3.6.3.6.2 | Task Dependent | Mechanical Corridor Finishes | 2021-03-13 07:00 | 2021-04-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 120 | 120 |  |  |  |  | MDC1.C4.C3150: FS, MDC1.C4.C3010: FS | MDC1.C4.C3280: FS, MDC1.C4.C3300: FS, MDC1.C4.C3290: FS | PCI | 180 | 0 |  | ['529: FS', '892: FS'] | ['410: FS', '412: FS', '411: FS']
450 | Not Started | MDC1-BL.5.3.6.4.6.4 | Task Dependent | Controls Installation | 2021-03-13 07:00 | 2021-04-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 53 | 53 |  |  |  |  | MDC1.C4.C3160: FS, MDC1.C4.C3090: FS | MDC1.C4.Cx2030: FS | VECA Electricians | 720 | 0 |  | ['530: FS', '722: FS'] | ['287: FS']
451 | Not Started | MDC1-BL.5.3.6.3.8.2 | Task Dependent | Mechanical Corridor Finishes | 2021-03-13 07:00 | 2021-04-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 108 | 108 |  |  |  |  | MDC1.C4.C4150: FS, MDC1.C4.C4010: FS | MDC1.C4.C4380: FS, MDC1.C4.C4330: FS, MDC1.C4.C4270: FS | PCI | 180 | 0 |  | ['532: FS', '894: FS'] | ['340: FS', '369: FS', '413: FS']
452 | Not Started | MDC1-BL.5.3.6.4.8.4 | Task Dependent | Controls Installation | 2021-03-13 07:00 | 2021-04-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 53 | 53 |  |  |  |  | MDC1.C4.C4160: FS, MDC1.C4.C4090: FS | MDC1.C4.Cx2050: FS | VECA Electricians | 720 | 0 |  | ['533: FS', '725: FS'] | ['285: FS']
453 | Not Started | MDC1-BL.5.1.4 | Task Dependent | Plant shutdown for winter | 2020-11-24 07:00 | 2021-04-03 17:00 |  |  |  |  | 0 | 0 | 100 | 100 | 106 | 106 | Start On or After | 2020-11-23 17:00 |  |  | MDC1.S.1300: FS | MDC1.S.1880: FS, MDC1.S.1880: FF |  | 0 | 0 |  | ['1113: FS'] | ['297: FS', '297: FF']
454 | Not Started | MDC1-BL.5.3.8.4.7.1 | Task Dependent | Ligthing Installation | 2021-03-19 07:00 | 2021-04-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C2.C4410: FS, MDC1.C3.C2130: FS, MDC1.C3.C2200: FS | MDC1.C3.C4400: FS, MDC1-C3.P1900: FS | VECA Electricians | 480 | 0 |  | ['503: FS', '910: FS', '779: FS'] | ['415: FS', '367: FS']
455 | Not Started | MDC1-BL.5.3.6.4.5.1 | Task Dependent | Ligthing Installation | 2021-03-19 07:00 | 2021-04-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 121 | 121 |  |  |  |  | MDC1.C3.C3290: FS, MDC1.C4.C1160: FS, MDC1.C4.C1200: FS | MDC1.C4.C3280: FS, MDC1-C4.P1900: FS | VECA Electricians | 480 | 0 |  | ['504: FS', '629: FS', '551: FS'] | ['410: FS', '292: FS']
456 | Not Started | MDC1-BL.5.3.6.3.2.2 | Task Dependent | Datahall Finishes | 2021-03-19 07:00 | 2021-04-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 100 | 100 |  |  |  |  | MDC1.C4.C3190: FS | MDC1-C3.P1900: FS, MDC1-C4.P1900: FS | PCI | 480 | 0 |  | ['505: FS'] | ['367: FS', '292: FS']
457 | Not Started | MDC1-BL.5.3.6.3.4.2 | Task Dependent | Datahall Finishes | 2021-03-19 07:00 | 2021-04-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 30 | 30 |  |  |  |  | MDC1.C4.C4190: FS | MDC1.C4.C4350: FS | PCI | 480 | 0 |  | ['506: FS'] | ['360: FS']
458 | Not Started | MDC1-BL.5.3.6.4.10.1 | Task Dependent | HAC Installation | 2021-03-19 07:00 | 2021-04-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C3190: FS | MDC1.C4.C3310: FS | TCM | 480 | 0 |  | ['505: FS'] | ['406: FS']
459 | Not Started | MDC1-BL.5.3.6.4.13.1 | Task Dependent | HAC Installation | 2021-03-19 07:00 | 2021-04-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C4190: FS | MDC1.C4.C4280: FS | TCM | 480 | 0 |  | ['506: FS'] | ['408: FS']
460 | Not Started | MDC1-BL.5.2.3.7 | Task Dependent | Cooling Automation | 2021-03-18 08:00 | 2021-04-02 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2170: FS, MDC1.C1.Cx2120: FS, MDC1.C1.Cx2130: FS, MDC1.C1.Cx2110: FS, MDC1.C1.Cx2160: FS, MDC1.C1.Cx2180: FS, MDC1.C1.Cx2140: FS, MDC1.C1.Cx2080: FS, MDC1.C1.Cx3000: FS | MDC1.C1.Cx3030: FS, MDC1.C2.Cx3010: FS | TCM | 1200 | 0 |  | ['510: FS', '517: FS', '518: FS', '538: FS', '513: FS', '508: FS', '519: FS', '550: FS', '507: FS'] | ['394: FS', '349: FS']
461 | Not Started | MDC1-BL.5.2.2.6.1 | Task Dependent | Network Startup | 2021-03-19 08:00 | 2021-04-01 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C1340: FS, MDC1.C2.Cx2010: FS | MDC1.C2.Cx2090: FS, MDC1.C2.Cx2130: FS, MDC1.C2.Cx2100: FS | LINX- TELECOM | 600 | 0 |  | ['728: FS', '498: FS'] | ['422: FS', '419: FS', '423: FS']
462 | Not Started | MDC1-BL.5.2.2.6.2 | Task Dependent | Equipment Yellow Tagging | 2021-03-19 08:00 | 2021-04-01 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C3320: FF, MDC1.C2.C3360: FS, MDC1.C2.C3330: FS, MDC1.C2.C3370: FS, MDC1.C2.C3300: FS, MDC1.C2.C3440: FS, MDC1.C2.C3380: FS, MDC1.C2.C3450: FS, MDC1.C2.C3150: FS, MDC1.C2.Cx2010: FS, MDC1-C2.P1800: FS | MDC1.C2.Cx2100: FS, MDC1.C2.Cx2170: FS | VECA Electricians | 1200 | 0 |  | ['685: FF', '625: FS', '672: FS', '616: FS', '708: FS', '535: FS', '613: FS', '499: FS', '948: FS', '498: FS', '594: FS'] | ['423: FS', '387: FS']
463 | Not Started | MDC1-BL.5.2.2.6.3 | Task Dependent | Network Startup | 2021-03-19 07:00 | 2021-03-31 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C2350: FS, MDC1.C2.Cx2000: FS | MDC1.C2.Cx2060: FS, MDC1.C2.Cx2120: FS, MDC1.C2.Cx2070: FS | LINX- TELECOM | 600 | 0 |  | ['730: FS', '500: FS'] | ['425: FS', '421: FS', '426: FS']
464 | Not Started | MDC1-BL.5.2.2.6.4 | Task Dependent | Equipment Yellow Tagging | 2021-03-19 07:00 | 2021-03-31 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C4270: FF, MDC1.C2.C4320: FS, MDC1.C2.C4290: FS, MDC1.C2.C4330: FS 5, MDC1.C2.C4370: FS, MDC1.C2.C4390: FS, MDC1.C2.C4400: FS, MDC1.C2.C4260: FS 5, MDC1.C2.C4380: FS, MDC1.C2.Cx2000: FS, MDC1-C2.P1800: FS, MDC1.C2.C4040: FS, MDC1.C2.C4050: FS, MDC1-2527: FS, MDC1.C2.C4120: FS | MDC1.C2.Cx2070: FS, MDC1.C2.Cx2150: FS | VECA Electricians | 1200 | 0 |  | ['686: FF', '626: FS', '674: FS', '617: FS 5', '577: FS', '501: FS', '502: FS', '711: FS 5', '556: FS', '500: FS', '594: FS', '1125: FS', '1096: FS', '1325: FS', '951: FS'] | ['426: FS', '392: FS']
465 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Lift & Set MER in Place | 2021-03-26 07:00 | 2021-03-31 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 1 | 1 |  |  |  |  | MDC1.C4.E1380: FS, MDC1.C4.E1220: FS, MDC1.C4.C3060: FS | MDC1.C4.C3260: FS, MDC1.C4.C3270: FS, MDC1.C4.C4250: FS | VECA Electricians | 120 | 0 |  | ['54: FS', '762: FS', '790: FS'] | ['447: FS', '432: FS', '441: FS']
466 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-03-16 07:00 | 2021-03-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 3 | 3 |  |  |  |  | MDC1.C3.C3280: FS, MDC1.C3.C3080: FS, MDC1.C3.C3230: FS, MDC1.C3.C1380: FS | MDC1.C3.Cx2030: FS, MDC1.C3.C3380: FS | VECA Electricians | 960 | 0 |  | ['526: FS', '874: FS', '591: FS', '514: FS'] | ['352: FS', '395: FS']
467 | Not Started | MDC1-BL.5.3.8.4.10.1 | Task Dependent | PDU's Installation | 2021-03-27 07:00 | 2021-03-30 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 2 | 2 |  |  |  |  | MDC1.C3.C3310: FS, MDC1.C3.E1420: FS, MDC1.C3.E1430: FS | MDC1.C3.C3390: FS, MDC1.C3.C3410: FS | VECA Electricians | 180 | 0 |  | ['481: FS', '203: FS', '204: FS'] | ['390: FS', '361: FS']
468 | Not Started | MDC1-BL.5.3.8.4.13.1 | Task Dependent | PDU's Installation | 2021-03-27 07:00 | 2021-03-30 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 2 | 2 |  |  |  |  | MDC1.C3.C4340: FS, MDC1.C3.E1440: FS, MDC1.C3.E1450: FS | MDC1.C3.C4420: FS, MDC1.C3.C4450: FS | VECA Electricians | 180 | 0 |  | ['482: FS', '207: FS', '208: FS'] | ['391: FS', '362: FS']
469 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-03-18 07:00 | 2021-03-30 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.C4.C1230: FS | MDC1.C4.C1320: FS |  | 0 | 0 |  | ['511: FS'] | ['437: FS']
470 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-03-26 07:00 | 2021-03-30 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 3 | 3 |  |  |  |  | MDC1.C4.C2060: FS, MDC1.C4.C2270: FS | MDC1.C4.C2330: FS, MDC1.C4.C2380: FS, MDC1.C4.C2360: FS, MDC1.C4.C4260: FS | SURE STEEL | 160 | 0 |  | ['878: FS', '483: FS'] | ['414: FS', '368: FS', '396: FS', '434: FS']
471 | Not Started | MDC1-BL.5.3.8.4.9.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-03-15 07:00 | 2021-03-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C1370: FS | MDC1.C3.C1460: FS, MDC1.C3.Cx2020: FS, MDC1.C3.Cx2000: FS, MDC1.C3.C1440: FS | LINX- TELECOM | 1440 | 0 |  | ['520: FS'] | ['397: FS', '357: FS', '389: FS', '427: FS']
472 | Not Started | MDC1-BL.5.3.8.4.10.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-03-15 07:00 | 2021-03-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C3270: FS | MDC1.C3.C3360: FS | LINX- TELECOM | 1440 | 0 |  | ['521: FS'] | ['428: FS']
473 | Not Started | MDC1-BL.5.3.8.4.11.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-03-15 07:00 | 2021-03-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C2360: FS | MDC1.C3.C2460: FS, MDC1.C3.Cx2040: FS, MDC1.C3.Cx2010: FS, MDC1.C3.C2430: FS | LINX- TELECOM | 1440 | 0 |  | ['522: FS'] | ['398: FS', '353: FS', '380: FS', '429: FS']
474 | Not Started | MDC1-BL.5.3.8.4.13.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-03-15 07:00 | 2021-03-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C4310: FS | MDC1.C3.C4390: FS | LINX- TELECOM | 1440 | 0 |  | ['523: FS'] | ['430: FS']
475 | Not Started | MDC1-BL.5.3.9.4.13.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-03-05 07:00 | 2021-03-29 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C2.C2450: FS, MDC1.C2.C4290: FS | MDC1.C2.Cx4010: FS, MDC1.C3.C2460: FS | LINX- TELECOM | 1440 | 0 |  | ['558: FS', '674: FS'] | ['263: FS', '398: FS']
476 | Not Started | MDC1-BL.5.3.8.4.1.4 | Task Dependent | Controls Installation | 2021-03-13 07:00 | 2021-03-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 15 | 15 |  |  |  |  | MDC1.C3.C1110: FS, MDC1.C3.C1160: FS, MDC1.C3.C1200: FS, MDC1.C3.C1360: FS | MDC1.C3.Cx2000: FS, MDC1-C3.P1800: FS | VECA Electricians | 720 | 0 |  | ['972: FS', '888: FS', '768: FS', '527: FS'] | ['389: FS', '32: FS']
477 | Not Started | MDC1-BL.5.3.8.4.3.4 | Task Dependent | Controls Installation | 2021-03-13 07:00 | 2021-03-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 15 | 15 |  |  |  |  | MDC1.C3.C2110: FS, MDC1.C3.C2160: FS, MDC1.C3.C2190: FS, MDC1.C3.C2330: FS, MDC1.C3.C2350: FS | MDC1.C3.Cx2010: FS | VECA Electricians | 720 | 0 |  | ['974: FS', '889: FS', '799: FS', '543: FS', '528: FS'] | ['380: FS']
478 | Not Started | MDC1-BL.5.3.6.4.6.2 | Task Dependent | Hydronic Piping Installation | 2021-03-13 07:00 | 2021-03-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 69 | 69 |  |  |  |  | MDC1.C4.C3170: FS | MDC1.C4.Cx2030: FF | TCM | 480 | 0 |  | ['531: FS'] | ['287: FF']
479 | Not Started | MDC1-BL.5.3.6.4.8.2 | Task Dependent | Hydronic Piping Installation | 2021-03-13 07:00 | 2021-03-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 69 | 69 |  |  |  |  | MDC1.C4.C4170: FS | MDC1.C4.Cx2050: FF | TCM | 480 | 0 |  | ['534: FS'] | ['285: FF']
480 | Not Started | MDC1-BL.5.3.8.4.13.3 | Task Dependent | Fire Alarm System | 2021-03-15 07:00 | 2021-03-26 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C3.C4310: FS | MDC1.C3.C4440: FS | VECA Electricians | 600 | 0 |  | ['523: FS'] | ['382: FS']
481 | Not Started | MDC1-BL.5.3.8.4.10.1 | Task Dependent | Power Bus Installation | 2021-03-15 07:00 | 2021-03-26 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C3.C3270: FS | MDC1.C3.C3340: FS, MDC1.C3.E1420: FS | VECA Electricians | 1200 | 0 |  | ['521: FS'] | ['467: FS', '203: FS']
482 | Not Started | MDC1-BL.5.3.8.4.13.1 | Task Dependent | Power Bus Installation | 2021-03-15 07:00 | 2021-03-26 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C3.C4310: FS | MDC1.C3.C4360: FS, MDC1.C3.E1440: FS | VECA Electricians | 1200 | 0 |  | ['523: FS'] | ['468: FS', '207: FS']
483 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Lift & Set MER in Place | 2021-03-19 07:00 | 2021-03-25 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C4.E1370: FS, MDC1.C4.E1130: FS, MDC1.C4.C2060: FS, MDC1.C4.C1230: FS | MDC1.C4.C2280: FS, MDC1.C4.C2300: FS | VECA Electricians | 120 | 0 |  | ['55: FS', '848: FS', '878: FS', '511: FS'] | ['470: FS', '444: FS']
484 | Not Started | MDC1-BL.5.3.9.4.10.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-03-01 07:00 | 2021-03-24 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 61 | 61 |  |  |  |  | MDC1.C2.C1440: FS, MDC1.C2.C3330: FS | MDC1.C2.Cx4010: FS, MDC1.C3.C1460: FS | LINX- TELECOM | 1440 | 0 |  | ['571: FS', '672: FS'] | ['263: FS', '397: FS']
485 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-03-09 07:00 | 2021-03-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C2110: FS, MDC1.C3.C2290: FS, MDC1.C3.C2330: FS | MDC1.C3.Cx2010: FS, MDC1.C3.C2440: FS | VECA Electricians | 960 | 0 |  | ['974: FS', '615: FS', '543: FS'] | ['380: FS', '420: FS']
486 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-03-18 07:00 | 2021-03-23 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 9 | 9 |  |  |  |  | MDC1.C4.C1060: FS, MDC1.C4.C1230: FS | MDC1.C4.C1320: FS, MDC1.C4.C1380: FS, MDC1.C4.C1340: FS, MDC1.C4.C3260: FS | SURE STEEL | 160 | 0 |  | ['876: FS', '511: FS'] | ['437: FS', '385: FS', '418: FS', '447: FS']
487 | Not Started | MDC1-BL.5.3.8.4.10.3 | Task Dependent | Fire Alarm System | 2021-03-10 07:00 | 2021-03-22 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 18 | 18 |  |  |  |  | MDC1.C3.C3270: FF 6 | MDC1.C3.C3400: FS | VECA Electricians | 600 | 0 |  | ['521: FF 6'] | ['379: FS']
488 | Not Started | MDC1-BL.5.3.6.3.1.2 | Task Dependent | Datahall Finishes | 2021-03-08 07:00 | 2021-03-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 110 | 110 |  |  |  |  | MDC1.C4.C1220: FS | MDC1-C3.P1900: FS, MDC1-C4.P1900: FS | PCI | 480 | 0 |  | ['548: FS'] | ['367: FS', '292: FS']
489 | Not Started | MDC1-BL.5.3.6.3.3.2 | Task Dependent | Datahall Finishes | 2021-03-08 07:00 | 2021-03-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 143 | 143 |  |  |  |  | MDC1.C4.C2220: FS | MDC1-C4.P1900: FS | PCI | 480 | 0 |  | ['549: FS'] | ['292: FS']
490 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-03-10 07:00 | 2021-03-22 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C3.C4290: FS, MDC1.C3.C4300: FS, MDC1.C3.C2330: FS | MDC1.C3.C4370: FS | VECA Electricians | 560 | 0 |  | ['563: FS', '539: FS', '543: FS'] | ['445: FS']
491 | Not Started | MDC1-BL.5.3.6.4.9.1 | Task Dependent | HAC Installation | 2021-03-08 07:00 | 2021-03-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C1220: FS | MDC1.C4.C1310: FS | TCM | 480 | 0 |  | ['548: FS'] | ['446: FS']
492 | Not Started | MDC1-BL.5.3.6.4.11.1 | Task Dependent | HAC Installation | 2021-03-08 07:00 | 2021-03-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C2220: FS | MDC1.C4.C2290: FS, MDC1.C4.C2320: FS | TCM | 480 | 0 |  | ['549: FS'] | ['448: FS', '417: FS']
493 | Not Started | MDC1-BL.5.2.3.6.4 | Task Dependent | EPMS Checkout / Point to Point | 2021-03-09 07:00 | 2021-03-19 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 10 | 10 |  |  |  |  | MDC1.C1.Cx2100: FS, MDC1.C1.Cx2090: FS | MDC1.C1.Cx3030: FS | LINX- TELECOM | 1200 | 0 |  | ['542: FS', '541: FS'] | ['394: FS']
494 | Not Started | MDC1-BL.5.3.6.4.5.3 | Task Dependent | Floor Drain System Installation | 2021-03-06 07:00 | 2021-03-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 144 | 144 |  |  |  |  | MDC1.C4.C1010: FS, MDC1.C4.C1200: FS | MDC1-C4.P1900: FS |  | 0 | 0 |  | ['990: FS', '551: FS'] | ['292: FS']
495 | Not Started | MDC1-BL.5.3.6.4.5.3 | Task Dependent | Toilet Piping Installation / DW | 2021-03-06 07:00 | 2021-03-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 144 | 144 |  |  |  |  | MDC1.C4.C1200: FS | MDC1-C4.P1900: FS | TCM | 480 | 0 |  | ['551: FS'] | ['292: FS']
496 | Not Started | MDC1-BL.5.3.6.4.7.3 | Task Dependent | Floor Drain System Installation | 2021-03-06 07:00 | 2021-03-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 144 | 144 |  |  |  |  | MDC1.C4.C2010: FS, MDC1.C4.C2200: FS | MDC1-C4.P1900: FS |  | 0 | 0 |  | ['991: FS', '553: FS'] | ['292: FS']
497 | Not Started | MDC1-BL.5.3.6.4.7.3 | Task Dependent | Toilet Piping Installation / DW | 2021-03-06 07:00 | 2021-03-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 144 | 144 |  |  |  |  | MDC1.C4.C2200: FS | MDC1-C4.P1900: FS | TCM | 480 | 0 |  | ['553: FS'] | ['292: FS']
498 | Not Started | MDC1-BL.5.2.2.6.1 | Task Dependent | Equipment Yellow Tagging | 2021-03-08 08:00 | 2021-03-19 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C1320: FS, MDC1.C2.C1260: FF, MDC1.C2.C1390: FS, MDC1.C2.C1340: FS, MDC1.C2.C1400: FS, MDC1.C2.C1410: FS, MDC1.C2.C1460: FS, MDC1-1996: FS, MDC1-1993: FS, MDC1-2004: FS, MDC1.C2.C1130: FS, MDC1.C2.C1450: FS, MDC1-C2.P1800: FS | MDC1.C2.Cx2040: FS, MDC1.C2.Cx2110: FS, MDC1.C2.Cx2050: FS | VECA Electricians | 1200 | 0 |  | ['784: FS', '836: FF', '678: FS', '728: FS', '671: FS', '660: FS', '544: FS', '1134: FS', '1310: FS', '1193: FS', '1041: FS', '568: FS', '594: FS'] | ['461: FS', '424: FS', '462: FS']
499 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Pull Conductors into Building | 2021-02-25 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C2.C3080: FS, MDC1.C2.C3380: FS, MDC1.C2.C3430: FS | MDC1.C2.Cx2050: FS | VECA Electricians | 1440 | 0 |  | ['1052: FS', '613: FS', '576: FS'] | ['462: FS']
500 | Not Started | MDC1-BL.5.2.2.6.3 | Task Dependent | Equipment Yellow Tagging | 2021-03-08 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C2250: FF, MDC1.C2.C2380: FS, MDC1.C2.C2350: FS, MDC1.C2.C2390: FS, MDC1.C2.C2430: FS, MDC1.C2.C2320: FS, MDC1.C2.C2420: FS, MDC1.C2.C2460: FS, MDC1.C2.C2180: FS, MDC1-C2.P1800: FS | MDC1.C2.Cx2020: FS, MDC1.C2.Cx2080: FS, MDC1.C2.Cx2030: FS | VECA Electricians | 1200 | 0 |  | ['839: FF', '679: FS', '730: FS', '673: FS', '590: FS', '787: FS', '636: FS', '545: FS', '949: FS', '594: FS'] | ['463: FS', '435: FS', '464: FS']
501 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Pull Conductors into Building | 2021-02-25 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C2.C4060: FS, MDC1.C2.C4370: FS | MDC1.C2.Cx2030: FS | VECA Electricians | 1440 | 0 |  | ['1053: FS', '577: FS'] | ['464: FS']
502 | Not Started | MDC1-BL.5.3.9.4.4.4 | Task Dependent | Controls Installation | 2021-03-05 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C4060: FS, MDC1.C2.C4100: FS, MDC1.C2.C4380: FS, MDC1.C2.C4040: FS, MDC1.C2.C4050: FS, MDC1-2527: FS | MDC1.C2.Cx2030: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0 |  | ['1053: FS', '971: FS', '556: FS', '1125: FS', '1096: FS', '1325: FS'] | ['464: FS', '31: FS']
503 | Not Started | MDC1-BL.5.3.9.4.8.1 | Task Dependent | Ligthing Installation | 2021-03-05 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C2.C2440: FS, MDC1.C2.C4120: FS, MDC1.C2.C4300: FS | MDC1.C3.C2410: FS | VECA Electricians | 480 | 0 |  | ['555: FS', '951: FS', '664: FS'] | ['454: FS']
504 | Not Started | MDC1-BL.5.3.8.4.6.1 | Task Dependent | Ligthing Installation | 2021-03-05 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 112 | 112 |  |  |  |  | MDC1.C3.C1330: FS, MDC1.C3.C3130: FS, MDC1.C3.C3160: FS | MDC1.C4.C1300: FS, MDC1-C3.P1900: FS | VECA Electricians | 480 | 0 |  | ['557: FS', '740: FS', '655: FS'] | ['455: FS', '367: FS']
505 | Not Started | MDC1-BL.5.3.6.3.2.1 | Task Dependent | Hang Wall Partitions | 2021-03-10 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 6 | 6 |  |  |  |  | MDC1.C4.CS1090: FS, MDC1.C4.C3180: SS 6 | MDC1.C4.C3220: FS, MDC1.C4.C3230: FS | PCI | 600 | 0 |  | ['1062: FS', '524: SS 6'] | ['456: FS', '458: FS']
506 | Not Started | MDC1-BL.5.3.6.3.4.1 | Task Dependent | Hang Wall Partitions | 2021-03-10 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 6 | 6 |  |  |  |  | MDC1.C4.CS1090: FS, MDC1.C4.C4180: SS 6 | MDC1.C4.C4210: FS, MDC1.C4.C4220: FS | PCI | 600 | 0 |  | ['1062: FS', '525: SS 6'] | ['457: FS', '459: FS']
507 | Not Started | MDC1-BL.5.2.3.7 | Task Dependent | Hydronic Pipe Flush (Open and closed Loop) | 2021-03-04 08:00 | 2021-03-18 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2120: SS 10, MDC1.C1.Cx2130: SS 10, MDC1.C1.Cx2160: SS 10, MDC1.C1.Cx2140: SS 10 | MDC1.C1.Cx3010: FS, MDC1.C2.Cx3000: FS | TCM | 1200 | 0 |  | ['517: SS 10', '518: SS 10', '513: SS 10', '519: SS 10'] | ['460: FS', '376: FS']
508 | Not Started | MDC1-BL.5.2.3.6.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-03-04 08:00 | 2021-03-18 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2070: FS | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3020: FS, MDC1-C1.P2000: FS | TCM | 640 | 0 |  | ['560: FS'] | ['460: FS', '436: FS', '509: FS']
509 | Not Started | MDC1-BL.3.2 | Finish Milestone | Construction Server- COLO-1 |  | 2021-03-18 08:00 |  |  | 2021-03-18 08:00 |  | 0 | 0 | 0 | 0 | 12 | 12 |  |  |  |  | MDC1.C1.Cx2170: FS, MDC1.C1.Cx2110: FS, MDC1.C1.Cx2180: FS, MDC1.C1.Cx2080: FS | MDC1.C1.Cx3020: FS |  | 0 | 0 |  | ['510: FS', '538: FS', '508: FS', '550: FS'] | ['436: FS']
510 | Not Started | MDC1-BL.5.2.3.6.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-03-04 07:00 | 2021-03-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2100: SS 6 | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3020: FS, MDC1-C1.P2000: FS | TCM | 640 | 0 |  | ['542: SS 6'] | ['460: FS', '436: FS', '509: FS']
511 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Lift & Set MER in Place | 2021-03-12 07:00 | 2021-03-17 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 1 | 1 |  |  |  |  | MDC1.C4.E1360: FS, MDC1.C4.E1120: FS, MDC1.C4.C1060: FS, MDC1-C4.P1600: FS, MDC1.C3.C4270: FS | MDC1.C4.C1280: FS, MDC1.C4.C1290: FS, MDC1.C4.C2270: FS | VECA Electricians | 120 | 0 |  | ['53: FS', '847: FS', '876: FS', '40: FS', '582: FS'] | ['486: FS', '469: FS', '483: FS']
512 | Not Started | MDC1-BL.5.2.3.6.2 | Task Dependent | EPMS Checkout / Point to Point | 2021-03-04 08:00 | 2021-03-16 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C1.Cx2070: FS, MDC1.C1.Cx2060: FS, MDC1.C1.Cx2060: FF | MDC1.C1.Cx3030: FS, MDC1.M1010: FS, MDC1.C1.Cx3050: FS | LINX- TELECOM | 1200 | 0 |  | ['560: FS', '559: FS', '559: FF'] | ['394: FS', '344: FS', '346: FS']
513 | Not Started | MDC1-BL.5.2.3.6.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-02-19 08:00 | 2021-03-16 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2030: FS, MDC1.S.1840: FS, MDC1.S.1850: FS | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3000: SS 10 | VECA Electricians | 2000 | 0 |  | ['596: FS', '611: FS', '601: FS'] | ['460: FS', '507: SS 10']
514 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-03-02 07:00 | 2021-03-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 3 | 3 |  |  |  |  | MDC1.C3.C1320: FS, MDC1.C3.C1110: FS, MDC1.C3.C1240: FS | MDC1.C3.Cx2000: FS, MDC1.C3.C1420: FS, MDC1.C3.C3330: FS | VECA Electricians | 960 | 0 |  | ['567: FS', '972: FS', '641: FS'] | ['389: FS', '440: FS', '466: FS']
515 | Not Started | MDC1-BL.5.3.8.4.9.1 | Task Dependent | PDU's Installation | 2021-03-12 07:00 | 2021-03-15 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 4 | 4 |  |  |  |  | MDC1.C3.C1350: FS, MDC1.C3.E1380: FS, MDC1.C3.E1390: FS | MDC1.C3.C1430: FS, MDC1.C3.C1450: FS | VECA Electricians | 180 | 0 |  | ['536: FS', '201: FS', '202: FS'] | ['438: FS', '403: FS']
516 | Not Started | MDC1-BL.5.3.8.4.11.1 | Task Dependent | PDU's Installation | 2021-03-12 07:00 | 2021-03-15 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 4 | 4 |  |  |  |  | MDC1.C3.C2340: FS, MDC1.C3.E1400: FS, MDC1.C3.E1410: FS | MDC1.C3.C2420: FS, MDC1.C3.C2450: FS | VECA Electricians | 180 | 0 |  | ['537: FS', '205: FS', '206: FS'] | ['439: FS', '404: FS']
517 | Not Started | MDC1-BL.5.2.3.6.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-02-19 07:00 | 2021-03-15 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2050: SS 6, MDC1.S.1840: FS, MDC1.S.1850: FS | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3000: SS 10 | VECA Electricians | 2000 | 0 |  | ['587: SS 6', '611: FS', '601: FS'] | ['460: FS', '507: SS 10']
518 | Not Started | MDC1-BL.5.2.3.6.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-02-19 07:00 | 2021-03-15 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2010: FS, MDC1.S.1840: FS, MDC1.S.1850: FS | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3000: SS 10 | VECA Electricians | 2000 | 0 |  | ['623: FS', '611: FS', '601: FS'] | ['460: FS', '507: SS 10']
519 | Not Started | MDC1-BL.5.2.3.6.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-02-19 07:00 | 2021-03-15 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2000: FS, MDC1.S.1840: FS, MDC1.S.1850: FS | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3000: SS 10 | VECA Electricians | 2000 | 0 |  | ['645: FS', '611: FS', '601: FS'] | ['460: FS', '507: SS 10']
520 | Not Started | MDC1-BL.5.3.8.4.9.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-03-01 07:00 | 2021-03-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C1310: FS | MDC1.C3.C1410: FS | LINX- TELECOM | 1440 | 0 |  | ['569: FS'] | ['471: FS']
521 | Not Started | MDC1-BL.5.3.8.4.10.1 | Task Dependent | Cable Tray Installation | 2021-03-01 07:00 | 2021-03-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C1310: FS, MDC1.C3.C3250: FS | MDC1.C4.C1310: FS, MDC1.C3.C3320: FS, MDC1.C3.C3310: FS, MDC1.C3.C3400: FS, MDC1.C3.C3300: FF 6 | VECA Electricians | 1440 | 0 |  | ['569: FS', '583: FS'] | ['446: FS', '472: FS', '481: FS', '379: FS', '487: FF 6']
522 | Not Started | MDC1-BL.5.3.8.4.11.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-03-01 07:00 | 2021-03-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C2310: FS, MDC1.C3.C2320: FF 6 | MDC1.C3.C2400: FS | LINX- TELECOM | 1440 | 0 |  | ['570: FS', '547: FF 6'] | ['473: FS']
523 | Not Started | MDC1-BL.5.3.8.4.13.1 | Task Dependent | Cable Tray Installation | 2021-03-01 07:00 | 2021-03-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C2310: FS, MDC1.C3.C4280: FS | MDC1.C3.C4350: FS, MDC1.C4.C2290: FS, MDC1.C3.C4340: FS, MDC1.C3.C4440: FS, MDC1.C3.C4330: FS | VECA Electricians | 1440 | 0 |  | ['570: FS', '584: FS'] | ['474: FS', '448: FS', '482: FS', '382: FS', '480: FS']
524 | Not Started | MDC1-BL.5.3.6.3.2.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-03-03 07:00 | 2021-03-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 6 | 6 |  |  |  |  | MDC1.C4.C1190: FS, MDC1.C4.C3130: FS | MDC1.C4.C3190: SS 6 | VECA Electricians | 1200 | 0 |  | ['564: FS', '608: FS'] | ['505: SS 6']
525 | Not Started | MDC1-BL.5.3.6.3.4.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-03-03 07:00 | 2021-03-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 6 | 6 |  |  |  |  | MDC1.C4.C2190: FS, MDC1.C4.C4130: FS | MDC1.C4.C4190: SS 6 | VECA Electricians | 1200 | 0 |  | ['565: FS', '609: FS'] | ['506: SS 6']
526 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-03-03 07:00 | 2021-03-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C3.C3230: FS, MDC1.C3.C3260: FS, MDC1.C3.C1320: FS | MDC1.C3.C3330: FS | VECA Electricians | 560 | 0 |  | ['591: FS', '562: FS', '567: FS'] | ['466: FS']
527 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-02-17 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 5 | 5 |  |  |  |  | MDC1.C3.C1160: FS, MDC1.C3.C1110: FS, MDC1.C3.C1240: FS, MDC1.C3.C1280: FS | MDC1.C3.C1400: FS, MDC1.C3.C3350: FS, MDC1.C3.C1420: FS | VECA Electricians | 1080 | 0 |  | ['888: FS', '972: FS', '641: FS', '614: FS'] | ['476: FS', '442: FS', '440: FS']
528 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-02-17 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 5 | 5 |  |  |  |  | MDC1.C3.C2160: FS, MDC1.C3.C2110: FS, MDC1.C3.C2290: FS | MDC1.C3.C2390: FS, MDC1.C3.C4380: FS | VECA Electricians | 1080 | 0 |  | ['889: FS', '974: FS', '615: FS'] | ['477: FS', '443: FS']
529 | Not Started | MDC1-BL.5.3.6.3.6.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2021-02-26 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 120 | 120 |  |  |  |  | MDC1.C4.C3140: FS | MDC1.C4.C3240: FS | VECA Electricians | 960 | 0 |  | ['573: FS'] | ['449: FS']
530 | Not Started | MDC1-BL.5.3.6.4.6.1 | Task Dependent | VFD'S Installation & Wiring | 2021-02-26 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C4.C3140: FS | MDC1.C4.C3280: FS, MDC1.C4.C3250: FS, MDC1.C4.Cx3020: FS | VECA Electricians | 240 | 0 |  | ['573: FS'] | ['410: FS', '450: FS', '244: FS']
531 | Not Started | MDC1-BL.5.3.6.4.6.2 | Task Dependent | AHU/DOAS Equipment Setting | 2021-02-26 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 69 | 69 |  |  |  |  | MDC1.C4.C3140: FS, MDC1.C4.E1320: FS, MDC1.C4.E1340: FS | MDC1.C4.C3200: FS | TCM | 480 | 0 |  | ['573: FS', '74: FS', '90: FS'] | ['478: FS']
532 | Not Started | MDC1-BL.5.3.6.3.8.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2021-02-26 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 108 | 108 |  |  |  |  | MDC1.C4.C4140: FS | MDC1.C4.C4230: FS | VECA Electricians | 960 | 0 |  | ['575: FS'] | ['451: FS']
533 | Not Started | MDC1-BL.5.3.6.4.8.1 | Task Dependent | VFD'S Installation & Wiring | 2021-02-26 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C4.C4140: FS | MDC1.C4.C4380: FS, MDC1.C4.C4240: FS, MDC1.C4.Cx3020: FS | VECA Electricians | 240 | 0 |  | ['575: FS'] | ['340: FS', '452: FS', '244: FS']
534 | Not Started | MDC1-BL.5.3.6.4.8.2 | Task Dependent | AHU/DOAS Equipment Setting | 2021-02-26 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 69 | 69 |  |  |  |  | MDC1.C4.C4140: FS, MDC1.C4.E1330: FS, MDC1.C4.E1350: FS | MDC1.C4.C4200: FS | TCM | 480 | 0 |  | ['575: FS', '76: FS', '92: FS'] | ['479: FS']
535 | Not Started | MDC1-BL.5.3.9.4.2.4 | Task Dependent | Controls Installation | 2021-02-25 07:00 | 2021-03-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C2.C3080: FS, MDC1.C2.C3120: FS, MDC1.C2.C3180: FS, MDC1.C2.C3430: FS | MDC1.C2.Cx2050: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0 |  | ['1052: FS', '986: FS', '886: FS', '576: FS'] | ['462: FS', '31: FS']
536 | Not Started | MDC1-BL.5.3.8.4.9.1 | Task Dependent | Power Bus Installation | 2021-03-01 07:00 | 2021-03-11 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C3.C1310: FS | MDC1.C3.C1390: FS, MDC1.C3.E1380: FS | VECA Electricians | 1200 | 0 |  | ['569: FS'] | ['515: FS', '201: FS']
537 | Not Started | MDC1-BL.5.3.8.4.11.1 | Task Dependent | Power Bus Installation | 2021-03-01 07:00 | 2021-03-11 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C3.C2310: FS | MDC1.C3.C2370: FS, MDC1.C3.E1400: FS | VECA Electricians | 1200 | 0 |  | ['570: FS'] | ['516: FS', '205: FS']
538 | Not Started | MDC1-BL.5.2.3.6.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-02-24 07:00 | 2021-03-10 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C1.Cx2040: FS | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3020: FS, MDC1-C1.P2000: FS | TCM | 640 | 0 |  | ['586: FS'] | ['460: FS', '436: FS', '509: FS']
539 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-02-25 07:00 | 2021-03-09 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C3.C4270: FS | MDC1.C3.C4320: FS, MDC1.C3.C4380: FS |  | 0 | 0 |  | ['582: FS'] | ['490: FS', '443: FS']
540 | Not Started | MDC1-BL.5.2.5.1 | Task Dependent | EPMS Checkout / Point to Point | 2021-02-24 07:00 | 2021-03-08 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 20 | 20 |  |  |  |  | MDC1.AD.Cx2010: FS | MDC1.M1010: FS, MDC1.C1.Cx3030: FS, MDC1.C1.Cx3050: FS | LINX- TELECOM | 1200 | 0 |  | ['585: FS'] | ['344: FS', '394: FS', '346: FS']
541 | Not Started | MDC1-BL.5.2.3.6.3 | Task Dependent | EPMS Checkout / Point to Point | 2021-02-24 07:00 | 2021-03-08 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 10 | 10 |  |  |  |  | MDC1.C1.Cx2040: FS | MDC1.C1.Cx3030: FS, MDC1.M1010: FS, MDC1.C1.Cx3050: FS, MDC1.C1.Cx2190: FS | LINX- TELECOM | 1200 | 0 |  | ['586: FS'] | ['394: FS', '344: FS', '346: FS', '493: FS']
542 | Not Started | MDC1-BL.5.2.3.6.4 | Task Dependent | Network Startup | 2021-02-24 07:00 | 2021-03-08 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C4380: FS, MDC1.C1.Cx2050: FS, MDC1.C1.Cx2040: FS | MDC1.C1.Cx2190: FS, MDC1.C1.Cx2170: SS 6 | LINX- TELECOM | 600 | 0 |  | ['750: FS', '587: FS', '586: FS'] | ['493: FS', '510: SS 6']
543 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-02-24 07:00 | 2021-03-08 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C3.C2290: FS, MDC1.C3.C2300: FS, MDC1.C3.C2300: FF | MDC1.C3.C2390: FS, MDC1.C3.C2380: FS, MDC1.C3.C4320: FS | VECA Electricians | 560 | 0 |  | ['615: FS', '588: FS', '588: FF'] | ['477: FS', '485: FS', '490: FS']
544 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Pull Conductors into Building | 2021-02-13 08:00 | 2021-03-08 08:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C2.C1080: FS, MDC1.C2.C1410: FS, MDC1.C2.C1430: FS | MDC1.C2.Cx2010: FS | VECA Electricians | 1440 | 0 |  | ['1122: FS', '660: FS', '618: FS'] | ['498: FS']
545 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Pull Conductors into Building | 2021-02-11 07:00 | 2021-03-06 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C2.C2060: FS, MDC1.C2.C2420: FS | MDC1.C2.Cx2000: FS | VECA Electricians | 1440 | 0 |  | ['1124: FS', '636: FS'] | ['500: FS']
546 | Not Started | MDC1-BL.5.3.8.4.9.3 | Task Dependent | Fire Alarm System | 2021-02-23 07:00 | 2021-03-06 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 20 | 20 |  |  |  |  | MDC1.C3.C1310: FF 6 | MDC1.C3.C1440: FS, MDC1-C3.P1800: FS | VECA Electricians | 600 | 0 |  | ['569: FF 6'] | ['427: FS', '32: FS']
547 | Not Started | MDC1-BL.5.3.8.4.11.3 | Task Dependent | Fire Alarm System | 2021-02-23 07:00 | 2021-03-06 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C3.C2310: FF 6 | MDC1.C3.C2360: FF 6, MDC1.C3.C2430: FS | VECA Electricians | 600 | 0 |  | ['570: FF 6'] | ['522: FF 6', '429: FS']
548 | Not Started | MDC1-BL.5.3.6.3.1.1 | Task Dependent | Hang Wall Partitions | 2021-02-25 07:00 | 2021-03-06 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 4 | 4 |  |  |  |  | MDC1.C4.CS1090: FS, MDC1.C4.C1190: SS 6 | MDC1.C4.C1260: FS, MDC1.C4.C1270: FS | PCI | 600 | 0 |  | ['1062: FS', '564: SS 6'] | ['488: FS', '491: FS']
549 | Not Started | MDC1-BL.5.3.6.3.3.1 | Task Dependent | Hang Wall Partitions | 2021-02-25 07:00 | 2021-03-06 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 4 | 4 |  |  |  |  | MDC1.C4.CS1090: FS, MDC1.C4.C2190: SS 6 | MDC1.C4.C2250: FS, MDC1.C4.C2260: FS | PCI | 600 | 0 |  | ['1062: FS', '565: SS 6'] | ['489: FS', '492: FS']
550 | Not Started | MDC1-BL.5.2.3.6.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-02-19 08:00 | 2021-03-06 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 10 | 10 |  |  |  |  | MDC1.C1.Cx2020: FS, MDC1.S.1840: FS | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3020: FS, MDC1-C1.P2000: FS | TCM | 640 | 0 |  | ['595: FS', '611: FS'] | ['460: FS', '436: FS', '509: FS']
551 | Not Started | MDC1-BL.5.3.6.3.5.2 | Task Dependent | Mechanical Corridor Finishes | 2021-02-12 07:00 | 2021-03-05 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 132 | 132 |  |  |  |  | MDC1.C4.C1150: FS, MDC1.C4.C1010: FS | MDC1.C4.C1300: FS, MDC1.C4.C1250: FS, MDC1-C4.P1900: FS, MDC1.C4.C1240: FS | PCI | 180 | 0 |  | ['628: FS', '990: FS'] | ['455: FS', '495: FS', '292: FS', '494: FS']
552 | Not Started | MDC1-BL.5.3.6.4.5.4 | Task Dependent | Controls Installation | 2021-02-12 07:00 | 2021-03-05 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 67 | 67 |  |  |  |  | MDC1.C4.C1160: FS, MDC1.C4.C1090: FS | MDC1.C4.Cx2000: FS, MDC1-C4.P1800: FS | VECA Electricians | 720 | 0 |  | ['629: FS', '802: FS'] | ['312: FS', '33: FS']
553 | Not Started | MDC1-BL.5.3.6.3.7.2 | Task Dependent | Mechanical Corridor Finishes | 2021-02-12 07:00 | 2021-03-05 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 132 | 132 |  |  |  |  | MDC1.C4.C2150: FS, MDC1.C4.C2010: FS | MDC1.C4.C2370: FS, MDC1.C4.C2240: FS, MDC1.C4.C2230: FS | PCI | 180 | 0 |  | ['632: FS', '991: FS'] | ['370: FS', '497: FS', '496: FS']
554 | Not Started | MDC1-BL.5.3.6.4.7.4 | Task Dependent | Controls Installation | 2021-02-12 07:00 | 2021-03-05 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 67 | 67 |  |  |  |  | MDC1.C4.C2160: FS, MDC1.C4.C2090: FS | MDC1.C4.Cx2010: FS | VECA Electricians | 720 | 0 |  | ['633: FS', '805: FS'] | ['298: FS']
555 | Not Started | MDC1-BL.5.3.9.4.7.1 | Task Dependent | Ligthing Installation | 2021-02-18 07:00 | 2021-03-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C1.C4480: FS, MDC1.C2.C2130: FS, MDC1.C2.C2300: SS 6 | MDC1.C2.C4410: FS | VECA Electricians | 480 | 0 |  | ['602: FS', '1031: FS', '785: SS 6'] | ['503: FS']
556 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-02-09 07:00 | 2021-03-04 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C2.C4060: FS, MDC1.C2.C4250: FS, MDC1.C2.C4280: FS, MDC1.C2.C2410: FS, MDC1.C2.C4040: FS, MDC1.C2.C4050: FS, MDC1-2527: FS | MDC1.C2.Cx2030: FS, MDC1.C2.C4400: FS | VECA Electricians | 1080 | 0 |  | ['1053: FS', '710: FS', '687: FS', '642: FS', '1125: FS', '1096: FS', '1325: FS'] | ['464: FS', '502: FS']
557 | Not Started | MDC1-BL.5.3.8.4.5.1 | Task Dependent | Ligthing Installation | 2021-02-18 07:00 | 2021-03-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 112 | 112 |  |  |  |  | MDC1.C2.C3390: FS, MDC1.C3.C1130: FS, MDC1.C3.C1250: FS | MDC1.C3.C3290: FS | VECA Electricians | 480 | 0 |  | ['603: FS', '905: FS', '637: FS'] | ['504: FS']
558 | Not Started | MDC1-BL.5.3.9.4.11.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-02-09 07:00 | 2021-03-04 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C1.C4460: FS, MDC1.C2.C2350: FS | MDC1.C2.Cx4010: FS, MDC1.C2.C4420: FS | LINX- TELECOM | 1440 | 0 |  | ['644: FS', '730: FS'] | ['263: FS', '475: FS']
559 | Not Started | MDC1-BL.5.2.3.6.1 | Task Dependent | EPMS Checkout / Point to Point | 2021-02-19 08:00 | 2021-03-04 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C1.Cx2020: FS | MDC1.C1.Cx3030: FS, MDC1.M1010: FS, MDC1.C1.Cx3050: FS, MDC1.C1.Cx2150: FS, MDC1.C1.Cx2150: FF | LINX- TELECOM | 1200 | 0 |  | ['595: FS'] | ['394: FS', '344: FS', '346: FS', '512: FS', '512: FF']
560 | Not Started | MDC1-BL.5.2.3.6.2 | Task Dependent | Network Startup | 2021-02-19 08:00 | 2021-03-04 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C3380: FS, MDC1.C1.Cx2030: FS, MDC1.C1.Cx2020: FS | MDC1.C1.Cx2180: FS, MDC1.C1.Cx2150: FS | LINX- TELECOM | 600 | 0 |  | ['761: FS', '596: FS', '595: FS'] | ['508: FS', '512: FS']
561 | Not Started | MDC1-BL.5.3.2.3.3 | Task Dependent | Concrete Floor Sealing/Epoxy | 2021-02-23 07:00 | 2021-03-02 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 43 | 43 |  |  |  |  | MDC1AD-1025: FS, MDC1AD-1010: FS | MDC1-C1.P1900: FS | PCI | 120 | 0 |  | ['675: FS', '589: FS'] | ['566: FS']
562 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-02-18 07:00 | 2021-03-02 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C3.C3200: FS | MDC1.C3.C3280: FS, MDC1.C3.C3350: FS |  | 0 | 0 |  | ['612: FS'] | ['526: FS', '442: FS']
563 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-02-25 07:00 | 2021-03-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 6 | 6 |  |  |  |  | MDC1.C3.C4050: FS, MDC1.C3.C4270: FS, MDC1.C3.C2290: FS | MDC1.C3.C4320: FS, MDC1.C3.C4370: FS, MDC1.C3.C4380: FS, MDC1.S.1900: FS | SURE STEEL | 160 | 0 |  | ['975: FS', '582: FS', '615: FS'] | ['490: FS', '445: FS', '443: FS', '257: FS']
564 | Not Started | MDC1-BL.5.3.6.3.1.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-02-18 07:00 | 2021-03-02 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C4.C3130: FS, MDC1.C4.C1140: FS | MDC1.C4.C3180: FS, MDC1.C4.C1220: SS 6 | VECA Electricians | 1200 | 0 |  | ['608: FS', '627: FS'] | ['524: FS', '548: SS 6']
565 | Not Started | MDC1-BL.5.3.6.3.3.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-02-18 07:00 | 2021-03-02 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C4.C4130: FS, MDC1.C4.C2140: FS | MDC1.C4.C4180: FS, MDC1.C4.C2220: SS 6 | VECA Electricians | 1200 | 0 |  | ['609: FS', '631: FS'] | ['525: FS', '549: SS 6']
566 | Not Started | MDC1-BL.3.2 | Finish Milestone | Admin / COLO 1 CSA complete |  | 2021-03-02 17:00 |  |  | 2021-03-02 17:00 |  | 0 | 0 | 0 | 0 | 43 | 43 |  |  |  |  | MDC1AD-1029: FS, MDC1AD-1026: FS, MDC1.C1.C4420: FS, MDC1.C1.C4430: FS, MDC1.C1.C1450: FS, MDC1.C1.C1350: FS, MDC1.C1.C2330: FS, MDC1.C1.C1450: SS, MDC1.C1.C3400: FS, MDC1.C1.C2400: FS, MDC1.C1.C4390: FS | MDC1.C1.Cx3040: FS |  | 0 | 0 |  | ['561: FS', '846: FS', '703: FS', '704: FS', '714: FS', '953: FS', '955: FS', '714: SS', '759: FS', '821: FS', '737: FS'] | ['355: FS']
567 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-02-17 07:00 | 2021-03-01 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.C3.C1240: FS, MDC1.C3.C1280: FS | MDC1.C3.C1380: FS, MDC1.C3.C3280: FS | VECA Electricians | 560 | 0 |  | ['641: FS', '614: FS'] | ['514: FS', '526: FS']
568 | Not Started | MDC1-BL.5.3.9.4.1.4 | Task Dependent | Controls Installation | 2021-02-13 08:00 | 2021-03-01 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C2.C1080: FS, MDC1.C2.C1120: FS, MDC1.C2.C1190: FS, MDC1.C2.C1430: FS | MDC1.C2.Cx2010: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0 |  | ['1122: FS', '1064: FS', '985: FS', '618: FS'] | ['498: FS', '31: FS']
569 | Not Started | MDC1-BL.5.3.8.4.9.1 | Task Dependent | Cable Tray Installation | 2021-02-13 07:00 | 2021-02-26 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C3210: FS, MDC1.C3.C1270: FS | MDC1.C3.C3270: FS, MDC1.C3.C1370: FS, MDC1.C3.C1350: FS, MDC1.C3.C1440: FS, MDC1.C3.C1340: FF 6 | VECA Electricians | 1440 | 0 |  | ['815: FS', '621: FS'] | ['521: FS', '520: FS', '536: FS', '427: FS', '546: FF 6']
570 | Not Started | MDC1-BL.5.3.8.4.11.1 | Task Dependent | Cable Tray Installation | 2021-02-13 07:00 | 2021-02-26 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C4170: FS, MDC1.C3.C2280: FS | MDC1.C3.C2360: FS, MDC1.C3.C4310: FS, MDC1.C3.C2340: FS, MDC1.C3.C2430: FS, MDC1.C3.C2320: FF 6 | VECA Electricians | 1440 | 0 |  | ['817: FS', '622: FS'] | ['522: FS', '523: FS', '537: FS', '429: FS', '547: FF 6']
571 | Not Started | MDC1-BL.5.3.9.4.9.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-02-03 07:00 | 2021-02-26 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 61 | 61 |  |  |  |  | MDC1.C1.C3460: FS, MDC1.C2.C1340: FS | MDC1.C2.Cx4010: FS, MDC1.C2.C3460: FS | LINX- TELECOM | 1440 | 0 |  | ['665: FS', '728: FS'] | ['263: FS', '484: FS']
572 | Not Started | MDC1-BL.5.3.6.4.5.2 | Task Dependent | Hydronic Piping Installation | 2021-02-12 07:00 | 2021-02-25 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C4.C1170: FS | MDC1.C4.Cx2000: FF | TCM | 480 | 0 |  | ['630: FS'] | ['312: FF']
573 | Not Started | MDC1-BL.5.3.6.3.6.1 | Task Dependent | OverHead MEPFP Rough-In | 2021-02-12 07:00 | 2021-02-25 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C4.C1150: FS, MDC1.C4.C1130: FS | MDC1.C4.C3160: FS, MDC1.C4.C3170: FS, MDC1.C4.C3150: FS, MDC1.C4.E1320: FS | TCM, VECA Electricians | 1360 | 0 |  | ['628: FS', '682: FS'] | ['530: FS', '531: FS', '529: FS', '74: FS']
574 | Not Started | MDC1-BL.5.3.6.4.7.2 | Task Dependent | Hydronic Piping Installation | 2021-02-12 07:00 | 2021-02-25 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C4.C2170: FS | MDC1.C4.Cx2010: FF | TCM | 480 | 0 |  | ['634: FS'] | ['298: FF']
575 | Not Started | MDC1-BL.5.3.6.3.8.1 | Task Dependent | OverHead MEPFP Rough-In | 2021-02-12 07:00 | 2021-02-25 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C4.C2150: FS, MDC1.C4.C2130: FS | MDC1.C4.C4160: FS, MDC1.C4.C4170: FS, MDC1.C4.C4150: FS, MDC1.C4.E1330: FS | TCM, VECA Electricians | 1360 | 0 |  | ['632: FS', '683: FS'] | ['533: FS', '534: FS', '532: FS', '76: FS']
576 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-02-02 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 19 | 19 | 0 | 0 |  |  |  |  | MDC1.C2.C3120: FS, MDC1.C2.C3080: FS, MDC1.C2.C3270: FS, MDC1.C2.C3310: FS, MDC1.C2.C3340: FS | MDC1.C2.C3440: FS, MDC1.C2.C3450: FS | VECA Electricians | 1080 | 0 |  | ['986: FS', '1052: FS', '732: FS', '696: FS', '666: FS'] | ['535: FS', '499: FS']
577 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-02-11 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C4310: FS, MDC1.C2.C4060: FS, MDC1.C2.C4250: FS, MDC1.C2.C2420: FS | MDC1.C2.Cx2030: FS, MDC1.C2.C4390: FS | VECA Electricians | 960 | 0 |  | ['643: FS', '1053: FS', '710: FS', '636: FS'] | ['464: FS', '501: FS']
578 | Not Started | MDC1-BL.5.3.8.4.5.3 | Task Dependent | Floor Drain System Installation | 2021-02-11 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 130 | 130 |  |  |  |  | MDC1.C3.C1030: FS, MDC1.C3.C1250: FS | MDC1-C3.P1900: FS |  | 0 | 0 |  | ['1078: FS', '637: FS'] | ['367: FS']
579 | Not Started | MDC1-BL.5.3.8.4.5.3 | Task Dependent | Toilet Piping Installation / DW | 2021-02-11 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 130 | 130 |  |  |  |  | MDC1.C3.C1250: FS | MDC1-C3.P1900: FS | TCM | 480 | 0 |  | ['637: FS'] | ['367: FS']
580 | Not Started | MDC1-BL.5.3.8.3.2.2 | Task Dependent | Datahall Finishes | 2021-02-11 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 130 | 130 |  |  |  |  | MDC1.C3.C3190: FS | MDC1-C3.P1900: FS | PCI | 480 | 0 |  | ['638: FS'] | ['367: FS']
581 | Not Started | MDC1-BL.5.3.8.3.4.2 | Task Dependent | Datahall Finishes | 2021-02-11 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 130 | 130 |  |  |  |  | MDC1.C3.C4230: FS | MDC1-C3.P1900: FS | PCI | 480 | 0 |  | ['639: FS'] | ['367: FS']
582 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Lift & Set MER in Place | 2021-02-19 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C3.E1370: FS, MDC1.C3.E1270: FS, MDC1.C3.C4050: FS, MDC1.C3.C3200: FS | MDC1.C3.C4290: FS, MDC1.C3.C4300: FS, MDC1.C4.C1230: FS | VECA Electricians | 120 | 0 |  | ['52: FS', '938: FS', '975: FS', '612: FS'] | ['563: FS', '539: FS', '511: FS']
583 | Not Started | MDC1-BL.5.3.8.4.10.1 | Task Dependent | HAC Installation | 2021-02-11 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C3190: FS | MDC1.C3.C3270: FS | TCM | 480 | 0 |  | ['638: FS'] | ['521: FS']
584 | Not Started | MDC1-BL.5.3.8.4.13.1 | Task Dependent | HAC Installation | 2021-02-11 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C4230: FS | MDC1.C3.C4310: FS | TCM | 480 | 0 |  | ['639: FS'] | ['523: FS']
585 | Not Started | MDC1-BL.5.2.5.1 | Task Dependent | Network Startup | 2021-02-10 07:00 | 2021-02-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 20 | 20 |  |  |  |  | MDC1AD-1027: FS, MDC1.AD.Cx2000: FS | MDC1.AD.Cx2020: FS | LINX- TELECOM | 720 | 0 |  | ['845: FS', '640: FS'] | ['540: FS']
586 | Not Started | MDC1-BL.5.2.3.6.3 | Task Dependent | Network Startup | 2021-02-12 07:00 | 2021-02-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C2370: FS, MDC1.C1.Cx2010: FS | MDC1.C1.Cx2090: FS, MDC1.C1.Cx2110: FS, MDC1.C1.Cx2100: FS | LINX- TELECOM | 600 | 0 |  | ['870: FS', '623: FS'] | ['541: FS', '538: FS', '542: FS']
587 | Not Started | MDC1-BL.5.2.3.6.4 | Task Dependent | Equipment Yellow Tagging | 2021-02-12 07:00 | 2021-02-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C4210: FS, MDC1.C1.C4360: FS, MDC1.C1.C4380: FS, MDC1.C1.C4300: FS, MDC1.C1.C4440: FS, MDC1.C1.C4290: FS, MDC1.C1.C4150: FS, MDC1.C1.C4470: FS, MDC1.C1.C4040: FS, MDC1.C1.C4450: FS, MDC1.C1.Cx2010: FS | MDC1.C1.Cx2100: FS, MDC1.C1.Cx2120: SS 6 | VECA Electricians | 1200 | 0 |  | ['960: FS', '777: FS', '750: FS', '873: FS', '695: FS', '872: FS', '1111: FS', '624: FS', '1236: FS', '647: FS', '623: FS'] | ['542: FS', '517: SS 6']
588 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-02-12 07:00 | 2021-02-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C3.C2260: FS | MDC1.C3.C2330: FS, MDC1.C3.C2330: FF |  | 0 | 0 |  | ['635: FS'] | ['543: FS', '543: FF']
589 | Not Started | MDC1-BL.5.3.2.3.3 | Task Dependent | Loading Dock Equipment & Dock Doors | 2021-01-29 07:00 | 2021-02-22 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 43 | 43 |  |  |  |  | MDC1-C1.P1200: FS, MDC1.AD.CS1040: FS, MDC1.AD.CS1050: FS, MDC1.C1.CS1110: FS, MDC1AD-1025: FS | MDC1AD-1029: FS | VECA Electricians | 400 | 0 |  | ['22: FS', '1326: FS', '1318: FS', '1241: FS', '675: FS'] | ['561: FS']
590 | Not Started | MDC1-BL.5.3.9.4.3.4 | Task Dependent | Controls Installation | 2021-02-09 07:00 | 2021-02-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 10 | 10 |  |  |  |  | MDC1.C2.C2060: FS, MDC1.C2.C2170: FS, MDC1.C2.C2230: FS, MDC1.C2.C2410: FS | MDC1.C2.Cx2000: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0 |  | ['1124: FS', '987: FS', '887: FS', '642: FS'] | ['500: FS', '31: FS']
591 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-02-18 07:00 | 2021-02-22 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 10 | 10 |  |  |  |  | MDC1.C3.C3050: FS, MDC1.C3.C3200: FS, MDC1.C3.C1240: FS | MDC1.C3.C3280: FS, MDC1.C3.C3330: FS, MDC1.C3.C3350: FS | SURE STEEL | 160 | 0 |  | ['973: FS', '612: FS', '641: FS'] | ['526: FS', '466: FS', '442: FS']
592 | Not Started | MDC1-BL.5.3.9.4.10.1 | Task Dependent | Light Fixtures Installation | 2021-02-15 07:00 | 2021-02-20 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 11 | 11 |  |  |  |  | MDC1.C2.C3360: FS, MDC1.C2.C3370: FS, MDC1.C2.C3290: FS | MDC1-C2.P1800: FS | VECA Electricians | 480 | 0 |  | ['625: FS', '616: FS', '717: FS'] | ['594: FS']
593 | Not Started | MDC1-BL.5.3.9.4.13.1 | Task Dependent | Light Fixtures Installation | 2021-02-15 07:00 | 2021-02-20 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 11 | 11 |  |  |  |  | MDC1.C2.C4320: FS, MDC1.C2.C4330: FS, MDC1.C2.C4240: FS | MDC1-C2.P1800: FS, MDC1-C2.P1800: SS | VECA Electricians | 480 | 0 |  | ['626: FS', '617: FS', '718: FS'] | ['594: FS', '594: SS']
594 | Not Started | MDC1-BL.3.3 | Finish Milestone | COLO 2 CSA complete |  | 2021-02-20 17:00 |  |  | 2021-02-20 17:00 |  | 0 | 0 | 0 | 0 | 11 | 11 |  |  |  |  | MDC1.C2.C4360: FS, MDC1.C2.C3400: FS, MDC1.C2.C3410: FS, MDC1.C2.C1420: FS, MDC1.C2.C3420: FS, MDC1.C2.C2400: FS, MDC1.C2.C4360: SS, MDC1.C2.C1360: FS, MDC1.C2.C2360: FS, MDC1.C2.C4340: FS, MDC1.C2.C1370: FS, MDC1.C2.C2310: FS, MDC1.C2.C4350: FS | MDC1.M1010: FS, MDC1.C1.Cx4020: FS, MDC1.C2.Cx2030: FS, MDC1.C2.Cx2000: FS, MDC1.C2.Cx2050: FS, MDC1.C2.Cx2010: FS |  | 0 | 0 |  | ['593: FS', '604: FS', '605: FS', '648: FS', '592: FS', '649: FS', '593: SS', '706: FS', '709: FS', '606: FS', '707: FS', '786: FS', '607: FS'] | ['344: FS', '267: FS', '464: FS', '500: FS', '462: FS', '498: FS']
595 | Not Started | MDC1-BL.5.2.3.6.1 | Task Dependent | Network Startup | 2021-02-08 08:00 | 2021-02-19 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2000: FS, MDC1-1976: FS, MDC1-C1.P1800: FS | MDC1.C1.Cx2060: FS, MDC1.C1.Cx2080: FS, MDC1.C1.Cx2070: FS | LINX- TELECOM | 600 | 0 |  | ['645: FS', '684: FS', '30: FS'] | ['559: FS', '550: FS', '560: FS']
596 | Not Started | MDC1-BL.5.2.3.6.2 | Task Dependent | Equipment Yellow Tagging | 2021-02-08 08:00 | 2021-02-19 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C3360: FS, MDC1.C1.C3380: FS, MDC1.C1.C3310: FS, MDC1.C1.C3410: FS, MDC1.C1.C3150: FS, MDC1.C1.C3230: FS, MDC1.C1.C3450: FS, MDC1.C1.C3470: FS, MDC1.C1.C3040: FS, MDC1.C1.C3330: FS, MDC1.C1.Cx2000: FS | MDC1.C1.Cx2070: FS, MDC1.C1.Cx2160: FS | VECA Electricians | 1200 | 0 |  | ['794: FS', '761: FS', '885: FS', '736: FS', '1084: FS', '966: FS', '669: FS', '646: FS', '1235: FS', '851: FS', '645: FS'] | ['560: FS', '513: FS']
597 | Not Started | MDC1-BL.5.3.8.4.6.3 | Task Dependent | Floor Drain System Installation | 2021-02-04 07:00 | 2021-02-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 135 | 135 |  |  |  |  | MDC1.C3.C3030: FS, MDC1.C3.C3160: FS | MDC1-C3.P1900: FS |  | 0 | 0 |  | ['1005: FS', '655: FS'] | ['367: FS']
598 | Not Started | MDC1-BL.5.3.8.4.6.3 | Task Dependent | Toilet Piping Installation / DW | 2021-02-04 07:00 | 2021-02-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 135 | 135 |  |  |  |  | MDC1.C3.C3160: FS | MDC1-C3.P1900: FS | TCM | 480 | 0 |  | ['655: FS'] | ['367: FS']
599 | Not Started | MDC1-BL.5.3.8.4.8.3 | Task Dependent | Floor Drain System Installation | 2021-02-04 07:00 | 2021-02-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 135 | 135 |  |  |  |  | MDC1.C3.C4030: FS, MDC1.C3.C4200: FS | MDC1-C3.P1900: FS |  | 0 | 0 |  | ['1008: FS', '657: FS'] | ['367: FS']
600 | Not Started | MDC1-BL.5.3.8.4.8.3 | Task Dependent | Toilet Piping Installation / DW | 2021-02-04 07:00 | 2021-02-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 135 | 135 |  |  |  |  | MDC1.C3.C4200: FS | MDC1-C3.P1900: FS | TCM | 480 | 0 |  | ['657: FS'] | ['367: FS']
601 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Yellow Tagging for UMS | 2021-01-18 07:00 | 2021-02-18 17:00 |  |  |  |  | 0 | 0 | 27 | 27 | 0 | 0 |  |  |  |  | MDC1.S.1810: FF, MDC1.S.1660: FF, MDC1.S.1530: FF, MDC1.S.1610: FF, MDC1.S.1450: FF, MDC1.S.1430: FF, MDC1.S.1800: FS, MDC1.S.1780: FS, MDC1.S.1810: FS, MDC1.S.1660: FS, MDC1.S.1530: FS, MDC1.S.1610: FS, MDC1.S.1790: FS, MDC1.S.1450: FS, MDC1.S.1430: FS, MDC1.S.1760: FS, MDC1.S.1490: FS, MDC1.S.1820: FS, MDC1.S.1570: FS, MDC1-P1050: FS | MDC1.C1.Cx3030: FS, MDC1.C1.Cx2140: FS, MDC1.C1.Cx2160: FS, MDC1.C1.Cx2130: FS, MDC1.C1.Cx2120: FS | VECA Electricians | 540 | 0 |  | ['726: FF', '881: FF', '979: FF', '935: FF', '1059: FF', '1068: FF', '766: FS', '764: FS', '726: FS', '881: FS', '979: FS', '935: FS', '765: FS', '1059: FS', '1068: FS', '771: FS', '1025: FS', '727: FS', '1072: FS', '939: FS'] | ['394: FS', '519: FS', '513: FS', '518: FS', '517: FS']
602 | Not Started | MDC1-BL.5.3.1.4.8.1 | Task Dependent | Ligthing Installation | 2021-02-03 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 70 | 70 |  |  |  |  | MDC1.C1.C2470: FF, MDC1.C1.C2470: FS, MDC1.C1.C4240: FS, MDC1.C1.C4350: FS | MDC1.C2.C2440: FS, MDC1.C1.C4490: FS | VECA Electricians | 480 | 0 |  | ['662: FF', '662: FS', '921: FS', '782: FS'] | ['555: FS', '610: FS']
603 | Not Started | MDC1-BL.5.3.9.4.6.1 | Task Dependent | Ligthing Installation | 2021-02-03 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 112 | 112 |  |  |  |  | MDC1.C2.C1350: FS, MDC1.C2.C3350: FS | MDC1.C3.C1330: FS | VECA Electricians | 480 | 0 |  | ['705: FS', '663: FS'] | ['557: FS']
604 | Not Started | MDC1-BL.5.3.9.4.6.3 | Task Dependent | Floor Drain System Installation | 2021-02-03 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 14 | 14 |  |  |  |  | MDC1.C2.C3100: FS, MDC1.C2.C3350: FS | MDC1-C2.P1800: FS |  | 0 | 0 |  | ['1016: FS', '663: FS'] | ['594: FS']
605 | Not Started | MDC1-BL.5.3.9.4.6.3 | Task Dependent | Toilet Piping Installation / DW | 2021-02-03 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 14 | 14 |  |  |  |  | MDC1.C2.C3350: FS | MDC1-C2.P1800: FS | TCM | 480 | 0 |  | ['663: FS'] | ['594: FS']
606 | Not Started | MDC1-BL.5.3.9.4.8.3 | Task Dependent | Floor Drain System Installation | 2021-02-03 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 14 | 14 |  |  |  |  | MDC1.C2.C4080: FS, MDC1.C2.C4300: FS | MDC1-C2.P1800: FS |  | 0 | 0 |  | ['1019: FS', '664: FS'] | ['594: FS']
607 | Not Started | MDC1-BL.5.3.9.4.8.3 | Task Dependent | Toilet Piping Installation / DW | 2021-02-03 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 14 | 14 |  |  |  |  | MDC1.C2.C4300: FS | MDC1-C2.P1800: FS | TCM | 480 | 0 |  | ['664: FS'] | ['594: FS']
608 | Not Started | MDC1-BL.5.3.6.3.2.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2021-02-12 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 4 | 4 |  |  |  |  | MDC1.C4.C1140: FS | MDC1.C4.C1190: FS, MDC1.C4.C3180: FS | TCM, VECA Electricians | 800 | 0 |  | ['627: FS'] | ['564: FS', '524: FS']
609 | Not Started | MDC1-BL.5.3.6.3.4.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2021-02-12 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 4 | 4 |  |  |  |  | MDC1.C4.C2140: FF, MDC1.C4.C2140: FS | MDC1.C4.C2190: FS, MDC1.C4.C4180: FS | TCM, VECA Electricians | 800 | 0 |  | ['631: FF', '631: FS'] | ['565: FS', '525: FS']
610 | Not Started | MDC1-BL.5.3.1.4.8.4 | Finish Milestone | Mechanical Corridor complete |  | 2021-02-17 17:00 |  |  | 2021-02-17 17:00 |  | 0 | 0 | 0 | 0 | 70 | 70 |  |  |  |  | MDC1.C1.C4430: FS, MDC1.C1.C4420: FS, MDC1.C1.C2360: FS, MDC1.C1.C2350: FS, MDC1.C1.C3440: FS, MDC1.C1.C3430: FS, MDC1.C1.C1370: FS, MDC1.C1.C1380: FS, MDC1.C1.C1470: FS, MDC1.C1.C3420: FS, MDC1.C1.C2470: FS, MDC1.C1.C4480: FS, MDC1.C1.C4290: FS | MDC1.M1010: FS |  | 0 | 0 |  | ['704: FS', '703: FS', '869: FS', '868: FS', '702: FS', '701: FS', '864: FS', '865: FS', '661: FS', '700: FS', '662: FS', '602: FS', '872: FS'] | ['344: FS']
611 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Yellow Tagging for URS | 2021-01-18 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 26 | 26 | 1 | 1 |  |  |  |  | MDC1.S.1800: FS, MDC1.S.1780: FS, MDC1.S.1810: FS, MDC1.S.1660: FS, MDC1.S.1530: FS, MDC1.S.1610: FS, MDC1.S.1790: SS 4, MDC1.S.1450: FS, MDC1.S.1430: FS, MDC1.S.1760: FS, MDC1.S.1490: FS, MDC1.S.1310: FS, MDC1-P1050: FS | MDC1.C1.Cx2140: FS, MDC1.C1.Cx2080: FS, MDC1.C1.Cx2160: FS, MDC1.C1.Cx2130: FS, MDC1.C1.Cx2120: FS | VECA Electricians | 540 | 0 |  | ['766: FS', '764: FS', '726: FS', '881: FS', '979: FS', '935: FS', '765: SS 4', '1059: FS', '1068: FS', '771: FS', '1025: FS', '1114: FS', '939: FS'] | ['519: FS', '550: FS', '513: FS', '518: FS', '517: FS']
612 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Lift & Set MER in Place | 2021-02-12 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 1 | 1 |  |  |  |  | MDC1.C3.E1360: FS, MDC1.C3.E1260: FS, MDC1.C3.C3050: FS, MDC1.C3.C2260: FS | MDC1.C3.C3230: FS, MDC1.C3.C3260: FS, MDC1.C3.C4270: FS | VECA Electricians | 120 | 0 |  | ['50: FS', '937: FS', '973: FS', '635: FS'] | ['591: FS', '562: FS', '582: FS']
613 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-02-02 07:00 | 2021-02-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 7 | 7 |  |  |  |  | MDC1.C2.C3340: FS, MDC1.C2.C3080: FS, MDC1.C2.C3270: FS | MDC1.C2.Cx2050: FS, MDC1.C2.C3450: FS | VECA Electricians | 960 | 0 |  | ['666: FS', '1052: FS', '732: FS'] | ['462: FS', '499: FS']
614 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-02-04 07:00 | 2021-02-16 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.C3.C1230: FS | MDC1.C3.C1320: FS, MDC1.C3.C1360: FS |  | 0 | 0 |  | ['659: FS'] | ['567: FS', '527: FS']
615 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-02-12 07:00 | 2021-02-16 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 5 | 5 |  |  |  |  | MDC1.C3.C2050: FS, MDC1.C3.C2260: FS | MDC1.C3.C2330: FS, MDC1.C3.C2380: FS, MDC1.C3.C2350: FS, MDC1.C3.C4290: FS | SURE STEEL | 160 | 0 |  | ['1056: FS', '635: FS'] | ['543: FS', '485: FS', '528: FS', '563: FS']
616 | Not Started | MDC1-BL.5.3.9.4.10.3 | Task Dependent | Controls Installation | 2021-01-30 07:00 | 2021-02-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C3210: FS, MDC1.C2.C3220: FS, MDC1.C2.C3330: FS | MDC1.C2.C3420: FS, MDC1.C2.Cx2050: FS | VECA Electricians | 720 | 0 |  | ['815: FS', '767: FS', '672: FS'] | ['592: FS', '462: FS']
617 | Not Started | MDC1-BL.5.3.9.4.13.3 | Task Dependent | Controls Installation | 2021-01-30 07:00 | 2021-02-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C4170: FS, MDC1.C2.C4200: FS, MDC1.C2.C4290: FS | MDC1.C2.C4360: FS, MDC1.C2.Cx2030: FS 5, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0 |  | ['817: FS', '738: FS', '674: FS'] | ['593: FS', '464: FS 5', '31: FS']
618 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-01-20 08:00 | 2021-02-13 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C2.C1120: FS, MDC1.C2.C1080: FS, MDC1.C2.C1290: FS, MDC1.C2.C1330: FS, MDC1.C2.C1380: FS | MDC1.C2.C1450: FS, MDC1.C2.C1460: FS | VECA Electricians | 1080 | 0 |  | ['1064: FS', '1122: FS', '812: FS', '772: FS', '699: FS'] | ['568: FS', '544: FS']
619 | Not Started | MDC1-BL.5.3.8.3.1.2 | Task Dependent | Datahall Finishes | 2021-01-29 07:00 | 2021-02-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C3.C1220: FS | MDC1-C3.P1800: FS | PCI | 480 | 0 |  | ['676: FS'] | ['32: FS']
620 | Not Started | MDC1-BL.5.3.8.3.3.2 | Task Dependent | Datahall Finishes | 2021-01-29 07:00 | 2021-02-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C3.C2250: FS | MDC1-C3.P1800: FS | PCI | 480 | 0 |  | ['677: FS'] | ['32: FS']
621 | Not Started | MDC1-BL.5.3.8.4.9.1 | Task Dependent | HAC Installation | 2021-01-29 07:00 | 2021-02-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C1220: FS | MDC1.C3.C1310: FS | TCM | 480 | 0 |  | ['676: FS'] | ['569: FS']
622 | Not Started | MDC1-BL.5.3.8.4.11.1 | Task Dependent | HAC Installation | 2021-01-29 07:00 | 2021-02-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C2250: FS | MDC1.C3.C2310: FS | TCM | 480 | 0 |  | ['677: FS'] | ['570: FS']
623 | Not Started | MDC1-BL.5.2.3.6.3 | Task Dependent | Equipment Yellow Tagging | 2021-01-30 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C2380: FS, MDC1.C1.C2370: FS, MDC1.C1.C2320: FS, MDC1.C1.C2140: FS, MDC1.C1.C2430: FS, MDC1.C1.C2300: FS, MDC1.C1.C2450: FS, MDC1.C1.C2460: FS, MDC1.C1.C2040: FS, MDC1.C1.C2310: FF 6 | MDC1.C1.Cx2040: FS, MDC1.C1.Cx2130: FS, MDC1.C1.Cx2050: FS | VECA Electricians | 1200 | 0 |  | ['862: FS', '870: FS', '970: FS', '1164: FS', '773: FS', '968: FS', '694: FS', '670: FS', '1271: FS', '969: FF 6'] | ['586: FS', '518: FS', '587: FS']
624 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Pull Conductors into Building | 2021-01-22 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 17 | 17 | 0 | 0 |  |  |  |  | MDC1.C1.C4090: FS, MDC1.C1.C4440: FS | MDC1.C1.Cx2050: FS | VECA Electricians | 1440 | 0 |  | ['1180: FS', '695: FS'] | ['587: FS']
625 | Not Started | MDC1-BL.5.3.9.4.10.1 | Task Dependent | Pull / Term / Test Conductors | 2021-01-18 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 13 | 13 |  |  |  |  | MDC1.C2.C3290: FS | MDC1.C2.C3420: FS, MDC1.C2.Cx2050: FS | VECA Electricians | 1680 | 0 |  | ['717: FS'] | ['592: FS', '462: FS']
626 | Not Started | MDC1-BL.5.3.9.4.13.1 | Task Dependent | Pull / Term / Test Conductors | 2021-01-18 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 13 | 13 |  |  |  |  | MDC1.C2.C4240: FS | MDC1.C2.C4360: FS, MDC1.C2.Cx2030: FS | VECA Electricians | 1680 | 0 |  | ['718: FS'] | ['593: FS', '464: FS']
627 | Not Started | MDC1-BL.5.3.6.3.1.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2021-02-05 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 4 | 4 |  |  |  |  | MDC1.C3.C3180: FS, MDC1.C3.C3060: FS, MDC1.C4.CS1090: FS, MDC1-C4.P1500: FS | MDC1.C4.C3130: FS, MDC1.C4.C1190: FS | TCM, VECA Electricians | 800 | 0 |  | ['653: FS', '958: FS', '1062: FS', '20: FS'] | ['608: FS', '564: FS']
628 | Not Started | MDC1-BL.5.3.6.3.5.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2021-01-28 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C4.C1130: FS | MDC1.C4.C1200: FS, MDC1.C4.C3140: FS | VECA Electricians | 960 | 0 |  | ['682: FS'] | ['551: FS', '573: FS']
629 | Not Started | MDC1-BL.5.3.6.4.5.1 | Task Dependent | VFD'S Installation & Wiring | 2021-01-28 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 67 | 67 |  |  |  |  | MDC1.C4.C1130: FS | MDC1.C4.C1300: FS, MDC1.C4.C1210: FS, MDC1.C4.Cx3020: FS | VECA Electricians | 240 | 0 |  | ['682: FS'] | ['455: FS', '552: FS', '244: FS']
630 | Not Started | MDC1-BL.5.3.6.4.5.2 | Task Dependent | AHU/DOAS Equipment Setting | 2021-01-28 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C4.C1130: FS, MDC1.C4.E1280: FS, MDC1.C4.E1300: FS | MDC1.C4.C1180: FS | TCM | 480 | 0 |  | ['682: FS', '73: FS', '89: FS'] | ['572: FS']
631 | Not Started | MDC1-BL.5.3.6.3.3.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2021-02-05 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 4 | 4 |  |  |  |  | MDC1.C3.C4220: FS, MDC1.C3.C4060: FS | MDC1.C4.C4130: FF, MDC1.C4.C4130: FS, MDC1.C4.C2190: FS | TCM, VECA Electricians | 800 | 0 |  | ['654: FS', '959: FS'] | ['609: FF', '609: FS', '565: FS']
632 | Not Started | MDC1-BL.5.3.6.3.7.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2021-01-28 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C4.C2130: FS | MDC1.C4.C4140: FS, MDC1.C4.C2200: FS | VECA Electricians | 960 | 0 |  | ['683: FS'] | ['575: FS', '553: FS']
633 | Not Started | MDC1-BL.5.3.6.4.7.1 | Task Dependent | VFD'S Installation & Wiring | 2021-01-28 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 67 | 67 |  |  |  |  | MDC1.C4.C2130: FS | MDC1.C4.C2370: FS, MDC1.C4.C2210: FS, MDC1.C4.Cx3020: FS | VECA Electricians | 240 | 0 |  | ['683: FS'] | ['370: FS', '554: FS', '244: FS']
634 | Not Started | MDC1-BL.5.3.6.4.7.2 | Task Dependent | AHU/DOAS Equipment Setting | 2021-01-28 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C4.C2130: FS, MDC1.C4.E1290: FS, MDC1.C4.E1310: FS | MDC1.C4.C2180: FS | TCM | 480 | 0 |  | ['683: FS', '75: FS', '91: FS'] | ['574: FS']
635 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Lift & Set MER in Place | 2021-02-05 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C3.E1350: FS, MDC1.C3.E1130: FS, MDC1.C3.C2050: FS, MDC1.C3.C1230: FS | MDC1.C3.C2290: FS, MDC1.C3.C2300: FS, MDC1.C3.C3200: FS | VECA Electricians | 120 | 0 |  | ['51: FS', '1033: FS', '1056: FS', '659: FS'] | ['615: FS', '588: FS', '612: FS']
636 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-01-27 07:00 | 2021-02-10 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C2060: FS, MDC1.C2.C2330: FS, MDC1.C2.C2370: FS | MDC1.C2.Cx2000: FS, MDC1.C2.C2460: FS, MDC1.C2.C4370: FS | VECA Electricians | 960 | 0 |  | ['1124: FS', '774: FS', '688: FS'] | ['500: FS', '545: FS', '577: FS']
637 | Not Started | MDC1-BL.5.3.8.3.5.2 | Task Dependent | Mechanical Corridor Finishes | 2021-01-20 07:00 | 2021-02-10 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 118 | 118 |  |  |  |  | MDC1.C3.C1120: FS, MDC1.C3.C1030: FS, MDC1.C2.C1360: FS | MDC1.C3.C1330: FS, MDC1.C3.C1300: FS, MDC1-C3.P1900: FS, MDC1.C3.C1290: FS | PCI | 180 | 0 |  | ['904: FS', '1078: FS', '706: FS'] | ['557: FS', '579: FS', '367: FS', '578: FS']
638 | Not Started | MDC1-BL.5.3.8.3.2.1 | Task Dependent | Hang Wall Partitions | 2021-02-01 07:00 | 2021-02-10 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 2 | 2 |  |  |  |  | MDC1.C3.CS1090: FS, MDC1.C3.C3180: SS 6 | MDC1.C3.C3240: FS, MDC1.C3.C3250: FS | PCI | 600 | 0 |  | ['1140: FS', '653: SS 6'] | ['580: FS', '583: FS']
639 | Not Started | MDC1-BL.5.3.8.3.4.1 | Task Dependent | Hang Wall Partitions | 2021-02-01 07:00 | 2021-02-10 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 2 | 2 |  |  |  |  | MDC1.C3.CS1090: FS, MDC1.C3.C4220: SS 6 | MDC1.C3.C4260: FS, MDC1.C3.C4280: FS | PCI | 600 | 0 |  | ['1140: FS', '654: SS 6'] | ['581: FS', '584: FS']
640 | Not Started | MDC1-BL.5.2.5.1 | Task Dependent | Level 2 Cx Admin | 2021-01-26 07:00 | 2021-02-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 20 | 20 |  |  |  |  | MDC1AD-1019: FS, MDC1AD-1027: FS, MDC1AD-1023: FS, MDC1-P1050: FS, MDC1-1969: FS 10, MDC1-1967: FS, MDC1-1971: FS, MDC1AD-1022: FS | MDC1.AD.Cx2010: FS, MDC1.M1010: FS, MDC1.C1.Cx3050: FS |  | 0 | 0 |  | ['882: FS', '845: FS', '757: FS', '939: FS', '746: FS 10', '795: FS', '1044: FS', '883: FS'] | ['585: FS', '344: FS', '346: FS']
641 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-02-04 07:00 | 2021-02-09 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 9 | 9 |  |  |  |  | MDC1.C3.C1230: FS | MDC1.C3.C1320: FS, MDC1.C3.C1380: FS, MDC1.C3.C1360: FS, MDC1.C3.C3230: FS | SURE STEEL | 160 | 0 |  | ['659: FS'] | ['567: FS', '514: FS', '527: FS', '591: FS']
642 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-01-14 07:00 | 2021-02-08 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C2.C2170: FS, MDC1.C2.C2060: FS, MDC1.C2.C2330: FS, MDC1.C2.C2340: FS | MDC1.C2.C2430: FS, MDC1.C2.C4380: FS | VECA Electricians | 1080 | 0 |  | ['987: FS', '1124: FS', '774: FS', '733: FS'] | ['590: FS', '556: FS']
643 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-01-27 07:00 | 2021-02-08 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C2.C4250: FS, MDC1.C2.C4280: FS, MDC1.C2.C2370: FS | MDC1.C2.C4370: FS | VECA Electricians | 560 | 0 |  | ['710: FS', '687: FS', '688: FS'] | ['577: FS']
644 | Not Started | MDC1-BL.5.3.1.4.13.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-01-14 07:00 | 2021-02-08 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C1.C2440: FS, MDC1.C1.C4380: FS | MDC1.C2.Cx4010: FS, MDC1.C1.Cx4000: FS, MDC1.C2.C2450: FS | LINX- TELECOM | 1440 | 0 |  | ['735: FS', '750: FS'] | ['263: FS', '295: FS', '558: FS']
645 | Not Started | MDC1-BL.5.2.3.6.1 | Task Dependent | Equipment Yellow Tagging | 2021-01-25 08:00 | 2021-02-08 08:00 |  |  |  |  | 0 | 0 | 11 | 11 | 0 | 0 |  |  |  |  | MDC1.C1.C1410: FS, MDC1.C1.C1400: FS, MDC1.C1.C1390: FS, MDC1.C1.C1340: FS, MDC1.C1.C1420: FS, MDC1-P1050: FS, MDC1.C1.C1460: FS, MDC1.C1.C1440: FS, MDC1.C1.C1320: FS, MDC1.C1.C1330: FS, MDC1.C1.C1130: FS, MDC1.C1.C1040: FS, MDC1.C1.C1290: FF, MDC1.C1.C3340: FF, MDC1.C1.C2260: FF, MDC1.C1.C4320: FF | MDC1.C1.Cx2020: FS, MDC1.C1.Cx2140: FS, MDC1.C1.Cx2030: FS | VECA Electricians | 1200 | 0 |  | ['831: FS', '861: FS', '866: FS', '965: FS', '818: FS', '939: FS', '689: FS', '716: FS', '963: FS', '964: FS', '1188: FS', '1270: FS', '1009: FF', '832: FF', '1011: FF', '833: FF'] | ['595: FS', '519: FS', '596: FS']
646 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Pull Conductors into Building | 2021-01-13 07:00 | 2021-02-05 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C1.C3080: FS, MDC1.C1.C3410: FS | MDC1.C1.Cx2030: FS | VECA Electricians | 1440 | 0 |  | ['1179: FS', '736: FS'] | ['596: FS']
647 | Not Started | MDC1-BL.5.3.1.4.4.4 | Task Dependent | Controls Installation | 2021-01-19 07:00 | 2021-02-05 17:00 |  |  |  |  | 0 | 0 | 16 | 16 | 4 | 4 |  |  |  |  | MDC1.C1.C4090: FS, MDC1.C1.C4120: FS, MDC1.C1.C4170: FS, MDC1.C1.C4410: FS | MDC1.C1.Cx2050: FS | VECA Electricians | 640 | 0 |  | ['1180: FS', '1132: FS', '1063: FS', '715: FS'] | ['587: FS']
648 | Not Started | MDC1-BL.5.3.9.4.9.1 | Task Dependent | Light Fixtures Installation | 2021-01-30 07:00 | 2021-02-05 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 23 | 23 |  |  |  |  | MDC1.C2.C1400: FS, MDC1.C2.C1300: FS | MDC1-C2.P1800: FS | VECA Electricians | 480 | 0 |  | ['671: FS', '797: FS'] | ['594: FS']
649 | Not Started | MDC1-BL.5.3.9.4.11.1 | Task Dependent | Light Fixtures Installation | 2021-01-30 07:00 | 2021-02-05 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 23 | 23 |  |  |  |  | MDC1.C2.C2380: FS, MDC1.C2.C2390: FS, MDC1.C2.C2280: FS | MDC1-C2.P1800: FS | VECA Electricians | 480 | 0 |  | ['679: FS', '673: FS', '798: FS'] | ['594: FS']
650 | Not Started | MDC1-BL.5.3.6.4.2.2 | Task Dependent | Mechanical Equipment Piping Connections | 2021-01-23 07:00 | 2021-02-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 99 | 99 |  |  |  |  | MDC1.C4.C3110: SS 5 | MDC1.C4.Cx2030: FS | TCM | 720 | 0 |  | ['667: SS 5'] | ['287: FS']
651 | Not Started | MDC1-BL.5.3.6.4.4.2 | Task Dependent | Mechanical Equipment Piping Connections | 2021-01-23 07:00 | 2021-02-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 99 | 99 |  |  |  |  | MDC1.C4.C4110: SS 5 | MDC1.C4.Cx2050: FS | TCM | 720 | 0 |  | ['668: SS 5'] | ['285: FS']
652 | Not Started | MDC1-BL.5.1.9 | Task Dependent | Telecom-RNG Fiber CNR buildout | 2020-12-02 07:00 | 2021-02-05 17:00 |  |  |  |  | 0 | 0 | 50 | 50 | 79 | 79 |  |  |  |  | MDC1.S.1540: FS | MDC1.C1.Cx4000: FS | LINX- TELECOM | 5000 | 0 |  | ['961: FS'] | ['295: FS']
653 | Not Started | MDC1-BL.5.3.8.3.2.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-01-25 07:00 | 2021-02-04 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C3.C1210: FS, MDC1.C3.C3060: FS | MDC1.C4.C1140: FS, MDC1.C3.C3190: SS 6 | VECA Electricians | 1200 | 0 |  | ['690: FS', '958: FS'] | ['627: FS', '638: SS 6']
654 | Not Started | MDC1-BL.5.3.8.3.4.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-01-25 07:00 | 2021-02-04 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C3.C2240: FS, MDC1.C3.C4060: FS | MDC1.C4.C2140: FS, MDC1.C3.C4230: SS 6 | VECA Electricians | 1200 | 0 |  | ['691: FS', '959: FS'] | ['631: FS', '639: SS 6']
655 | Not Started | MDC1-BL.5.3.8.3.6.2 | Task Dependent | Mechanical Corridor Finishes | 2021-01-13 07:00 | 2021-02-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 135 | 135 |  |  |  |  | MDC1.C3.C3120: FS, MDC1.C3.C3030: FS | MDC1.C3.C3290: FS, MDC1.C3.C3220: FS, MDC1-C3.P1900: FS, MDC1.C3.C3210: FS | PCI | 180 | 0 |  | ['739: FS', '1005: FS'] | ['504: FS', '598: FS', '367: FS', '597: FS']
656 | Not Started | MDC1-BL.5.3.8.4.6.4 | Task Dependent | Controls Installation | 2021-01-13 07:00 | 2021-02-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 67 | 67 |  |  |  |  | MDC1.C3.C3130: FS, MDC1.C3.C3100: FS | MDC1.C3.Cx2030: FS | VECA Electricians | 720 | 0 |  | ['740: FS', '824: FS'] | ['352: FS']
657 | Not Started | MDC1-BL.5.3.8.3.8.2 | Task Dependent | Mechanical Corridor Finishes | 2021-01-13 07:00 | 2021-02-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 135 | 135 |  |  |  |  | MDC1.C3.C4150: FS, MDC1.C3.C4030: FS | MDC1.C3.C4400: FS, MDC1.C3.C4250: FS, MDC1-C3.P1900: FS, MDC1.C3.C4240: FS | PCI | 180 | 0 |  | ['742: FS', '1008: FS'] | ['415: FS', '600: FS', '367: FS', '599: FS']
658 | Not Started | MDC1-BL.5.3.8.4.8.4 | Task Dependent | Controls Installation | 2021-01-13 07:00 | 2021-02-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 67 | 67 |  |  |  |  | MDC1.C3.C4160: FS, MDC1.C3.C4120: FS | MDC1.C3.Cx2050: FS | VECA Electricians | 720 | 0 |  | ['743: FS', '827: FS'] | ['354: FS']
659 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Lift & Set MER in Place | 2021-01-29 07:00 | 2021-02-03 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 1 | 1 |  |  |  |  | MDC1.C3.E1340: FS, MDC1.C3.E1120: FS, MDC1.C3.C1050: FS, MDC1-C3.P1600: FS, MDC1.C2.C4220: FS | MDC1.C3.C1240: FS, MDC1.C3.C1280: FS, MDC1.C3.C2260: FS | VECA Electricians | 120 | 0 |  | ['49: FS', '1032: FS', '1054: FS', '38: FS', '734: FS'] | ['641: FS', '614: FS', '635: FS']
660 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-01-20 08:00 | 2021-02-03 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 8 | 8 |  |  |  |  | MDC1.C2.C1380: FS, MDC1.C2.C1080: FS, MDC1.C2.C1290: FS | MDC1.C2.Cx2010: FS, MDC1.C2.C1460: FS | VECA Electricians | 960 | 0 |  | ['699: FS', '1122: FS', '812: FS'] | ['498: FS', '544: FS']
661 | Not Started | MDC1-BL.5.3.1.4.5.1 | Task Dependent | Ligthing Installation | 2021-01-20 07:00 | 2021-02-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 82 | 82 |  |  |  |  | MDC1.C1.C3420: FS, MDC1.C1.C1220: FS, MDC1.C1.C1310: FS | MDC1.C1.C4490: FS | VECA Electricians | 480 | 0 |  | ['700: FS', '1082: FS', '962: FS'] | ['610: FS']
662 | Not Started | MDC1-BL.5.3.1.4.7.1 | Task Dependent | Ligthing Installation | 2021-01-20 07:00 | 2021-02-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 70 | 70 |  |  |  |  | MDC1.C1.C3420: FS, MDC1.C1.C2200: FS, MDC1.C1.C2290: FS | MDC1.C1.C4480: FF, MDC1.C1.C4480: FS, MDC1.C1.C4490: FS | VECA Electricians | 480 | 0 |  | ['700: FS', '1088: FS', '967: FS'] | ['602: FF', '602: FS', '610: FS']
663 | Not Started | MDC1-BL.5.3.9.3.6.2 | Task Dependent | Mechanical Corridor Finishes | 2021-01-12 07:00 | 2021-02-02 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 14 | 14 |  |  |  |  | MDC1.C2.C3240: FS, MDC1.C2.C3100: FS | MDC1.C2.C3390: FS, MDC1.C2.C3410: FS, MDC1.C2.C3400: FS | PCI | 180 | 0 |  | ['751: FS', '1016: FS'] | ['603: FS', '605: FS', '604: FS']
664 | Not Started | MDC1-BL.5.3.9.3.8.2 | Task Dependent | Mechanical Corridor Finishes | 2021-01-12 07:00 | 2021-02-02 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 14 | 14 |  |  |  |  | MDC1.C2.C4180: FS, MDC1.C2.C4080: FS | MDC1.C2.C4410: FS, MDC1.C2.C4350: FS, MDC1.C2.C4340: FS | PCI | 180 | 0 |  | ['753: FS', '1019: FS'] | ['503: FS', '607: FS', '606: FS']
665 | Not Started | MDC1-BL.5.3.1.4.10.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-01-09 07:00 | 2021-02-02 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 61 | 61 |  |  |  |  | MDC1.C1.C1430: FS, MDC1.C1.C3380: FS | MDC1.C2.Cx4010: FS, MDC1.C1.Cx4000: FS, MDC1.C2.C1440: FS | LINX- TELECOM | 1440 | 0 |  | ['776: FS', '761: FS'] | ['263: FS', '295: FS', '571: FS']
666 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-01-21 07:00 | 2021-02-01 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C3270: FS, MDC1.C2.C3310: FS | MDC1.C2.C3380: FS, MDC1.C2.C3430: FS | VECA Electricians | 560 | 0 |  | ['732: FS', '696: FS'] | ['613: FS', '576: FS']
667 | Not Started | MDC1-BL.5.3.6.4.2.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2021-01-18 07:00 | 2021-01-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 75 | 75 |  |  |  |  | MDC1.C4.C3080: FS, MDC1.C4.E1240: FS, MDC1.C4.E1250: FS | MDC1.C4.C3390: FS, MDC1.C4.C3120: SS 5, MDC1.C4.C3370: FS, MDC1.C4.C3410: FS | TCM | 720 | 0 |  | ['721: FS', '147: FS', '148: FS'] | ['351: FS', '650: SS 5', '358: FS', '325: FS']
668 | Not Started | MDC1-BL.5.3.6.4.4.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2021-01-18 07:00 | 2021-01-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 75 | 75 |  |  |  |  | MDC1.C4.C4080: FS, MDC1.C4.E1260: FS, MDC1.C4.E1270: FS | MDC1.C4.C4390: FS, MDC1.C4.C4120: SS 5, MDC1.C4.C4360: FS, MDC1.C4.C4410: FS | TCM | 720 | 0 |  | ['724: FS', '151: FS', '152: FS'] | ['336: FS', '651: SS 5', '347: FS', '315: FS']
669 | Not Started | MDC1-BL.5.3.1.4.2.4 | Task Dependent | Controls Installation | 2021-01-11 07:00 | 2021-01-29 17:00 |  |  |  |  | 0 | 0 | 16 | 16 | 6 | 6 |  |  |  |  | MDC1.C1.C3080: FS, MDC1.C1.C3130: FS, MDC1.C1.C3180: FS, MDC1.C1.C3390: FS | MDC1.C1.Cx2030: FS | VECA Electricians | 640 | 0 |  | ['1179: FS', '1117: FS', '1047: FS', '758: FS'] | ['596: FS']
670 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Pull Conductors into Building | 2021-01-07 07:00 | 2021-01-29 17:00 |  |  |  |  | 0 | 0 | 19 | 19 | 0 | 0 |  |  |  |  | MDC1.C1.C2090: FS, MDC1.C1.C2430: FS | MDC1.C1.Cx2010: FS | VECA Electricians | 1440 | 0 |  | ['1221: FS', '773: FS'] | ['623: FS']
671 | Not Started | MDC1-BL.5.3.9.4.9.3 | Task Dependent | Controls Installation | 2021-01-15 07:00 | 2021-01-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C2.C1230: FS, MDC1.C2.C1240: FS, MDC1.C2.C1340: FS | MDC1.C2.C1420: FS, MDC1.C2.Cx2010: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0 |  | ['896: FS', '854: FS', '728: FS'] | ['648: FS', '498: FS', '31: FS']
672 | Not Started | MDC1-BL.5.3.9.4.10.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-01-15 07:00 | 2021-01-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C3280: FS | MDC1.C2.C3460: FS, MDC1.C2.Cx2100: FS, MDC1.C2.Cx2050: FS, MDC1.C2.C3370: FS | LINX- TELECOM | 1440 | 0 |  | ['729: FS'] | ['484: FS', '423: FS', '462: FS', '616: FS']
673 | Not Started | MDC1-BL.5.3.9.4.11.3 | Task Dependent | Controls Installation | 2021-01-15 07:00 | 2021-01-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C2.C2220: FS, MDC1.C2.C2240: FS, MDC1.C2.C2350: FS | MDC1.C2.C2400: FS, MDC1.C2.Cx2000: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0 |  | ['897: FS', '855: FS', '730: FS'] | ['649: FS', '500: FS', '31: FS']
674 | Not Started | MDC1-BL.5.3.9.4.13.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-01-15 07:00 | 2021-01-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C4230: FS | MDC1.C2.C4420: FS, MDC1.C2.Cx2070: FS, MDC1.C2.Cx2030: FS, MDC1.C2.C4330: FS | LINX- TELECOM | 1440 | 0 |  | ['731: FS'] | ['475: FS', '426: FS', '464: FS', '617: FS']
675 | Not Started | MDC1-BL.5.3.2.3.3 | Task Dependent | Ceilings / Ligthing / FA Devices | 2020-12-11 07:00 | 2021-01-28 17:00 |  |  |  |  | 0 | 0 | 36 | 36 | 43 | 43 |  |  |  |  | MDC1AD-1018: FS, MDC1AD-1024: FS, MDC1AD-1021: FS | MDC1AD-1029: FS, MDC1AD-1010: FS | PCI, VECA Electricians | 2800 | 0 |  | ['980: FS', '1156: FS', '900: FS'] | ['561: FS', '589: FS']
676 | Not Started | MDC1-BL.5.3.8.3.1.1 | Task Dependent | Hang Wall Partitions | 2021-01-20 07:00 | 2021-01-28 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 0 | 0 |  |  |  |  | MDC1.C3.CS1090: FS, MDC1.C3.C1210: SS 6 | MDC1.C3.C1260: FS, MDC1.C3.C1270: FS | PCI | 600 | 0 |  | ['1140: FS', '690: SS 6'] | ['619: FS', '621: FS']
677 | Not Started | MDC1-BL.5.3.8.3.3.1 | Task Dependent | Hang Wall Partitions | 2021-01-20 07:00 | 2021-01-28 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 0 | 0 |  |  |  |  | MDC1.C3.CS1090: FS, MDC1.C3.C2240: SS 6 | MDC1.C3.C2270: FS, MDC1.C3.C2280: FS | PCI | 600 | 0 |  | ['1140: FS', '691: SS 6'] | ['620: FS', '622: FS']
678 | Not Started | MDC1-BL.5.3.9.4.9.1 | Task Dependent | Pull / Term / Test Conductors | 2021-01-02 07:00 | 2021-01-27 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 31 | 31 |  |  |  |  | MDC1.C2.C1300: FS | MDC1.C2.Cx2010: FS | VECA Electricians | 1680 | 0 |  | ['797: FS'] | ['498: FS']
679 | Not Started | MDC1-BL.5.3.9.4.11.1 | Task Dependent | Pull / Term / Test Conductors | 2021-01-02 07:00 | 2021-01-27 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 25 | 25 |  |  |  |  | MDC1.C2.C2280: FS | MDC1.C2.C2400: FS, MDC1.C2.Cx2000: FS | VECA Electricians | 1680 | 0 |  | ['798: FS'] | ['649: FS', '500: FS']
680 | Not Started | MDC1-BL.5.3.8.4.6.2 | Task Dependent | Hydronic Piping Installation | 2021-01-13 07:00 | 2021-01-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C3.C3140: FS | MDC1.C3.Cx2030: FF | TCM | 480 | 0 |  | ['741: FS'] | ['352: FF']
681 | Not Started | MDC1-BL.5.3.8.4.8.2 | Task Dependent | Hydronic Piping Installation | 2021-01-13 07:00 | 2021-01-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C3.C4170: FS | MDC1.C3.Cx2050: FF | TCM | 480 | 0 |  | ['744: FS'] | ['354: FF']
682 | Not Started | MDC1-BL.5.3.6.3.5.1 | Task Dependent | OverHead MEPFP Rough-In | 2021-01-13 07:00 | 2021-01-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C3120: FS, MDC1.C4.C1010: FS | MDC1.C4.C1160: FS, MDC1.C4.C1170: FS, MDC1.C4.C3140: FS, MDC1.C4.C1150: FS, MDC1.C4.E1300: FS | TCM, VECA Electricians | 1360 | 0 |  | ['739: FS', '990: FS'] | ['629: FS', '630: FS', '573: FS', '628: FS', '89: FS']
683 | Not Started | MDC1-BL.5.3.6.3.7.1 | Task Dependent | OverHead MEPFP Rough-In | 2021-01-13 07:00 | 2021-01-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C4150: FS, MDC1.C4.C2010: FS | MDC1.C4.C2160: FS, MDC1.C4.C4140: FS, MDC1.C4.C2150: FS, MDC1.C4.C2170: FS, MDC1.C4.E1290: FS | TCM, VECA Electricians | 1360 | 0 |  | ['742: FS', '991: FS'] | ['633: FS', '575: FS', '632: FS', '634: FS', '75: FS']
684 | Not Started | MDC1-BL.5.3.2.4.5.4 | Task Dependent | Controls Installation | 2021-01-13 07:00 | 2021-01-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 8 | 8 |  |  |  |  | MDC1-1963: FS, MDC1-1964: FS, MDC1-1975: FS, MDC1-1968: FS | MDC1.C1.Cx2020: FS | VECA Electricians | 720 | 0 |  | ['1217: FS', '1071: FS', '993: FS', '745: FS'] | ['595: FS']
685 | Not Started | MDC1-BL.5.3.9.4.6.2 | Task Dependent | Hydronic Piping Installation | 2021-01-12 07:00 | 2021-01-26 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C2.C3250: FS | MDC1.C2.Cx2050: FF | TCM | 480 | 0 |  | ['752: FS'] | ['462: FF']
686 | Not Started | MDC1-BL.5.3.9.4.8.2 | Task Dependent | Hydronic Piping Installation | 2021-01-12 07:00 | 2021-01-26 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C2.C4190: FS | MDC1.C2.Cx2030: FF | TCM | 480 | 0 |  | ['754: FS'] | ['464: FF']
687 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-01-14 07:00 | 2021-01-26 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C2.C4220: FS | MDC1.C2.C4310: FS, MDC1.C2.C4380: FS |  | 0 | 0 |  | ['734: FS'] | ['643: FS', '556: FS']
688 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-01-14 07:00 | 2021-01-26 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C2330: FS, MDC1.C2.C2340: FS | MDC1.C2.C2420: FS, MDC1.C2.C4310: FS | VECA Electricians | 560 | 0 |  | ['774: FS', '733: FS'] | ['636: FS', '643: FS']
689 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Pull Conductors into Building | 2020-12-29 08:00 | 2021-01-25 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C1.C1090: FS, MDC1.C1.C1420: FS | MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS | VECA Electricians | 1440 | 0 |  | ['1218: FS', '818: FS'] | ['645: FS', '30: FS']
690 | Not Started | MDC1-BL.5.3.8.3.1.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-01-12 07:00 | 2021-01-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C3240: FS, MDC1.C3.C3060: FS, MDC1.C3.C1090: FS | MDC1.C3.C3180: FS, MDC1.C3.C1220: SS 6 | VECA Electricians | 1200 | 0 |  | ['751: FS', '958: FS', '996: FS'] | ['653: FS', '676: SS 6']
691 | Not Started | MDC1-BL.5.3.8.3.3.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-01-12 07:00 | 2021-01-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C4180: FS, MDC1.C3.C4060: FS, MDC1.C3.C2090: FS | MDC1.C3.C4220: FS, MDC1.C3.C2250: SS 6 | VECA Electricians | 1200 | 0 |  | ['753: FS', '959: FS', '997: FS'] | ['654: FS', '677: SS 6']
692 | Not Started | MDC1-BL.5.3.6.4.1.2 | Task Dependent | Mechanical Equipment Piping Connections | 2021-01-08 07:00 | 2021-01-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 77 | 77 |  |  |  |  | MDC1.C4.C1110: SS 5 | MDC1.C4.C1390: FS, MDC1.C4.Cx2000: FS | TCM | 720 | 0 |  | ['720: SS 5'] | ['375: FS', '312: FS']
693 | Not Started | MDC1-BL.5.3.6.4.3.2 | Task Dependent | Mechanical Equipment Piping Connections | 2021-01-08 07:00 | 2021-01-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 101 | 101 |  |  |  |  | MDC1.C4.C2110: SS 5 | MDC1.C4.Cx2010: FS | TCM | 720 | 0 |  | ['723: SS 5'] | ['298: FS']
694 | Not Started | MDC1-BL.5.3.1.4.3.4 | Task Dependent | Controls Installation | 2021-01-02 07:00 | 2021-01-21 17:00 |  |  |  |  | 0 | 0 | 16 | 16 | 7 | 7 |  |  |  |  | MDC1.C1.C2090: FS, MDC1.C1.C2120: FS, MDC1.C1.C2410: FS, MDC1.C1.C2420: FS | MDC1.C1.Cx2010: FS | VECA Electricians | 640 | 0 |  | ['1221: FS', '1185: FS', '813: FS', '796: FS'] | ['623: FS']
695 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-01-07 07:00 | 2021-01-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.C4090: FS, MDC1.C1.C4280: FS, MDC1.C1.C4370: FS | MDC1.C1.Cx2050: FS, MDC1.C1.C4470: FS | VECA Electricians | 960 | 0 |  | ['1180: FS', '871: FS', '775: FS'] | ['587: FS', '624: FS']
696 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-01-08 07:00 | 2021-01-20 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C3230: FS | MDC1.C2.C3340: FS, MDC1.C2.C3430: FS |  | 0 | 0 |  | ['770: FS'] | ['666: FS', '576: FS']
697 | Not Started | MDC1-BL.5.3.8.4.7.3 | Task Dependent | Floor Drain System Installation | 2021-01-06 07:00 | 2021-01-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 159 | 159 |  |  |  |  | MDC1.C3.C2030: FS, MDC1.C3.C2200: FS | MDC1-C3.P1900: FS |  | 0 | 0 |  | ['1079: FS', '779: FS'] | ['367: FS']
698 | Not Started | MDC1-BL.5.3.8.4.7.3 | Task Dependent | Toilet Piping Installation / DW | 2021-01-06 07:00 | 2021-01-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 159 | 159 |  |  |  |  | MDC1.C3.C2200: FS | MDC1-C3.P1900: FS | TCM | 480 | 0 |  | ['779: FS'] | ['367: FS']
699 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-01-07 08:00 | 2021-01-20 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C1290: FS, MDC1.C2.C1330: FS | MDC1.C2.C1410: FS, MDC1.C2.C1430: FS | VECA Electricians | 560 | 0 |  | ['812: FS', '772: FS'] | ['660: FS', '618: FS']
700 | Not Started | MDC1-BL.5.3.1.4.6.1 | Task Dependent | Ligthing Installation | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 70 | 70 |  |  |  |  | MDC1.C1.C3280: FS, MDC1.C1.C3370: FS | MDC1.C1.C2470: FS, MDC1.C1.C1470: FS, MDC1.C1.C4490: FS | VECA Electricians | 480 | 0 |  | ['918: FS', '781: FS'] | ['662: FS', '661: FS', '610: FS']
701 | Not Started | MDC1-BL.5.3.1.4.6.3 | Task Dependent | Floor Drain System Installation | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 94 | 94 |  |  |  |  | MDC1.C1.C3110: FS, MDC1.C1.C3370: FS | MDC1.C1.C4490: FS |  | 0 | 0 |  | ['1147: FS', '781: FS'] | ['610: FS']
702 | Not Started | MDC1-BL.5.3.1.4.6.3 | Task Dependent | Toilet Piping Installation / DW | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 94 | 94 |  |  |  |  | MDC1.C1.C3370: FS | MDC1.C1.C4490: FS | TCM | 480 | 0 |  | ['781: FS'] | ['610: FS']
703 | Not Started | MDC1-BL.5.3.1.4.8.3 | Task Dependent | Floor Drain System Installation | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 77 | 77 |  |  |  |  | MDC1.C1.C4110: FS, MDC1.C1.C4350: FS | MDC1-C1.P1900: FS, MDC1.C1.C4490: FS |  | 0 | 0 |  | ['1150: FS', '782: FS'] | ['566: FS', '610: FS']
704 | Not Started | MDC1-BL.5.3.1.4.8.3 | Task Dependent | Toilet Piping Installation / DW | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 77 | 77 |  |  |  |  | MDC1.C1.C4350: FS | MDC1-C1.P1900: FS, MDC1.C1.C4490: FS | TCM | 480 | 0 |  | ['782: FS'] | ['566: FS', '610: FS']
705 | Not Started | MDC1-BL.5.3.9.4.5.1 | Task Dependent | Ligthing Installation | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 124 | 124 |  |  |  |  | MDC1.C2.C1150: FS, MDC1.C2.C1310: FS | MDC1.C2.C3390: FS | VECA Electricians | 480 | 0 |  | ['1029: FS', '783: FS'] | ['603: FS']
706 | Not Started | MDC1-BL.5.3.9.4.5.3 | Task Dependent | Floor Drain System Installation | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1.C2.C1100: FS, MDC1.C2.C1310: FS | MDC1-C2.P1800: FS, MDC1.C3.C1250: FS |  | 0 | 0 |  | ['1092: FS', '783: FS'] | ['594: FS', '637: FS']
707 | Not Started | MDC1-BL.5.3.9.4.5.3 | Task Dependent | Toilet Piping Installation / DW | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1.C2.C1310: FS | MDC1-C2.P1800: FS | TCM | 480 | 0 |  | ['783: FS'] | ['594: FS']
708 | Not Started | MDC1-BL.5.3.9.4.6.4 | Task Dependent | Controls Installation | 2020-12-23 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 48 | 48 |  |  |  |  | MDC1.C2.C3140: FS, MDC1.C2.C3200: FS | MDC1.C2.Cx2050: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0 |  | ['947: FS', '838: FS'] | ['462: FS', '31: FS']
709 | Not Started | MDC1-BL.5.3.9.4.7.3 | Task Dependent | Floor Drain System Installation | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1.C2.C2080: SS 6, MDC1.C2.C2300: FS | MDC1-C2.P1800: FS |  | 0 | 0 |  | ['1094: SS 6', '785: FS'] | ['594: FS']
710 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-01-14 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 8 | 8 |  |  |  |  | MDC1.C2.C4040: FS, MDC1.C2.C4220: FS, MDC1.C2.C2330: FS | MDC1.C2.C4310: FS, MDC1.C2.C4370: FS, MDC1.C2.C4380: FS, MDC1.S.1900: FS | SURE STEEL | 160 | 0 |  | ['1125: FS', '734: FS', '774: FS'] | ['643: FS', '577: FS', '556: FS', '257: FS']
711 | Not Started | MDC1-BL.5.3.9.4.8.4 | Task Dependent | Controls Installation | 2020-12-23 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 43 | 43 |  |  |  |  | MDC1.C2.C4160: FS | MDC1.C2.Cx2030: FS 5, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0 |  | ['841: FS'] | ['464: FS 5', '31: FS']
712 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 82 | 82 |  |  |  |  | MDC1.C4.C3060: FS, MDC1.C4.E1180: FS, MDC1.C4.E1190: FS | MDC1.C4.C3380: FS, MDC1.C4.C3390: FS, MDC1.C4.C3440: FS, MDC1.C4.C3370: FS, MDC1.C4.C3410: FS | VECA Electricians | 480 | 0 |  | ['790: FS', '177: FS', '178: FS'] | ['350: FS', '351: FS', '304: FS', '358: FS', '325: FS']
713 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 84 | 84 |  |  |  |  | MDC1.C4.C4060: FS, MDC1.C4.E1200: FS, MDC1.C4.E1210: FS | MDC1.C4.C4370: FS, MDC1.C4.C4390: FS, MDC1.C4.C4440: FS, MDC1.C4.C4360: FS, MDC1.C4.C4410: FS | VECA Electricians | 480 | 0 |  | ['792: FS', '181: FS', '182: FS'] | ['339: FS', '336: FS', '299: FS', '347: FS', '315: FS']
714 | Not Started | MDC1-BL.5.3.1.4.9.1 | Task Dependent | Light Fixtures Installation | 2021-01-11 07:00 | 2021-01-18 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 78 | 78 |  |  |  |  | MDC1.C1.C3400: FS, MDC1.C1.C1400: FS, MDC1.C1.C1340: FF, MDC1.C1.C1340: FS, MDC1.C1.C1270: FS | MDC1-C1.P1900: FS, MDC1-C1.P1900: SS | VECA Electricians | 480 | 0 |  | ['759: FS', '861: FS', '965: FF', '965: FS', '1034: FS'] | ['566: FS', '566: SS']
715 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2020-12-23 07:00 | 2021-01-18 17:00 |  |  |  |  | 0 | 0 | 17 | 17 | 4 | 4 |  |  |  |  | MDC1.C1.C4120: FS, MDC1.C1.C4090: FS, MDC1.C1.C4280: FS, MDC1.C1.C4340: FS | MDC1.C1.C4450: FS | VECA Electricians | 1080 | 0 |  | ['1132: FS', '1180: FS', '871: FS', '835: FS'] | ['647: FS']
716 | Not Started | MDC1-BL.5.3.1.4.1.4 | Task Dependent | Controls Installation | 2020-12-23 08:00 | 2021-01-18 08:00 |  |  |  |  | 0 | 0 | 16 | 16 | 6 | 6 |  |  |  |  | MDC1.C1.C1090: FS, MDC1.C1.C1110: FS, MDC1.C1.C1160: FS, MDC1.C1.C1410: FS | MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS | VECA Electricians | 640 | 0 |  | ['1218: FS', '1207: FS', '1159: FS', '831: FS'] | ['645: FS', '30: FS']
717 | Not Started | MDC1-BL.5.3.9.4.10.1 | Task Dependent | PDU's Installation | 2021-01-13 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 13 | 13 |  |  |  |  | MDC1.C2.C3260: FS, MDC1.C2.C3210: FS, MDC1.C2.C3130: FS, MDC1.C2.E1420: FS, MDC1.C2.E1430: FS | MDC1.C2.C3360: FS, MDC1.C2.C3420: FS | VECA Electricians | 180 | 0 |  | ['748: FS', '815: FS', '946: FS', '195: FS', '196: FS'] | ['625: FS', '592: FS']
718 | Not Started | MDC1-BL.5.3.9.4.13.1 | Task Dependent | PDU's Installation | 2021-01-13 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 13 | 13 |  |  |  |  | MDC1.C2.C4210: FS, MDC1.C2.E1440: FS, MDC1.C2.E1450: FS, MDC1.C2.C4110: FS | MDC1.C2.C4320: FS, MDC1.C2.C4360: FS | VECA Electricians | 180 | 0 |  | ['749: FS', '199: FS', '200: FS', '950: FS'] | ['626: FS', '593: FS']
719 | Not Started | MDC1-BL.5.3.8.4.4.4 | Task Dependent | Fire Alarm Installation | 2021-01-02 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 70 | 70 |  |  |  |  | MDC1.C3.C4130: FS, MDC1.C3.C4100: FS | MDC1.C3.C4410: FS | VECA Electricians | 240 | 0 |  | ['800: FS', '875: FS'] | ['400: FS']
720 | Not Started | MDC1-BL.5.3.6.4.1.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2021-01-02 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C4.C1080: FS, MDC1.C4.E1140: FS, MDC1.C4.E1150: FS, MDC1-C4.P1700: FS | MDC1.C4.C1340: FS, MDC1.C4.C1120: SS 5, MDC1.C4.C1390: FS, MDC1.C4.C1410: FS | TCM | 720 | 0 |  | ['801: FS', '145: FS', '146: FS', '41: FS'] | ['418: FS', '692: SS 5', '375: FS', '343: FS']
721 | Not Started | MDC1-BL.5.3.6.4.2.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2021-01-12 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 75 | 75 |  |  |  |  | MDC1.C4.C3070: FS | MDC1.C4.C3110: FS, MDC1.C4.E1240: FS | SURE STEEL | 160 | 0 |  | ['755: FS'] | ['667: FS', '147: FS']
722 | Not Started | MDC1-BL.5.3.6.4.6.4 | Task Dependent | Fire Alarm System | 2021-01-02 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 98 | 98 |  |  |  |  | MDC1.C4.C3050: FS | MDC1.C4.C3250: FS | VECA Electricians | 240 | 0 |  | ['803: FS'] | ['450: FS']
723 | Not Started | MDC1-BL.5.3.6.4.3.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2021-01-02 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C4.C2080: FS, MDC1.C4.E1160: FS, MDC1.C4.E1170: FS | MDC1.C4.C2360: FS, MDC1.C4.C2120: SS 5, MDC1.C4.C2400: FS, MDC1.C4.C2430: FS | TCM | 720 | 0 |  | ['804: FS', '149: FS', '150: FS'] | ['396: FS', '693: SS 5', '356: FS', '320: FS']
724 | Not Started | MDC1-BL.5.3.6.4.4.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2021-01-12 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 75 | 75 |  |  |  |  | MDC1.C4.C4070: FS | MDC1.C4.C4110: FS, MDC1.C4.E1260: FS | SURE STEEL | 160 | 0 |  | ['756: FS'] | ['668: FS', '151: FS']
725 | Not Started | MDC1-BL.5.3.6.4.8.4 | Task Dependent | Fire Alarm System | 2021-01-02 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 98 | 98 |  |  |  |  | MDC1.C4.C4050: FS | MDC1.C4.C4240: FS | VECA Electricians | 240 | 0 |  | ['806: FS'] | ['452: FS']
726 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -4 WEST UPMS | 2021-01-09 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 0 | 0 |  |  |  |  | MDC1.S.1750: FS, MDC1.S.1710: FS, MDC1.S.1800: FS | MDC1.S.1850: FF, MDC1.S.1850: FS, MDC1.S.1840: FS | VECA Electricians | 360 | 0 |  | ['793: FS', '808: FS', '766: FS'] | ['601: FF', '601: FS', '611: FS']
727 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term- UMS- Load side | 2021-01-02 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.S.1740: FS, MDC1.S.1630: FS, MDC1.S.1650: FS, MDC1.S.1730: FS | MDC1.S.1850: FS | VECA Electricians | 720 | 0 |  | ['811: FS', '898: FS', '880: FS', '810: FS'] | ['601: FS']
728 | Not Started | MDC1-BL.5.3.9.4.9.2 | Task Dependent | BMS Pull Wire / Term / Test | 2020-12-30 07:00 | 2021-01-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C2.C1280: FS | MDC1.C2.C1440: FS, MDC1.C2.Cx2040: FS, MDC1.C2.Cx2010: FS, MDC1.C2.C1400: FS | LINX- TELECOM | 1440 | 0 |  | ['814: FS'] | ['571: FS', '461: FS', '498: FS', '671: FS']
729 | Not Started | MDC1-BL.5.3.9.4.10.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-12-30 07:00 | 2021-01-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C3210: FS | MDC1.C2.C3330: FS | LINX- TELECOM | 1440 | 0 |  | ['815: FS'] | ['672: FS']
730 | Not Started | MDC1-BL.5.3.9.4.11.2 | Task Dependent | BMS Pull Wire / Term / Test | 2020-12-30 07:00 | 2021-01-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C2.C2270: FS | MDC1.C2.C2450: FS, MDC1.C2.Cx2020: FS, MDC1.C2.Cx2000: FS, MDC1.C2.C2390: FS | LINX- TELECOM | 1440 | 0 |  | ['816: FS'] | ['558: FS', '463: FS', '500: FS', '673: FS']
731 | Not Started | MDC1-BL.5.3.9.4.13.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-12-30 07:00 | 2021-01-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C4170: FS | MDC1.C2.C4290: FS | LINX- TELECOM | 1440 | 0 |  | ['817: FS'] | ['674: FS']
732 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-01-08 07:00 | 2021-01-13 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 5 | 5 |  |  |  |  | MDC1.C2.C3050: FS, MDC1.C2.C3230: FS, MDC1.C2.C1290: FS | MDC1.C2.C3340: FS, MDC1.C2.C3380: FS, MDC1.C2.C3430: FS | SURE STEEL | 160 | 0 |  | ['1123: FS', '770: FS', '812: FS'] | ['666: FS', '613: FS', '576: FS']
733 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-01-02 07:00 | 2021-01-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C2290: FS | MDC1.C2.C2370: FS, MDC1.C2.C2410: FS |  | 0 | 0 |  | ['807: FS'] | ['688: FS', '642: FS']
734 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Lift & Set MER in Place | 2021-01-08 07:00 | 2021-01-13 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 2 | 2 |  |  |  |  | MDC1.C2.E1410: FS, MDC1.C2.E1200: FS, MDC1.C2.C4040: FS, MDC1.C2.C3230: FS | MDC1.C2.C4250: FS, MDC1.C2.C4280: FS, MDC1.C3.C1230: FS | VECA Electricians | 120 | 0 |  | ['48: FS', '1104: FS', '1125: FS', '770: FS'] | ['710: FS', '687: FS', '659: FS']
735 | Not Started | MDC1-BL.5.3.1.4.11.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2020-12-16 07:00 | 2021-01-13 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C1.C2370: FS | MDC1.C2.Cx4010: FS, MDC1.C1.Cx4000: FS, MDC1.C1.C4460: FS | LINX- TELECOM | 1440 | 0 |  | ['870: FS'] | ['263: FS', '295: FS', '644: FS']
736 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2020-12-28 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.C3350: FS, MDC1.C1.C3080: FS, MDC1.C1.C3250: FS | MDC1.C1.Cx2030: FS, MDC1.C1.C3470: FS | VECA Electricians | 960 | 0 |  | ['828: FS', '1179: FS', '945: FS'] | ['596: FS', '646: FS']
737 | Not Started | MDC1-BL.5.3.1.4.13.1 | Task Dependent | Light Fixtures Installation | 2021-01-06 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 82 | 82 |  |  |  |  | MDC1.C1.C4360: FS, MDC1.C1.C4300: FS, MDC1.C1.C4220: FS | MDC1.C1.C4400: FS, MDC1-C1.P1900: FS | VECA Electricians | 480 | 0 |  | ['777: FS', '873: FS', '941: FS'] | ['747: FS', '566: FS']
738 | Not Started | MDC1-BL.5.3.9.4.13.3 | Task Dependent | Fire Alarm System | 2020-12-30 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 25 | 25 |  |  |  |  | MDC1.C2.C4170: FS | MDC1.C2.C4330: FS, MDC1-C2.P1900: FS | VECA Electricians | 600 | 0 |  | ['817: FS'] | ['617: FS', '31: FS']
739 | Not Started | MDC1-BL.5.3.8.3.6.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-12-28 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C3090: FF, MDC1.C3.C3090: FS | MDC1.C4.C1130: FS, MDC1.C3.C3160: FS | VECA Electricians | 960 | 0 |  | ['823: FF', '823: FS'] | ['682: FS', '655: FS']
740 | Not Started | MDC1-BL.5.3.8.4.6.1 | Task Dependent | VFD'S Installation & Wiring | 2020-12-28 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 67 | 67 |  |  |  |  | MDC1.C3.C3090: FS | MDC1.C3.C3290: FS, MDC1.C3.C3170: FS, MDC1.C3.Cx3020: FS | VECA Electricians | 240 | 0 |  | ['823: FS'] | ['504: FS', '656: FS', '275: FS']
741 | Not Started | MDC1-BL.5.3.8.4.6.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-12-28 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C3.C3090: FS, MDC1.C3.E1300: FS, MDC1.C3.E1320: FS | MDC1.C3.C3150: FS | TCM | 480 | 0 |  | ['823: FS', '70: FS', '86: FS'] | ['680: FS']
742 | Not Started | MDC1-BL.5.3.8.3.8.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-12-28 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C4110: FS | MDC1.C4.C2130: FS, MDC1.C3.C4200: FS | VECA Electricians | 960 | 0 |  | ['826: FS'] | ['683: FS', '657: FS']
743 | Not Started | MDC1-BL.5.3.8.4.8.1 | Task Dependent | VFD'S Installation & Wiring | 2020-12-28 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 67 | 67 |  |  |  |  | MDC1.C3.C4110: FS | MDC1.C3.C4400: FS, MDC1.C3.C4210: FS, MDC1.C3.Cx3020: FS | VECA Electricians | 240 | 0 |  | ['826: FS'] | ['415: FS', '658: FS', '275: FS']
744 | Not Started | MDC1-BL.5.3.8.4.8.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-12-28 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C3.C4110: FS, MDC1.C3.E1310: FS, MDC1.C3.E1330: FS | MDC1.C3.C4190: FS | TCM | 480 | 0 |  | ['826: FS', '72: FS', '88: FS'] | ['681: FS']
745 | Not Started | MDC1-BL.5.3.2.4.5.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2020-12-15 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 8 | 8 |  |  |  |  | MDC1AD-1019: FS, MDC1-1963: FS | MDC1-1976: FS | VECA Electricians | 1080 | 0 |  | ['882: FS', '1217: FS'] | ['684: FS']
746 | Not Started | MDC1-BL.5.3.2.4.5.1 | Task Dependent | Pull Conductors into Building | 2020-12-15 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 20 | 20 |  |  |  |  | MDC1AD-1019: FS, MDC1-1963: FS | MDC1.AD.Cx2000: FS 10 | VECA Electricians | 1440 | 0 |  | ['882: FS', '1217: FS'] | ['640: FS 10']
747 | Not Started | MDC1-BL.5.3.1.4.13.3 | Finish Milestone | Data Hall complete |  | 2021-01-12 17:00 |  |  | 2021-01-12 17:00 |  | 0 | 0 | 0 | 0 | 94 | 94 |  |  |  |  | MDC1.C1.C4390: FS, MDC1.C1.C2400: FS, MDC1.C1.C3400: FS, MDC1.C1.C4380: FS | MDC1.C1.Cx3050: FS, MDC1.C1.Cx4020: FS |  | 0 | 0 |  | ['737: FS', '821: FS', '759: FS', '750: FS'] | ['346: FS', '267: FS']
748 | Not Started | MDC1-BL.5.3.9.4.10.1 | Task Dependent | Power Bus Installation | 2020-12-30 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 13 | 13 |  |  |  |  | MDC1.C2.C3210: FS, MDC1.C2.C3170: FS | MDC1.C2.C3290: FS, MDC1.C2.E1420: FS | VECA Electricians | 1200 | 0 |  | ['815: FS', '914: FS'] | ['717: FS', '195: FS']
749 | Not Started | MDC1-BL.5.3.9.4.13.1 | Task Dependent | Power Bus Installation | 2020-12-30 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 13 | 13 |  |  |  |  | MDC1.C2.C4170: FS | MDC1.C2.C4240: FS, MDC1.C2.E1440: FS | VECA Electricians | 1200 | 0 |  | ['817: FS'] | ['718: FS', '199: FS']
750 | Not Started | MDC1-BL.5.3.1.4.13.2 | Task Dependent | BMS Pull Wire / Term / Test | 2020-12-23 07:00 | 2021-01-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 25 | 25 |  |  |  |  | MDC1.C1.C4330: FS, MDC1.C1.C4180: FS | MDC1.C1.C4460: FS, MDC1.C1.Cx2100: FS, MDC1.C1.Cx2050: FS, MDC1.C1.C4400: FS | LINX- TELECOM | 1440 | 0 |  | ['834: FS', '1040: FS'] | ['644: FS', '542: FS', '587: FS', '747: FS']
751 | Not Started | MDC1-BL.5.3.9.3.6.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-12-23 07:00 | 2021-01-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C3190: FS, MDC1.C2.C3190: SS 5 | MDC1.C3.C1210: FS, MDC1.C2.C3350: FS | VECA Electricians | 960 | 0 |  | ['837: FS', '837: SS 5'] | ['690: FS', '663: FS']
752 | Not Started | MDC1-BL.5.3.9.4.6.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-12-23 07:00 | 2021-01-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C2.C3090: FS, MDC1.C2.E1320: FS, MDC1.C2.E1340: FS | MDC1.C2.C3320: FS | TCM | 480 | 0 |  | ['1042: FS', '66: FS', '82: FS'] | ['685: FS']
753 | Not Started | MDC1-BL.5.3.9.3.8.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-12-23 07:00 | 2021-01-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C4150: FS, MDC1.C2.C4150: SS 5 | MDC1.C3.C2240: FS, MDC1.C2.C4300: FS | VECA Electricians | 960 | 0 |  | ['840: FS', '840: SS 5'] | ['691: FS', '664: FS']
754 | Not Started | MDC1-BL.5.3.9.4.8.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-12-23 07:00 | 2021-01-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C2.C4070: FS, MDC1.C2.E1330: FS, MDC1.C2.E1350: FS | MDC1.C2.C4270: FS | TCM | 480 | 0 |  | ['1043: FS', '68: FS', '84: FS'] | ['686: FS']
755 | Not Started | MDC1-BL.5.3.6.4.2.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-12-23 07:00 | 2021-01-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 75 | 75 |  |  |  |  | MDC1.C4.C3060: SS 6, MDC1.C4.C3000: FS | MDC1.C4.C3080: FS | CSI, VECA Electricians | 1440 | 0 |  | ['790: SS 6', '1098: FS'] | ['721: FS']
756 | Not Started | MDC1-BL.5.3.6.4.4.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-12-23 07:00 | 2021-01-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 75 | 75 |  |  |  |  | MDC1.C4.C4060: SS 6, MDC1.C4.C4000: FS | MDC1.C4.C4080: FS | CSI, VECA Electricians | 1440 | 0 |  | ['792: SS 6', '932: FS'] | ['724: FS']
757 | Not Started | MDC1-BL.5.3.2.4.4 | Task Dependent | Mechanical Devices & Trim | 2020-12-15 07:00 | 2021-01-09 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 32 | 32 |  |  |  |  | MDC1AD-1019: FS, MDC1AD-1021: FS | MDC1.AD.Cx2000: FS | TCM | 360 | 0 |  | ['882: FS', '900: FS'] | ['640: FS']
758 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2020-12-12 07:00 | 2021-01-09 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 6 | 6 |  |  |  |  | MDC1.C1.C3130: FS, MDC1.C1.C3080: FS, MDC1.C1.C3250: FS, MDC1.C1.C3300: FS | MDC1.C1.C3450: FS | VECA Electricians | 1080 | 0 |  | ['1117: FS', '1179: FS', '945: FS', '895: FS'] | ['669: FS']
759 | Not Started | MDC1-BL.5.3.1.4.10.1 | Task Dependent | Light Fixtures Installation | 2021-01-04 07:00 | 2021-01-09 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 78 | 78 |  |  |  |  | MDC1.C1.C3360: FS, MDC1.C1.C3310: FS, MDC1.C1.C3240: FS | MDC1.C1.C1450: FS, MDC1.C1.C4400: FS, MDC1-C1.P1900: FS | VECA Electricians | 480 | 0 |  | ['794: FS', '885: FS', '954: FS'] | ['714: FS', '747: FS', '566: FS']
760 | Not Started | MDC1-BL.4.10.2.1.4 | Finish Milestone | Pad Ready for MER COLO-4 Cell-4 |  | 2021-01-09 17:00 |  |  | 2021-01-09 17:00 |  | 0 | 0 | 0 | 0 | 66 | 66 |  |  |  |  | MDC1.C4.C4060: FS 5 | MDC1.C4.C4250: FS |  | 0 | 0 |  | ['792: FS 5'] | ['441: FS']
761 | Not Started | MDC1-BL.5.3.1.4.10.2 | Task Dependent | BMS Pull Wire / Term / Test | 2020-12-21 07:00 | 2021-01-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C1.C3190: FS, MDC1.C1.C3330: FS | MDC1.C1.C3460: FS, MDC1.C1.Cx2070: FS, MDC1.C1.Cx2030: FS | LINX- TELECOM | 1440 | 0 |  | ['1048: FS', '851: FS'] | ['665: FS', '560: FS', '596: FS']
762 | Not Started | MDC1-BL.4.10.2.1.4 | Finish Milestone | Pad Ready for MER COLO-4 Cell-3 |  | 2021-01-08 17:00 |  |  | 2021-01-08 17:00 |  | 0 | 0 | 0 | 0 | 62 | 62 |  |  |  |  | MDC1.C4.C3060: FS 4 | MDC1.C4.C3210: FS |  | 0 | 0 |  | ['790: FS 4'] | ['465: FS']
763 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | PULL- URS to COLO-4 | 2021-01-05 07:00 | 2021-01-08 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.C4.C4040: FS, MDC1.C4.C2040: FS, MDC1.C4.C3040: FS, MDC1.C4.C1040: FS, MDC1.S.1140: FS, MDC1.S.1180: FS, MDC1.S.1460: FS, MDC1.S.1670: FS, MDC1.S.1580: FS, MDC1.S.1200: FS, MDC1.S.1640: FS, MDC1.S.1750: FS, MDC1-1996: FS | MDC1.S.1790: FF | VECA Electricians | 240 | 0 |  | ['820: FS', '902: FS', '819: FS', '901: FS', '1237: FS', '1213: FS', '1046: FS', '863: FS', '952: FS', '1206: FS', '884: FS', '793: FS', '1134: FS'] | ['765: FF']
764 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -4 East UPMS | 2021-01-02 07:00 | 2021-01-08 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 6 | 6 |  |  |  |  | MDC1.S.1720: FS, MDC1.S.1710: FS, MDC1.S.1660: FS | MDC1.S.1850: FS, MDC1.S.1840: FS | VECA Electricians | 360 | 0 |  | ['809: FS', '808: FS', '881: FS'] | ['601: FS', '611: FS']
765 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | TERM- URS- Load Side | 2020-12-21 07:00 | 2021-01-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.S.1770: FF, MDC1.S.1640: FS, MDC1.S.1500: FS, MDC1.S.1480: FS | MDC1.S.1850: FS, MDC1.S.1840: SS 4, MDC1.S.1800: FF | VECA Electricians | 720 | 0 |  | ['763: FF', '884: FS', '1000: FS', '1039: FS'] | ['601: FS', '611: SS 4', '766: FF']
766 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term- JAZ to Structure- (Incl Stress Cones) from ums | 2020-12-28 07:00 | 2021-01-08 17:00 |  |  |  |  | 0 | 0 | 9 | 9 | 0 | 0 |  |  |  |  | MDC1.S.1700: FS, MDC1.S.1690: FS, MDC1.S.1790: FF | MDC1.S.1850: FS, MDC1.S.1840: FS, MDC1.S.1810: FS | VECA Electricians | 360 | 0 |  | ['844: FS', '849: FS', '765: FF'] | ['601: FS', '611: FS', '726: FS']
767 | Not Started | MDC1-BL.5.3.9.4.10.3 | Task Dependent | Fire Alarm System | 2020-12-22 07:00 | 2021-01-07 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 29 | 29 |  |  |  |  | MDC1.C2.C3210: FF 6 | MDC1.C2.C3370: FS | VECA Electricians | 600 | 0 |  | ['815: FF 6'] | ['616: FS']
768 | Not Started | MDC1-BL.5.3.8.4.1.4 | Task Dependent | Fire Alarm Installation | 2020-12-19 07:00 | 2021-01-07 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 67 | 67 |  |  |  |  | MDC1.C3.C1160: FS, MDC1.C3.C1110: FS, MDC1.C3.C1170: FS | MDC1.C3.C1400: FS, MDC1-C3.P1800: FS | VECA Electricians | 240 | 0 |  | ['888: FS', '972: FS', '856: FS'] | ['476: FS', '32: FS']
769 | Not Started | MDC1-BL.5.3.8.4.4.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-12-19 07:00 | 2021-01-07 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 89 | 89 |  |  |  |  | MDC1.C3.C4130: SS 5 | MDC1.C3.Cx2050: FS | TCM | 720 | 0 |  | ['800: SS 5'] | ['354: FS']
770 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Lift & Set MER in Place | 2021-01-02 07:00 | 2021-01-07 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C2.C3050: FS, MDC1.C2.E1210: FS, MDC1.C2.E1360: FS, MDC1.C2.C2290: FS | MDC1.C2.C3310: FS, MDC1.C2.C3270: FS, MDC1.C2.C4220: FS | VECA Electricians | 120 | 0 |  | ['1123: FS', '1102: FS', '47: FS', '807: FS'] | ['696: FS', '732: FS', '734: FS']
771 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term- JUMS to URS- (Incl Stress Cones) | 2020-12-23 07:00 | 2021-01-07 17:00 |  |  |  |  | 0 | 0 | 9 | 9 | 7 | 7 |  |  |  |  | MDC1.S.1600: FS, MDC1.S.1700: FS | MDC1.S.1850: FS, MDC1.S.1840: FS | VECA Electricians | 360 | 0 |  | ['934: FS', '844: FS'] | ['601: FS', '611: FS']
772 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2020-12-21 08:00 | 2021-01-07 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C1250: FS | MDC1.C2.C1380: FS, MDC1.C2.C1430: FS |  | 0 | 0 |  | ['850: FS'] | ['699: FS', '618: FS']
773 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2020-12-18 07:00 | 2021-01-06 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.C2390: FS, MDC1.C1.C2090: FS, MDC1.C1.C2280: FS | MDC1.C1.Cx2010: FS, MDC1.C1.C2460: FS | VECA Electricians | 960 | 0 |  | ['860: FS', '1221: FS', '984: FS'] | ['623: FS', '670: FS']
774 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-01-02 07:00 | 2021-01-06 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 6 | 6 |  |  |  |  | MDC1.C2.C2030: FS, MDC1.C2.C2290: FS | MDC1.C2.C2370: FS, MDC1.C2.C2420: FS, MDC1.C2.C2410: FS, MDC1.C2.C4250: FS | SURE STEEL | 160 | 0 |  | ['1183: FS', '807: FS'] | ['688: FS', '636: FS', '642: FS', '710: FS']
775 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2020-12-23 07:00 | 2021-01-06 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 0 | 0 |  |  |  |  | MDC1.C1.C4280: FS, MDC1.C1.C4340: FS, MDC1.C1.C2390: FS | MDC1.C1.C4440: FS | VECA Electricians | 560 | 0 |  | ['871: FS', '835: FS', '860: FS'] | ['695: FS']
776 | Not Started | MDC1-BL.5.3.1.4.9.2 | Task Dependent | Install Production Fiber (Includes MOR rack set & Fiber runner) | 2020-12-09 07:00 | 2021-01-06 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 63 | 63 |  |  |  |  | MDC1.C1.C1390: SS 6, MDC1.C1.C1330: SS 6 | MDC1.C1.Cx4000: FS, MDC1.C1.C3460: FS | LINX- TELECOM | 1440 | 0 |  | ['866: SS 6', '964: SS 6'] | ['295: FS', '665: FS']
777 | Not Started | MDC1-BL.5.3.1.4.13.1 | Task Dependent | Pull / Term / Test Conductors | 2020-12-07 07:00 | 2021-01-05 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 30 | 30 |  |  |  |  | MDC1.C1.C4220: FS | MDC1.C1.C4390: FS, MDC1.C1.Cx2050: FS | VECA Electricians | 1680 | 0 |  | ['941: FS'] | ['737: FS', '587: FS']
778 | Not Started | MDC1-BL.5.3.8.4.5.4 | Task Dependent | Controls Installation | 2020-12-10 07:00 | 2021-01-05 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 81 | 81 |  |  |  |  | MDC1.C3.C1130: FS, MDC1.C3.C1150: FS | MDC1.C3.Cx2000: FS, MDC1-C3.P1800: FS | VECA Electricians | 720 | 0 |  | ['905: FS', '907: FS'] | ['389: FS', '32: FS']
779 | Not Started | MDC1-BL.5.3.8.3.7.2 | Task Dependent | Mechanical Corridor Finishes | 2020-12-10 07:00 | 2021-01-05 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 156 | 156 |  |  |  |  | MDC1.C3.C2120: FS, MDC1.C3.C2030: FS | MDC1.C3.C2410: FS, MDC1.C3.C2230: FS, MDC1-C3.P1900: FS, MDC1.C3.C2220: FS | PCI | 180 | 0 |  | ['909: FS', '1079: FS'] | ['454: FS', '698: FS', '367: FS', '697: FS']
780 | Not Started | MDC1-BL.5.3.8.4.7.4 | Task Dependent | Controls Installation | 2020-12-10 07:00 | 2021-01-05 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 81 | 81 |  |  |  |  | MDC1.C3.C2130: FS, MDC1.C3.C2150: FS | MDC1.C3.Cx2010: FS | VECA Electricians | 720 | 0 |  | ['910: FS', '912: FS'] | ['380: FS']
781 | Not Started | MDC1-BL.5.3.1.3.6.2 | Task Dependent | Mechanical Corridor Finishes | 2020-12-09 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 70 | 70 |  |  |  |  | MDC1.C1.C3270: FS, MDC1.C1.C3110: SS | MDC1.C1.C3420: FS, MDC1.C1.C3440: FS, MDC1.C1.C3430: FS | PCI | 180 | 0 |  | ['917: FS', '1147: SS'] | ['700: FS', '702: FS', '701: FS']
782 | Not Started | MDC1-BL.5.3.1.3.8.2 | Task Dependent | Mechanical Corridor Finishes | 2020-12-09 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 77 | 77 |  |  |  |  | MDC1.C1.C4230: FS, MDC1.C1.C4110: SS | MDC1.C1.C4480: FS, MDC1.C1.C4430: FS, MDC1.C1.C4420: FS | PCI | 180 | 0 |  | ['920: FS', '1150: SS'] | ['602: FS', '704: FS', '703: FS']
783 | Not Started | MDC1-BL.5.3.9.3.5.2 | Task Dependent | Mechanical Corridor Finishes | 2020-12-09 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 38 | 38 |  |  |  |  | MDC1.C2.C1200: FS, MDC1.C2.C1100: FS | MDC1.C2.C1350: FS, MDC1.C2.C1370: FS, MDC1.C2.C1360: FS | PCI | 180 | 0 |  | ['923: FS', '1092: FS'] | ['705: FS', '707: FS', '706: FS']
784 | Not Started | MDC1-BL.5.3.9.4.5.4 | Task Dependent | Controls Installation | 2020-12-09 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 50 | 50 |  |  |  |  | MDC1.C2.C1150: FS, MDC1.C2.C1220: FS | MDC1.C2.Cx2010: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0 |  | ['1029: FS', '925: FS'] | ['498: FS', '31: FS']
785 | Not Started | MDC1-BL.5.3.9.3.7.2 | Task Dependent | Mechanical Corridor Finishes | 2020-12-09 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 38 | 38 |  |  |  |  | MDC1.C2.C2190: FS, MDC1.C2.C2080: FS | MDC1.C2.C2440: SS 6, MDC1.C2.C2310: SS 6, MDC1.C2.C2360: FS | PCI | 180 | 0 |  | ['927: FS', '1094: FS'] | ['555: SS 6', '786: SS 6', '709: FS']
786 | Not Started | MDC1-BL.5.3.9.4.7.3 | Task Dependent | Toilet Piping Installation / DW | 2020-12-16 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C2.C2300: SS 6 | MDC1-C2.P1800: FS | TCM | 480 | 0 |  | ['785: SS 6'] | ['594: FS']
787 | Not Started | MDC1-BL.5.3.9.4.7.4 | Task Dependent | Controls Installation | 2020-12-09 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 50 | 50 |  |  |  |  | MDC1.C2.C2130: FS, MDC1.C2.C2210: FS | MDC1.C2.Cx2000: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0 |  | ['1031: FS', '929: FS'] | ['500: FS', '31: FS']
788 | Not Started | MDC1-BL.5.3.8.4.2.4 | Task Dependent | Fire Alarm Installation | 2020-12-16 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 80 | 80 |  |  |  |  | MDC1.C3.C3080: FS, MDC1.C3.C3050: SS, MDC1.C3.C3000: FS, MDC1-2527: FS | MDC1.C3.C3370: FS | VECA Electricians | 240 | 0 |  | ['874: FS', '973: SS', '1153: FS', '1325: FS'] | ['399: FS']
789 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-12-16 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 72 | 72 |  |  |  |  | MDC1.C4.C1060: FS, MDC1.C4.E1060: FS, MDC1.C4.E1070: FS | MDC1.C4.C1380: FS, MDC1.C4.C1340: FS, MDC1.C4.C1390: FS, MDC1.C4.C1410: FS, MDC1.C4.C1440: FS | VECA Electricians | 480 | 0 |  | ['876: FS', '183: FS', '184: FS'] | ['385: FS', '418: FS', '375: FS', '343: FS', '328: FS']
790 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-12-16 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C4.C3020: FS | MDC1.C4.C3070: SS 6, MDC1.C4.C3260: FS, MDC1.C4.C3100: FS, MDC1.C4.E1220: FS 4, MDC1.C4.C3210: FS, MDC1.C4.E1180: FS | CSI, VECA Electricians | 1440 | 0 |  | ['877: FS'] | ['755: SS 6', '447: FS', '712: FS', '762: FS 4', '465: FS', '177: FS']
791 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-12-16 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 72 | 72 |  |  |  |  | MDC1.C4.C2060: FS, MDC1.C4.E1040: FS, MDC1.C4.E1050: FS | MDC1.C4.C2380: FS, MDC1.C4.C2360: FS, MDC1.C4.C2440: FS, MDC1.C4.C2400: FS, MDC1.C4.C2430: FS | VECA Electricians | 480 | 0 |  | ['878: FS', '179: FS', '180: FS'] | ['368: FS', '396: FS', '317: FS', '356: FS', '320: FS']
792 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-12-16 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 66 | 66 |  |  |  |  | MDC1.C4.C4020: FS | MDC1.C4.C4070: SS 6, MDC1.C4.C4260: FS, MDC1.C4.C4100: FS, MDC1.C4.E1230: FS 5, MDC1.C4.C4250: FS, MDC1.C4.E1200: FS | CSI, VECA Electricians | 1440 | 0 |  | ['879: FS'] | ['756: SS 6', '434: FS', '713: FS', '760: FS 5', '441: FS', '181: FS']
793 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-4 Cell 2- Cell - 4 | 2021-01-02 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 0 | 0 |  |  |  |  | MDC1.S.1350: FS, MDC1.S.1560: FF, MDC1.S.1560: FS, MDC1.C4.C2040: FS, MDC1.C4.C4040: FS, MDC1.S.1710: FS, MDC1-1996: FS | MDC1.S.1810: FS, MDC1.S.1770: FS | VECA Electricians | 120 | 0 |  | ['1107: FS', '957: FF', '957: FS', '902: FS', '820: FS', '808: FS', '1134: FS'] | ['726: FS', '763: FS']
794 | Not Started | MDC1-BL.5.3.1.4.10.1 | Task Dependent | Pull / Term / Test Conductors | 2020-12-03 07:00 | 2021-01-02 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 28 | 28 |  |  |  |  | MDC1.C1.C3240: FS, MDC1.C1.C3190: FS | MDC1.C1.C3400: FS, MDC1.C1.Cx2030: FS | VECA Electricians | 1680 | 0 |  | ['954: FS', '1048: FS'] | ['759: FS', '596: FS']
795 | Not Started | MDC1-BL.5.3.2.4.5.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2020-12-15 07:00 | 2021-01-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1AD-1019: FS, MDC1-1961: FS, MDC1-2012: FS, MDC1-1963: FS | MDC1.AD.Cx2000: FS | VECA Electricians | 960 | 0 |  | ['882: FS', '1259: FS', '1295: FS', '1217: FS'] | ['640: FS']
796 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2020-12-07 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 7 | 7 |  |  |  |  | MDC1.C1.C2120: FS, MDC1.C1.C2090: FS, MDC1.C1.C2280: FS, MDC1.C1.C2340: FS | MDC1.C1.C2410: SS 5, MDC1.C1.C2450: FS | VECA Electricians | 1080 | 0 |  | ['1185: FS', '1221: FS', '984: FS', '940: FS'] | ['813: SS 5', '694: FS']
797 | Not Started | MDC1-BL.5.3.9.4.9.1 | Task Dependent | PDU's Installation | 2020-12-28 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 31 | 31 |  |  |  |  | MDC1.C2.C1270: FS, MDC1.C2.C1230: FS, MDC1.C2.C1140: FS, MDC1.C2.E1370: FS, MDC1.C2.E1380: FS | MDC1.C2.C1390: FS, MDC1.C2.C1420: FS | VECA Electricians | 180 | 0 |  | ['829: FS', '896: FS', '1028: FS', '193: FS', '194: FS'] | ['678: FS', '648: FS']
798 | Not Started | MDC1-BL.5.3.9.4.11.1 | Task Dependent | PDU's Installation | 2020-12-28 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 25 | 25 |  |  |  |  | MDC1.C2.C2260: FS, MDC1.C2.E1390: FS, MDC1.C2.E1400: FS, MDC1.C2.C2120: FS | MDC1.C2.C2380: FS, MDC1.C2.C2400: FS | VECA Electricians | 180 | 0 |  | ['830: FS', '197: FS', '198: FS', '1030: FS'] | ['679: FS', '649: FS']
799 | Not Started | MDC1-BL.5.3.8.4.3.4 | Task Dependent | Fire Alarm Installation | 2020-12-14 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 72 | 72 |  |  |  |  | MDC1.C3.C2160: FS, MDC1.C3.C2110: FS | MDC1.C3.C2390: FS | VECA Electricians | 240 | 0 |  | ['889: FS', '974: FS'] | ['477: FS']
800 | Not Started | MDC1-BL.5.3.8.4.4.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-12-14 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C3.C4090: FS, MDC1.C3.E1280: FS, MDC1.C3.E1290: FS | MDC1.C3.C4380: FS, MDC1.C3.C4140: SS 5, MDC1.C3.C4180: FS, MDC1.C3.C4410: FS | TCM | 720 | 0 |  | ['890: FS', '143: FS', '144: FS'] | ['443: FS', '769: SS 5', '719: FS', '400: FS']
801 | Not Started | MDC1-BL.5.3.6.4.1.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-12-23 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 62 | 62 |  |  |  |  | MDC1.C4.C1070: FS | MDC1.C4.C1110: FS, MDC1.C4.E1140: FS | SURE STEEL | 160 | 0 |  | ['842: FS'] | ['720: FS', '145: FS']
802 | Not Started | MDC1-BL.5.3.6.4.5.4 | Task Dependent | Fire Alarm System | 2020-12-14 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 100 | 100 |  |  |  |  | MDC1.C4.C1050: FS | MDC1.C4.C1210: FS, MDC1-C4.P1800: FS | VECA Electricians | 240 | 0 |  | ['891: FS'] | ['552: FS', '33: FS']
803 | Not Started | MDC1-BL.5.3.6.4.6.4 | Task Dependent | Fire Riser Installation | 2020-12-14 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 98 | 98 |  |  |  |  | MDC1.C4.C3010: FS | MDC1.C4.C3090: FS |  | 0 | 0 |  | ['892: FS'] | ['722: FS']
804 | Not Started | MDC1-BL.5.3.6.4.3.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-12-23 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 62 | 62 |  |  |  |  | MDC1.C4.C2070: FS | MDC1.C4.C2110: FS, MDC1.C4.E1160: FS | SURE STEEL | 160 | 0 |  | ['843: FS'] | ['723: FS', '149: FS']
805 | Not Started | MDC1-BL.5.3.6.4.7.4 | Task Dependent | Fire Alarm System | 2020-12-14 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 100 | 100 |  |  |  |  | MDC1.C4.C2050: FS | MDC1.C4.C2210: FS | VECA Electricians | 240 | 0 |  | ['893: FS'] | ['554: FS']
806 | Not Started | MDC1-BL.5.3.6.4.8.4 | Task Dependent | Fire Riser Installation | 2020-12-14 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 98 | 98 |  |  |  |  | MDC1.C4.C4010: FS | MDC1.C4.C4090: FS |  | 0 | 0 |  | ['894: FS'] | ['725: FS']
807 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Lift & Set MER in Place | 2020-12-22 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C2.E1130: FS, MDC1.C2.C2030: FS, MDC1.C2.E1310: FS, MDC1.C2.C1250: FS | MDC1.C2.C2340: FS, MDC1.C2.C2330: FS, MDC1.C2.C3230: FS | VECA Electricians | 120 | 0 |  | ['1158: FS', '1183: FS', '46: FS', '850: FS'] | ['733: FS', '774: FS', '770: FS']
808 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull Cross Overs- COLO-4 CELL-3 to CELL-4 | 2020-12-29 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 0 | 0 |  |  |  |  | MDC1.S.1350: FS, MDC1.S.1520: FS, MDC1.C4.C3040: FS, MDC1.C4.C4040: FS, MDC1.C4.C2040: FS, MDC1.S.1720: SS, MDC1-1996: FS | MDC1.S.1810: FS, MDC1.S.1780: FS, MDC1.S.1750: FS | VECA Electricians | 120 | 0 |  | ['1107: FS', '978: FS', '819: FS', '820: FS', '902: FS', '809: SS', '1134: FS'] | ['726: FS', '764: FS', '793: FS']
809 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-4 - CELL-1 to Cell-3 | 2020-12-29 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 0 | 0 |  |  |  |  | MDC1.C4.C3040: FS, MDC1.C4.C1040: FS, MDC1.S.1680: FS, MDC1-1996: FS | MDC1.S.1780: FS, MDC1.S.1710: SS | VECA Electricians | 120 | 0 |  | ['819: FS', '901: FS', '858: FS', '1134: FS'] | ['764: FS', '808: SS']
810 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull- UMS to COLO-1 | 2020-12-03 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.S.1550: FS, MDC1.C1.C1040: FS, MDC1.C1.C3040: FS, MDC1.C1.C2040: FS, MDC1.C1.C4040: FS, MDC1-1996: FS | MDC1.S.1820: FS | VECA Electricians | 1200 | 0 |  | ['956: FS', '1270: FS', '1235: FS', '1271: FS', '1236: FS', '1134: FS'] | ['727: FS']
811 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull- UMS to COLO-4 | 2020-12-29 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 0 | 0 |  |  |  |  | MDC1.C4.C3040: FS, MDC1.C4.C1040: FS, MDC1.S.1590: FS, MDC1-1996: FS | MDC1.S.1820: FS | VECA Electricians | 120 | 0 |  | ['819: FS', '901: FS', '933: FS', '1134: FS'] | ['727: FS']
812 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2020-12-21 08:00 | 2020-12-30 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 5 | 5 |  |  |  |  | MDC1.C2.C1040: FS, MDC1.C2.C1250: FS | MDC1.C2.C1380: FS, MDC1.C2.C1410: FS, MDC1.C2.C1430: FS, MDC1.C2.C3270: FS | SURE STEEL | 160 | 0 |  | ['1181: FS', '850: FS'] | ['699: FS', '660: FS', '618: FS', '732: FS']
813 | Not Started | MDC1-BL.5.3.1.4.3.4 | Task Dependent | Fire Alarm Installation | 2020-12-12 07:00 | 2020-12-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 8 | 8 |  |  |  |  | MDC1.C1.C2120: FS, MDC1.C1.C2090: FS, MDC1.C1.C2420: SS 5 | MDC1.C1.C2450: FS | VECA Electricians | 240 | 0 |  | ['1185: FS', '1221: FS', '796: SS 5'] | ['694: FS']
814 | Not Started | MDC1-BL.5.3.9.4.9.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-12-12 07:00 | 2020-12-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C2.C1230: FS | MDC1.C2.C1340: FS | LINX- TELECOM | 1440 | 0 |  | ['896: FS'] | ['728: FS']
815 | Not Started | MDC1-BL.5.3.9.4.10.1 | Task Dependent | Cable Tray Installation | 2020-12-12 07:00 | 2020-12-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C1230: FS, MDC1.C2.C3170: FS | MDC1.C3.C1310: FS, MDC1.C2.C3260: FS, MDC1.C2.C3290: FS, MDC1.C2.C3370: FS, MDC1.C2.C3220: FF 6, MDC1.C2.C3280: FS | VECA Electricians | 1440 | 0 |  | ['896: FS', '914: FS'] | ['569: FS', '748: FS', '717: FS', '616: FS', '767: FF 6', '729: FS']
816 | Not Started | MDC1-BL.5.3.9.4.11.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-12-12 07:00 | 2020-12-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C2.C2220: FS | MDC1.C2.C2350: FS | LINX- TELECOM | 1440 | 0 |  | ['897: FS'] | ['730: FS']
817 | Not Started | MDC1-BL.5.3.9.4.13.1 | Task Dependent | Cable Tray Installation | 2020-12-12 07:00 | 2020-12-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C2220: FS, MDC1.C2.C4140: FS | MDC1.C3.C2310: FS, MDC1.C2.C4210: FS, MDC1.C2.C4330: FS, MDC1.C2.C4200: FS, MDC1.C2.C4230: FS | VECA Electricians | 1440 | 0 |  | ['897: FS', '915: FS'] | ['570: FS', '749: FS', '617: FS', '738: FS', '731: FS']
818 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2020-12-11 08:00 | 2020-12-29 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.C1360: FS, MDC1.C1.C1090: FS, MDC1.C1.C1280: FS | MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS, MDC1.C1.C1460: FS | VECA Electricians | 960 | 0 |  | ['899: FS', '1218: FS', '1026: FS'] | ['645: FS', '30: FS', '689: FS']
819 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-12-21 07:00 | 2020-12-28 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.C4.C3030: FS, MDC1.C4.E1080: FS, MDC1.C4.E1090: FS | MDC1.S.1770: FS, MDC1.S.1740: FS, MDC1.S.1720: FS, MDC1.S.1710: FS | VECA Electricians | 80 | 0 |  | ['852: FS', '119: FS', '120: FS'] | ['763: FS', '811: FS', '809: FS', '808: FS']
820 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-12-21 07:00 | 2020-12-28 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.C4.C4030: FS, MDC1.C4.E1100: FS, MDC1.C4.E1110: FS | MDC1.S.1770: FS, MDC1.S.1710: FS, MDC1.S.1750: FS | VECA Electricians | 80 | 0 |  | ['853: FS', '123: FS', '124: FS'] | ['763: FS', '808: FS', '793: FS']
821 | Not Started | MDC1-BL.5.3.1.4.11.1 | Task Dependent | Light Fixtures Installation | 2020-12-17 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 94 | 94 |  |  |  |  | MDC1.C1.C2380: FS, MDC1.C1.C2320: FS, MDC1.C1.C2250: FS | MDC1.C1.C4400: FS, MDC1-C1.P1900: FS | VECA Electricians | 480 | 0 |  | ['862: FS', '970: FS', '1035: FS'] | ['747: FS', '566: FS']
822 | Not Started | MDC1-BL.5.3.8.4.5.2 | Task Dependent | Hydronic Piping Installation | 2020-12-10 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C3.C1140: FS | MDC1.C3.Cx2000: FF | TCM | 480 | 0 |  | ['906: FS'] | ['389: FF']
823 | Not Started | MDC1-BL.5.3.8.3.6.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-12-10 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C1120: FS, MDC1.C3.C1070: FS | MDC1.C3.C3140: FS, MDC1.C3.C3130: FS, MDC1.C3.C3120: FF, MDC1.C3.C3120: FS, MDC1.C3.E1300: FS | TCM, VECA Electricians | 1360 | 0 |  | ['904: FS', '1003: FS'] | ['741: FS', '740: FS', '739: FF', '739: FS', '70: FS']
824 | Not Started | MDC1-BL.5.3.8.4.6.4 | Task Dependent | Fire Alarm System | 2020-12-10 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 79 | 79 |  |  |  |  | MDC1.C3.C3070: FS | MDC1.C3.C3170: FS | VECA Electricians | 240 | 0 |  | ['908: FS'] | ['656: FS']
825 | Not Started | MDC1-BL.5.3.8.4.7.2 | Task Dependent | Hydronic Piping Installation | 2020-12-10 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C3.C2140: FS | MDC1.C3.Cx2010: FF | TCM | 480 | 0 |  | ['911: FS'] | ['380: FF']
826 | Not Started | MDC1-BL.5.3.8.3.8.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-12-10 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C2120: FS, MDC1.C3.C2070: FS | MDC1.C3.C4170: FS, MDC1.C3.C4160: FS, MDC1.C3.C4150: FS, MDC1.C3.E1310: FS | TCM, VECA Electricians | 1360 | 0 |  | ['909: FS', '1006: FS'] | ['744: FS', '743: FS', '742: FS', '72: FS']
827 | Not Started | MDC1-BL.5.3.8.4.8.4 | Task Dependent | Fire Alarm System | 2020-12-10 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 79 | 79 |  |  |  |  | MDC1.C3.C4080: FS | MDC1.C3.C4210: FS | VECA Electricians | 240 | 0 |  | ['913: FS'] | ['658: FS']
828 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2020-12-12 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C3250: FS, MDC1.C1.C3300: FS | MDC1.C1.C3410: FS | VECA Electricians | 560 | 0 |  | ['945: FS', '895: FS'] | ['736: FS']
829 | Not Started | MDC1-BL.5.3.9.4.9.1 | Task Dependent | Power Bus Installation | 2020-12-12 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 31 | 31 |  |  |  |  | MDC1.C2.C1230: FS, MDC1.C2.C1180: FS | MDC1.C2.C1300: FS, MDC1.C2.E1370: FS | VECA Electricians | 1200 | 0 |  | ['896: FS', '994: FS'] | ['797: FS', '193: FS']
830 | Not Started | MDC1-BL.5.3.9.4.11.1 | Task Dependent | Power Bus Installation | 2020-12-12 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 25 | 25 |  |  |  |  | MDC1.C2.C2220: FS | MDC1.C2.C2280: FS, MDC1.C2.E1390: FS | VECA Electricians | 1200 | 0 |  | ['897: FS'] | ['798: FS', '197: FS']
831 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2020-11-25 08:00 | 2020-12-23 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 6 | 6 |  |  |  |  | MDC1.C1.C1090: FS, MDC1.C1.C1110: FS, MDC1.C1.C1280: FS, MDC1.C1.C1300: FS | MDC1.C1.Cx2000: FS, MDC1.C1.C1440: FS | VECA Electricians | 1080 | 0 |  | ['1218: FS', '1207: FS', '1026: FS', '983: FS'] | ['645: FS', '716: FS']
832 | Not Started | MDC1-BL.5.3.1.4.6.2 | Task Dependent | Hydronic Piping Installation | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C3290: FS | MDC1.C1.Cx2000: FF, MDC1-C1.P1800: FS | TCM | 480 | 0 |  | ['919: FS'] | ['645: FF', '30: FS']
833 | Not Started | MDC1-BL.5.3.1.4.8.2 | Task Dependent | Hydronic Piping Installation | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C4250: FS | MDC1.C1.Cx2000: FF, MDC1-C1.P1800: FS | TCM | 480 | 0 |  | ['922: FS'] | ['645: FF', '30: FS']
834 | Not Started | MDC1-BL.5.3.1.4.13.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 25 | 25 |  |  |  |  | MDC1.C1.C4260: FS, MDC1.C1.C4180: FS | MDC1.C1.C4380: FS | LINX- TELECOM | 1440 | 0 |  | ['936: FS', '1040: FS'] | ['750: FS']
835 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2020-12-11 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C4270: FS, MDC1.C1.C2340: FS | MDC1.C1.C4370: FS, MDC1.C1.C4410: FS |  | 0 | 0 |  | ['903: FS', '940: FS'] | ['775: FS', '715: FS']
836 | Not Started | MDC1-BL.5.3.9.4.5.2 | Task Dependent | Hydronic Piping Installation | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 66 | 66 |  |  |  |  | MDC1.C2.C1210: FS | MDC1.C2.Cx2010: FF | TCM | 480 | 0 |  | ['924: FS'] | ['498: FF']
837 | Not Started | MDC1-BL.5.3.9.3.6.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C1200: FS, MDC1.C2.C1160: FS | MDC1.C2.C3240: FS, MDC1.C2.C3240: SS 5, MDC1.C2.E1340: FS | TCM, VECA Electricians | 1360 | 0 |  | ['923: FS', '1014: FS'] | ['751: FS', '751: SS 5', '82: FS']
838 | Not Started | MDC1-BL.5.3.9.4.6.4 | Task Dependent | Fire Alarm System | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C2.C3160: FS | MDC1.C2.C3300: FS, MDC1-C2.P1900: FS | VECA Electricians | 240 | 0 |  | ['926: FS'] | ['708: FS', '31: FS']
839 | Not Started | MDC1-BL.5.3.9.4.7.2 | Task Dependent | Hydronic Piping Installation | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 66 | 66 |  |  |  |  | MDC1.C2.C2200: FS | MDC1.C2.Cx2000: FF | TCM | 480 | 0 |  | ['928: FS'] | ['500: FF']
840 | Not Started | MDC1-BL.5.3.9.3.8.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C2190: FS, MDC1.C2.C2140: FS | MDC1.C2.C4180: FS, MDC1.C2.C4180: SS 5, MDC1.C2.E1330: FS | TCM, VECA Electricians | 1360 | 0 |  | ['927: FS', '1017: FS'] | ['753: FS', '753: SS 5', '68: FS']
841 | Not Started | MDC1-BL.5.3.9.4.8.4 | Task Dependent | Fire Alarm System | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 43 | 43 |  |  |  |  | MDC1.C2.C4130: FS | MDC1.C2.C4260: FS, MDC1-C2.P1900: FS | VECA Electricians | 240 | 0 |  | ['930: FS'] | ['711: FS', '31: FS']
842 | Not Started | MDC1-BL.5.3.6.4.1.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C4.C1060: SS 6, MDC1.C4.C1000: FS, MDC1.C3.C1060: FS, MDC1.C3.C1060: FF | MDC1.C4.C1080: FS, MDC1-C4.P1700: FS | CSI, VECA Electricians | 1440 | 0 |  | ['876: SS 6', '1154: FS', '1020: FS', '1020: FF'] | ['801: FS', '41: FS']
843 | Not Started | MDC1-BL.5.3.6.4.3.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C4.C2060: SS 6, MDC1.C4.C2000: FS | MDC1.C4.C2080: FS | CSI, VECA Electricians | 1440 | 0 |  | ['878: SS 6', '1023: FS'] | ['804: FS']
844 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term URS- Line Side | 2020-12-16 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 1 | 1 |  |  |  |  | MDC1.S.1600: FS, MDC1.S.1660: FS | MDC1.S.1800: FS, MDC1.S.1760: FS | VECA Electricians | 360 | 0 |  | ['934: FS', '881: FS'] | ['766: FS', '771: FS']
845 | Not Started | MDC1-BL.5.3.2.4.1 | Task Dependent | Electrical Devices & Trim | 2020-11-30 07:00 | 2020-12-21 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 44 | 44 |  |  |  |  | MDC1AD-1018: FS | MDC1.AD.Cx2000: FS, MDC1.AD.Cx2010: FS | VECA Electricians | 1800 | 0 |  | ['980: FS'] | ['640: FS', '585: FS']
846 | Not Started | MDC1-BL.5.3.2.4.3 | Task Dependent | Security Devices & Trim | 2020-11-30 07:00 | 2020-12-21 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 96 | 96 |  |  |  |  | MDC1AD-1018: FS | MDC1-C1.P1900: FS |  | 0 | 0 |  | ['980: FS'] | ['566: FS']
847 | Not Started | MDC1-BL.4.10.2.1.4 | Finish Milestone | Pad Ready for MER COLO-4 Cell-1 |  | 2020-12-21 17:00 |  |  | 2020-12-21 17:00 |  | 0 | 0 | 0 | 0 | 62 | 62 |  |  |  |  | MDC1.C4.C1060: FS 5 | MDC1.C4.C1230: FS |  | 0 | 0 |  | ['876: FS 5'] | ['511: FS']
848 | Not Started | MDC1-BL.4.10.2.1.4 | Finish Milestone | Pad Ready for MER COLO-4 Cell-2 |  | 2020-12-21 17:00 |  |  | 2020-12-21 17:00 |  | 0 | 0 | 0 | 0 | 67 | 67 |  |  |  |  | MDC1.C4.C2060: FS 5 | MDC1.C4.C2270: FS |  | 0 | 0 |  | ['878: FS 5'] | ['483: FS']
849 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term- UMS- Line Side | 2020-12-15 07:00 | 2020-12-21 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 2 | 2 |  |  |  |  | MDC1.S.1680: SS | MDC1.S.1800: FS | VECA Electricians | 360 | 0 |  | ['858: SS'] | ['766: FS']
850 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Lift & Set MER in Place | 2020-12-15 08:00 | 2020-12-21 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C2.E1120: FS, MDC1.C2.C1040: FS, MDC1.C2.E1300: FS, MDC1-C2.P1600: FS, MDC1.C1.C4270: FS | MDC1.C2.C1330: FS, MDC1.C2.C1290: FS, MDC1.C2.C2290: FS | VECA Electricians | 120 | 0 |  | ['1157: FS', '1181: FS', '45: FS', '36: FS', '903: FS'] | ['772: FS', '812: FS', '807: FS']
851 | Not Started | MDC1-BL.5.3.1.4.10.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-12-07 07:00 | 2020-12-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C1.C3260: FS, MDC1.C1.C3190: FS | MDC1.C1.Cx2030: FS, MDC1.C1.C3380: FS | LINX- TELECOM | 1440 | 0 |  | ['944: FS', '1048: FS'] | ['596: FS', '761: FS']
852 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-12-16 07:00 | 2020-12-19 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.C4.C3020: FS | MDC1.C4.C3040: FS, MDC1.C4.E1080: FS | CSI, VECA Electricians | 480 | 0 |  | ['877: FS'] | ['819: FS', '119: FS']
853 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-12-16 07:00 | 2020-12-19 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.C4.C4020: FS | MDC1.C4.C4040: FS, MDC1.C4.E1100: FS | CSI, VECA Electricians | 480 | 0 |  | ['879: FS'] | ['820: FS', '123: FS']
854 | Not Started | MDC1-BL.5.3.9.4.9.3 | Task Dependent | Fire Alarm System | 2020-12-08 07:00 | 2020-12-18 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 41 | 41 |  |  |  |  | MDC1.C2.C1230: FF 6 | MDC1.C2.C1400: FS, MDC1-C2.P1900: FS | VECA Electricians | 600 | 0 |  | ['896: FF 6'] | ['671: FS', '31: FS']
855 | Not Started | MDC1-BL.5.3.9.4.11.3 | Task Dependent | Fire Alarm System | 2020-12-08 07:00 | 2020-12-18 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 41 | 41 |  |  |  |  | MDC1.C2.C2220: FF 6 | MDC1.C2.C2390: FS, MDC1-C2.P1900: FS | VECA Electricians | 600 | 0 |  | ['897: FF 6'] | ['673: FS', '31: FS']
856 | Not Started | MDC1-BL.5.3.8.4.1.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-12-04 07:00 | 2020-12-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 67 | 67 |  |  |  |  | MDC1.C3.C1160: SS 5 | MDC1.C3.C1200: FS, MDC1.C3.Cx2000: FS | TCM | 720 | 0 |  | ['888: SS 5'] | ['768: FS', '389: FS']
857 | Not Started | MDC1-BL.5.3.8.4.3.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-12-04 07:00 | 2020-12-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 91 | 91 |  |  |  |  | MDC1.C3.C2160: SS 5 | MDC1.C3.Cx2010: FS | TCM | 720 | 0 |  | ['889: SS 5'] | ['380: FS']
858 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull - JAZ to UMS | 2020-12-15 07:00 | 2020-12-18 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 2 | 2 |  |  |  |  | MDC1.S.1470: FS, MDC1.S.1210: FS, MDC1-2133: FS, MDC1.S.1170: FS, MDC1.S.1370: FS, MDC1-2189: FS, MDC1.S.1640: FS, MDC1-1996: FS | MDC1.S.1690: SS, MDC1.S.1720: FS | VECA Electricians | 240 | 0 |  | ['1038: FS', '1187: FS', '1136: FS', '1225: FS', '1103: FS', '1226: FS', '884: FS', '1134: FS'] | ['849: SS', '809: FS']
859 | Not Started | MDC1-BL.5.3.1.4.13.3 | Task Dependent | Fire Alarm System | 2020-12-07 07:00 | 2020-12-17 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 116 | 116 |  |  |  |  | MDC1.C1.C4220: FS | MDC1.M1010: FS | VECA Electricians | 600 | 0 |  | ['941: FS'] | ['344: FS']
860 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2020-12-07 07:00 | 2020-12-17 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C2280: FS, MDC1.C1.C2340: FS | MDC1.C1.C2430: FS, MDC1.C1.C4370: FS | VECA Electricians | 560 | 0 |  | ['984: FS', '940: FS'] | ['773: FS', '775: FS']
861 | Not Started | MDC1-BL.5.3.1.4.9.1 | Task Dependent | Pull / Term / Test Conductors | 2020-11-18 07:00 | 2020-12-16 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 27 | 27 |  |  |  |  | MDC1.C1.C1270: FS | MDC1.C1.C1450: FS, MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS | VECA Electricians | 1680 | 0 |  | ['1034: FS'] | ['714: FS', '645: FS', '30: FS']
862 | Not Started | MDC1-BL.5.3.1.4.11.1 | Task Dependent | Pull / Term / Test Conductors | 2020-11-18 07:00 | 2020-12-16 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 32 | 32 |  |  |  |  | MDC1.C1.C2250: FS, MDC1.C1.C2180: FS | MDC1.C1.C2400: FS, MDC1.C1.Cx2010: FS | VECA Electricians | 1680 | 0 |  | ['1035: FS', '1110: FS'] | ['821: FS', '623: FS']
863 | Not Started | MDC1-BL.5.1.3.1.2.5 | Task Dependent | Duct Bank - Vault to COLO-4 UPM | 2020-12-10 07:00 | 2020-12-16 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 11 | 11 |  |  |  |  | MDC1.S.1620: FS, MDC1.C4.C2020: FS | MDC1.S.1770: FS |  | 0 | 0 |  | ['916: FS', '977: FS'] | ['763: FS']
864 | Not Started | MDC1-BL.5.3.1.4.5.3 | Task Dependent | Floor Drain System Installation | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 118 | 118 |  |  |  |  | MDC1.C1.C1120: FS, MDC1.C1.C1310: FS | MDC1.C1.C4490: FS |  | 0 | 0 |  | ['1198: FS', '962: FS'] | ['610: FS']
865 | Not Started | MDC1-BL.5.3.1.4.5.3 | Task Dependent | Toilet Piping Installation / DW | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 118 | 118 |  |  |  |  | MDC1.C1.C1310: FS | MDC1.C1.C4490: FS | TCM | 480 | 0 |  | ['962: FS'] | ['610: FS']
866 | Not Started | MDC1-BL.5.3.1.4.9.2 | Task Dependent | BMS Pull Wire / Term / Test | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 28 | 28 |  |  |  |  | MDC1.C1.C1330: FS | MDC1.C1.C1430: SS 6, MDC1.C1.Cx2000: FS | LINX- TELECOM | 1440 | 0 |  | ['964: FS'] | ['776: SS 6', '645: FS']
867 | Not Started | MDC1-BL.5.3.1.4.10.3 | Task Dependent | Fire Alarm System | 2020-12-03 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 118 | 118 |  |  |  |  | MDC1.C1.C3240: FS | MDC1.M1010: FS | VECA Electricians | 600 | 0 |  | ['954: FS'] | ['344: FS']
868 | Not Started | MDC1-BL.5.3.1.4.7.3 | Task Dependent | Floor Drain System Installation | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 118 | 118 |  |  |  |  | MDC1.C1.C2110: FS, MDC1.C1.C2290: FS | MDC1.C1.C4490: FS |  | 0 | 0 |  | ['1199: FS', '967: FS'] | ['610: FS']
869 | Not Started | MDC1-BL.5.3.1.4.7.3 | Task Dependent | Toilet Piping Installation / DW | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 118 | 118 |  |  |  |  | MDC1.C1.C2290: FS | MDC1.C1.C4490: FS | TCM | 480 | 0 |  | ['967: FS'] | ['610: FS']
870 | Not Started | MDC1-BL.5.3.1.4.11.2 | Task Dependent | BMS Pull Wire / Term / Test | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C2310: FS | MDC1.C1.C2440: FS, MDC1.C1.Cx2040: FS, MDC1.C1.Cx2010: FS | LINX- TELECOM | 1440 | 0 |  | ['969: FS'] | ['735: FS', '586: FS', '623: FS']
871 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2020-12-11 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 6 | 6 |  |  |  |  | MDC1.C1.C4050: FS, MDC1.C1.C4270: FS, MDC1.C1.C2280: FS | MDC1.C1.C4370: FS, MDC1.C1.C4440: FS, MDC1.C1.C4410: FS, MDC1.S.1900: FS | SURE STEEL | 160 | 0 |  | ['1222: FS', '903: FS', '984: FS'] | ['775: FS', '695: FS', '715: FS', '257: FS']
872 | Not Started | MDC1-BL.5.3.1.4.8.4 | Task Dependent | Controls Installation | 2020-11-20 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 43 | 43 |  |  |  |  | MDC1.C1.C4200: FS | MDC1.C1.Cx2050: FS, MDC1.C1.C4490: FS | VECA Electricians | 720 | 0 |  | ['1013: FS'] | ['587: FS', '610: FS']
873 | Not Started | MDC1-BL.5.3.1.4.13.3 | Task Dependent | Controls Installation | 2020-12-07 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 43 | 43 |  |  |  |  | MDC1.C1.C4220: FS | MDC1.C1.C4390: FS, MDC1.C1.Cx2050: FS | VECA Electricians | 720 | 0 |  | ['941: FS'] | ['737: FS', '587: FS']
874 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 72 | 72 |  |  |  |  | MDC1.C3.C3050: FS, MDC1.C3.E1220: FS, MDC1.C3.E1230: FS | MDC1.C3.C3330: FS, MDC1.C3.C3350: FS, MDC1.C3.C3380: FS, MDC1.C3.C3110: FS, MDC1.C3.C3370: FS | VECA Electricians | 480 | 0 |  | ['973: FS', '171: FS', '172: FS'] | ['466: FS', '442: FS', '395: FS', '788: FS', '399: FS']
875 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 72 | 72 |  |  |  |  | MDC1.C3.C4050: FS, MDC1.C3.E1240: FS, MDC1.C3.E1250: FS | MDC1.C3.C4370: FS, MDC1.C3.C4380: FS, MDC1.C3.C4430: FS, MDC1.C3.C4180: FS, MDC1.C3.C4410: FS | VECA Electricians | 480 | 0 |  | ['975: FS', '175: FS', '176: FS'] | ['445: FS', '443: FS', '381: FS', '719: FS', '400: FS']
876 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C4.C1020: FS | MDC1.C4.C1070: SS 6, MDC1.C4.C1280: FS, MDC1.C4.C1100: FS, MDC1-C4.P1600: FS, MDC1.C4.E1120: FS 5, MDC1.C4.C1230: FS, MDC1.C4.E1060: FS | CSI, VECA Electricians | 1440 | 0 |  | ['976: FS'] | ['842: SS 6', '486: FS', '789: FS', '40: FS', '847: FS 5', '511: FS', '183: FS']
877 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Electrical Underground Rough-In | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.C1020: FS | MDC1.C4.C3060: FS, MDC1.C4.C3030: FS | VECA Electricians | 960 | 0 |  | ['976: FS'] | ['790: FS', '852: FS']
878 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C4.C2020: FS | MDC1.C4.C2070: SS 6, MDC1.C4.C2280: FS, MDC1.C4.C2100: FS, MDC1.C4.E1130: FS 5, MDC1.C4.C2270: FS, MDC1.C4.E1040: FS | CSI, VECA Electricians | 1440 | 0 |  | ['977: FS'] | ['843: SS 6', '470: FS', '791: FS', '848: FS 5', '483: FS', '179: FS']
879 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Electrical Underground Rough-In | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.C2020: FS | MDC1.C4.C4060: FS, MDC1.C4.C4030: FS | VECA Electricians | 960 | 0 |  | ['977: FS'] | ['792: FS', '853: FS']
880 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull- UMS to COLO-2 | 2020-12-03 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 10 | 10 |  |  |  |  | MDC1.S.1550: FS, MDC1-1996: FS | MDC1.S.1820: FS | VECA Electricians | 600 | 0 |  | ['956: FS', '1134: FS'] | ['727: FS']
881 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -3 WEST UPMS | 2020-12-09 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 1 | 1 |  |  |  |  | MDC1.S.1560: FS, MDC1.S.1520: FS, MDC1.S.1610: FS | MDC1.S.1850: FF, MDC1.S.1850: FS, MDC1.S.1840: FS, MDC1.S.1700: FS, MDC1.S.1780: FS | VECA Electricians | 360 | 0 |  | ['957: FS', '978: FS', '935: FS'] | ['601: FF', '601: FS', '611: FS', '844: FS', '764: FS']
882 | Not Started | MDC1-BL.5.3.2.4.1 | Task Dependent | Set Electrical Equipment | 2020-10-28 07:00 | 2020-12-14 17:00 |  |  |  |  | 0 | 0 | 36 | 36 | 8 | 8 |  |  |  |  | MDC1AD-1016: FS, MDC1-2505: FS, MDC1-2506: FS, MDC1-2507: FS, MDC1-2508: FS, MDC1-2511: FS, MDC1-2512: FS, MDC1-2514: FS, MDC1-2513: FS | MDC1-1969: FS, MDC1-1968: FS, MDC1-1967: FS, MDC1AD-1023: FS, MDC1.AD.Cx2000: FS | VECA Electricians | 2880 | 0 |  | ['1129: FS', '219: FS', '220: FS', '221: FS', '222: FS', '225: FS', '226: FS', '228: FS', '227: FS'] | ['746: FS', '745: FS', '795: FS', '757: FS', '640: FS']
883 | Not Started | MDC1-BL.5.3.2.4.2 | Task Dependent | Plumbing Devices & Trim | 2020-11-19 07:00 | 2020-12-14 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 50 | 50 |  |  |  |  | MDC1AD-1020: FS | MDC1.AD.Cx2000: FS | TCM | 360 | 0 |  | ['1027: FS'] | ['640: FS']
884 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | PULL- URS to COLO-3 | 2020-12-10 07:00 | 2020-12-14 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 2 | 2 |  |  |  |  | MDC1.C3.C4040: FS, MDC1.C3.C2040: FS, MDC1.C3.C3040: FS, MDC1.C3.C1040: FS, MDC1.S.1200: FS, MDC1.S.1620: FS, MDC1.S.1460: FS, MDC1.S.1500: FS, MDC1.S.1600: FS, MDC1-1996: FS | MDC1.S.1790: FS, MDC1.S.1770: FS, MDC1.S.1680: FS | VECA Electricians | 240 | 0 |  | ['999: FS', '1075: FS', '998: FS', '1074: FS', '1206: FS', '916: FS', '1046: FS', '1000: FS', '934: FS', '1134: FS'] | ['765: FS', '763: FS', '858: FS']
885 | Not Started | MDC1-BL.5.3.1.4.10.3 | Task Dependent | Controls Installation | 2020-12-03 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 41 | 41 |  |  |  |  | MDC1.C1.C3240: FS | MDC1.C1.C3400: FS, MDC1.C1.Cx2030: FS | VECA Electricians | 720 | 0 |  | ['954: FS'] | ['759: FS', '596: FS']
886 | Not Started | MDC1-BL.5.3.9.4.2.4 | Task Dependent | Fire Alarm Installation | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C2.C3120: FS, MDC1.C2.C3080: FS | MDC1.C2.C3440: FS | VECA Electricians | 240 | 0 |  | ['986: FS', '1052: FS'] | ['535: FS']
887 | Not Started | MDC1-BL.5.3.9.4.3.4 | Task Dependent | Fire Alarm Installation | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C2.C2170: FS, MDC1.C2.C2060: FS | MDC1.C2.C2430: FS, MDC1-C2.P1900: FS | VECA Electricians | 240 | 0 |  | ['987: FS', '1124: FS'] | ['590: FS', '31: FS']
888 | Not Started | MDC1-BL.5.3.8.4.1.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C3.C1100: FS, MDC1.C3.E1180: FS, MDC1.C3.E1190: FS, MDC1-C3.P1700: FS | MDC1.C3.C1360: FS, MDC1.C3.C1170: SS 5, MDC1.C3.C1200: FS, MDC1.C3.C1400: FS | TCM | 720 | 0 |  | ['988: FS', '139: FS', '140: FS', '39: FS'] | ['527: FS', '856: SS 5', '768: FS', '476: FS']
889 | Not Started | MDC1-BL.5.3.8.4.3.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C3.C2100: FS, MDC1.C3.E1200: FS, MDC1.C3.E1210: FS | MDC1.C3.C2350: FS, MDC1.C3.C2170: SS 5, MDC1.C3.C2190: FS, MDC1.C3.C2390: FS | TCM | 720 | 0 |  | ['989: FS', '141: FS', '142: FS'] | ['528: FS', '857: SS 5', '799: FS', '477: FS']
890 | Not Started | MDC1-BL.5.3.8.4.4.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-12-09 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 62 | 62 |  |  |  |  | MDC1.C3.C4070: FS | MDC1.C3.C4130: FS, MDC1.C3.E1290: FS | SURE STEEL | 160 | 0 |  | ['931: FS'] | ['800: FS', '144: FS']
891 | Not Started | MDC1-BL.5.3.6.4.5.4 | Task Dependent | Fire Riser Installation | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 100 | 100 |  |  |  |  | MDC1.C4.C1010: FS | MDC1.C4.C1090: FS |  | 0 | 0 |  | ['990: FS'] | ['802: FS']
892 | Not Started | MDC1-BL.5.3.6.3.6.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 98 | 98 |  |  |  |  | MDC1.C4.CS1090: FS, MDC1.C4.C1010: FS | MDC1.C4.C3240: FS, MDC1.C4.C3290: FS, MDC1.C4.C3050: FS | PCI | 480 | 0 |  | ['1062: FS', '990: FS'] | ['449: FS', '411: FS', '803: FS']
893 | Not Started | MDC1-BL.5.3.6.4.7.4 | Task Dependent | Fire Riser Installation | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 100 | 100 |  |  |  |  | MDC1.C4.C2010: FS | MDC1.C4.C2090: FS |  | 0 | 0 |  | ['991: FS'] | ['805: FS']
894 | Not Started | MDC1-BL.5.3.6.3.8.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 98 | 98 |  |  |  |  | MDC1.C4.CS1090: FS, MDC1.C4.C2010: FS | MDC1.C4.C4230: FS, MDC1.C4.C4270: FS, MDC1.C4.C4050: FS | PCI | 480 | 0 |  | ['1062: FS', '991: FS'] | ['451: FS', '413: FS', '806: FS']
895 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2020-11-30 07:00 | 2020-12-11 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C3210: FS | MDC1.C1.C3350: FS, MDC1.C1.C3390: FS |  | 0 | 0 |  | ['981: FS'] | ['828: FS', '758: FS']
896 | Not Started | MDC1-BL.5.3.9.4.9.1 | Task Dependent | Cable Tray Installation | 2020-11-24 07:00 | 2020-12-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C1180: FS | MDC1.C2.C1280: FS, MDC1.C2.C3210: FS, MDC1.C2.C1270: FS, MDC1.C2.C1300: FS, MDC1.C2.C1400: FS, MDC1.C2.C1240: FF 6 | VECA Electricians | 1440 | 0 |  | ['994: FS'] | ['814: FS', '815: FS', '829: FS', '797: FS', '671: FS', '854: FF 6']
897 | Not Started | MDC1-BL.5.3.9.4.11.1 | Task Dependent | Cable Tray Installation | 2020-11-24 07:00 | 2020-12-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C1.C4180: FS, MDC1.C2.C2160: FS | MDC1.C2.C4170: FS, MDC1.C2.C2260: FS, MDC1.C2.C2390: FS, MDC1.C2.C2240: FF 6, MDC1.C2.C2270: FS | VECA Electricians | 1440 | 0 |  | ['1040: FS', '995: FS'] | ['817: FS', '830: FS', '673: FS', '855: FF 6', '816: FS']
898 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull- UMS to COLO-3 | 2020-12-03 07:00 | 2020-12-11 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 13 | 13 |  |  |  |  | MDC1.C3.C3040: FS, MDC1.C3.C1040: FS, MDC1.S.1550: FS, MDC1.S.1270: FS, MDC1-1996: FS | MDC1.S.1820: FS | VECA Electricians | 420 | 0 |  | ['998: FS', '1074: FS', '956: FS', '1143: FS', '1134: FS'] | ['727: FS']
899 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2020-11-25 08:00 | 2020-12-11 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C1280: FS, MDC1.C1.C1300: FS | MDC1.C1.C1420: FS | VECA Electricians | 560 | 0 |  | ['1026: FS', '983: FS'] | ['818: FS']
900 | Not Started | MDC1-BL.5.3.2.4.4 | Task Dependent | Mechanical Ductwork Installation | 2020-11-16 07:00 | 2020-12-10 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 35 | 35 |  |  |  |  | MDC1AD-1016: FS, MDC1AD-1021.1: FS | MDC1AD-1023: FS, MDC1AD-1025: FS | TCM | 360 | 0 |  | ['1129: FS', '1045: FS'] | ['757: FS', '675: FS']
901 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-12-07 07:00 | 2020-12-10 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 12 | 12 |  |  |  |  | MDC1.C4.C1030: FS, MDC1.C4.E1010: FS, MDC1.C4.E1000: FS | MDC1.S.1770: FS, MDC1.S.1740: FS, MDC1.S.1720: FS | VECA Electricians | 80 | 0 |  | ['942: FS', '118: FS', '117: FS'] | ['763: FS', '811: FS', '809: FS']
902 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-12-07 07:00 | 2020-12-10 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 12 | 12 |  |  |  |  | MDC1.C4.C2030: FS, MDC1.C4.E1020: FS, MDC1.C4.E1030: FS | MDC1.S.1770: FS, MDC1.S.1710: FS, MDC1.S.1750: FS | VECA Electricians | 80 | 0 |  | ['943: FS', '121: FS', '122: FS'] | ['763: FS', '808: FS', '793: FS']
903 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Lift & Set MER in Place | 2020-12-04 07:00 | 2020-12-10 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C1.E1470: FS, MDC1.C1.E1230: FS, MDC1.C1.C4050: FS, MDC1.C1.C3210: FS | MDC1.C1.C4280: FS, MDC1.C1.C4340: FS, MDC1.C2.C1250: FS | VECA Electricians | 120 | 0 |  | ['44: FS', '1205: FS', '1222: FS', '981: FS'] | ['871: FS', '835: FS', '850: FS']
904 | Not Started | MDC1-BL.5.3.8.3.5.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C1070: FS | MDC1.C3.C1250: FS, MDC1.C3.C3090: FS | VECA Electricians | 960 | 0 |  | ['1003: FS'] | ['637: FS', '823: FS']
905 | Not Started | MDC1-BL.5.3.8.4.5.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C3.C1070: FS | MDC1.C3.C1330: FS, MDC1.C3.C1190: FS, MDC1.C3.Cx3020: FS | VECA Electricians | 240 | 0 |  | ['1003: FS'] | ['557: FS', '778: FS', '275: FS']
906 | Not Started | MDC1-BL.5.3.8.4.5.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C3.C1070: FS, MDC1.C3.E1140: FS, MDC1.C3.E1160: FS | MDC1.C3.C1180: FS | TCM | 480 | 0 |  | ['1003: FS', '69: FS', '85: FS'] | ['822: FS']
907 | Not Started | MDC1-BL.5.3.8.4.5.4 | Task Dependent | Fire Alarm System | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C3.C1080: FS | MDC1.C3.C1190: FS, MDC1-C3.P1800: FS | VECA Electricians | 240 | 0 |  | ['1004: FS'] | ['778: FS', '32: FS']
908 | Not Started | MDC1-BL.5.3.8.4.6.4 | Task Dependent | Fire Riser Installation | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 79 | 79 |  |  |  |  | MDC1.C3.C3030: FS | MDC1.C3.C3100: FS |  | 0 | 0 |  | ['1005: FS'] | ['824: FS']
909 | Not Started | MDC1-BL.5.3.8.3.7.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C2070: FS | MDC1.C3.C4110: FS, MDC1.C3.C2200: FS | VECA Electricians | 960 | 0 |  | ['1006: FS'] | ['826: FS', '779: FS']
910 | Not Started | MDC1-BL.5.3.8.4.7.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C3.C2070: FS | MDC1.C3.C2410: FS, MDC1.C3.C2210: FS, MDC1.C3.Cx3020: FS | VECA Electricians | 240 | 0 |  | ['1006: FS'] | ['454: FS', '780: FS', '275: FS']
911 | Not Started | MDC1-BL.5.3.8.4.7.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C3.C2070: FS, MDC1.C3.E1150: FS, MDC1.C3.E1170: FS | MDC1.C3.C2180: FS | TCM | 480 | 0 |  | ['1006: FS', '71: FS', '87: FS'] | ['825: FS']
912 | Not Started | MDC1-BL.5.3.8.4.7.4 | Task Dependent | Fire Alarm System | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C3.C2080: FS | MDC1.C3.C2210: FS | VECA Electricians | 240 | 0 |  | ['1007: FS'] | ['780: FS']
913 | Not Started | MDC1-BL.5.3.8.4.8.4 | Task Dependent | Fire Riser Installation | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 79 | 79 |  |  |  |  | MDC1.C3.C4030: FS | MDC1.C3.C4120: FS |  | 0 | 0 |  | ['1008: FS'] | ['827: FS']
914 | Not Started | MDC1-BL.5.3.9.4.10.1 | Task Dependent | HAC Installation | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 13 | 13 |  |  |  |  | MDC1.C2.C3110: FS | MDC1.C2.C3210: FS, MDC1.C2.C3260: FS | TCM | 480 | 0 |  | ['1001: FS'] | ['815: FS', '748: FS']
915 | Not Started | MDC1-BL.5.3.9.4.13.1 | Task Dependent | HAC Installation | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 13 | 13 |  |  |  |  | MDC1.C2.C4090: FS | MDC1.C2.C4170: FS | TCM | 480 | 0 |  | ['1002: FS'] | ['817: FS']
916 | Not Started | MDC1-BL.5.1.3.1.2.5 | Task Dependent | Duct Bank - Vault to COLO-3 UPM | 2020-12-04 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 2 | 2 |  |  |  |  | MDC1.S.1580: FS, MDC1.S.1460: FS, MDC1.C3.C3010: FS | MDC1.S.1640: FS, MDC1.S.1670: FS |  | 0 | 0 |  | ['952: FS', '1046: FS', '1055: FS'] | ['884: FS', '863: FS']
917 | Not Started | MDC1-BL.5.3.1.3.6.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 70 | 70 |  |  |  |  | MDC1.C1.C3200: FS | MDC1.C1.C3370: FS | VECA Electricians | 960 | 0 |  | ['1010: FS'] | ['781: FS']
918 | Not Started | MDC1-BL.5.3.1.4.6.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 88 | 88 |  |  |  |  | MDC1.C1.C3200: FS | MDC1.C1.C3420: FS, MDC1.C1.Cx3020: FS | VECA Electricians | 240 | 0 |  | ['1010: FS'] | ['700: FS', '436: FS']
919 | Not Started | MDC1-BL.5.3.1.4.6.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C3200: FS, MDC1.C1.E1390: FS, MDC1.C1.E1410: FS | MDC1.C1.C3340: FS | TCM | 480 | 0 |  | ['1010: FS', '62: FS', '78: FS'] | ['832: FS']
920 | Not Started | MDC1-BL.5.3.1.3.8.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 77 | 77 |  |  |  |  | MDC1.C1.C4190: FS, MDC1.C1.C4190: SS 5 | MDC1.C1.C4350: FS | VECA Electricians | 960 | 0 |  | ['1012: FS', '1012: SS 5'] | ['782: FS']
921 | Not Started | MDC1-BL.5.3.1.4.8.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 89 | 89 |  |  |  |  | MDC1.C1.C4190: FS | MDC1.C1.C4480: FS, MDC1.C1.Cx3020: FS | VECA Electricians | 240 | 0 |  | ['1012: FS'] | ['602: FS', '436: FS']
922 | Not Started | MDC1-BL.5.3.1.4.8.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C4190: FS, MDC1.C1.E1400: FS, MDC1.C1.E1420: FS | MDC1.C1.C4320: FS | TCM | 480 | 0 |  | ['1012: FS', '64: FS', '80: FS'] | ['833: FS']
923 | Not Started | MDC1-BL.5.3.9.3.5.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C1160: FS, MDC1.C2.C1160: SS 5 | MDC1.C2.C3190: FS, MDC1.C2.C1310: FS | VECA Electricians | 960 | 0 |  | ['1014: FS', '1014: SS 5'] | ['837: FS', '783: FS']
924 | Not Started | MDC1-BL.5.3.9.4.5.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 66 | 66 |  |  |  |  | MDC1.C2.C1090: FS, MDC1.C2.E1260: FS, MDC1.C2.E1280: FS | MDC1.C2.C1260: FS | TCM | 480 | 0 |  | ['1100: FS', '65: FS', '81: FS'] | ['836: FS']
925 | Not Started | MDC1-BL.5.3.9.4.5.4 | Task Dependent | Fire Alarm System | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C2.C1170: FS | MDC1.C2.C1320: FS, MDC1-C2.P1900: FS | VECA Electricians | 240 | 0 |  | ['1015: FS'] | ['784: FS', '31: FS']
926 | Not Started | MDC1-BL.5.3.9.4.6.4 | Task Dependent | Fire Riser Installation | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C2.C3100: FS | MDC1.C2.C3200: FS |  | 0 | 0 |  | ['1016: FS'] | ['838: FS']
927 | Not Started | MDC1-BL.5.3.9.3.7.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C2140: FS, MDC1.C2.C2140: SS 5 | MDC1.C2.C4150: FS, MDC1.C2.C2300: FS | VECA Electricians | 960 | 0 |  | ['1017: FS', '1017: SS 5'] | ['840: FS', '785: FS']
928 | Not Started | MDC1-BL.5.3.9.4.7.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 66 | 66 |  |  |  |  | MDC1.C2.C2070: FS, MDC1.C2.E1270: FS, MDC1.C2.E1290: FS | MDC1.C2.C2250: FS | TCM | 480 | 0 |  | ['1101: FS', '67: FS', '83: FS'] | ['839: FS']
929 | Not Started | MDC1-BL.5.3.9.4.7.4 | Task Dependent | Fire Alarm System | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C2.C2150: FS | MDC1.C2.C2320: FS, MDC1-C2.P1900: FS | VECA Electricians | 240 | 0 |  | ['1018: FS'] | ['787: FS', '31: FS']
930 | Not Started | MDC1-BL.5.3.9.4.8.4 | Task Dependent | Fire Riser Installation | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 43 | 43 |  |  |  |  | MDC1.C2.C4080: FS | MDC1.C2.C4160: FS |  | 0 | 0 |  | ['1019: FS'] | ['841: FS']
931 | Not Started | MDC1-BL.5.3.8.4.4.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C3.C4050: SS 6, MDC1.C3.C4020: FS | MDC1.C3.C4090: FS | CSI, VECA Electricians | 1440 | 0 |  | ['975: SS 6', '1022: FS'] | ['890: FS']
932 | Not Started | MDC1-BL.5.3.6.4.4.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 87 | 87 |  |  |  |  | MDC1.C4.C2000: FS | MDC1.C4.C4070: FS | TCM | 720 | 0 |  | ['1023: FS'] | ['756: FS']
933 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - COLO-4 UPM to UMS | 2020-12-03 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 14 | 14 |  |  |  |  | MDC1.S.1550: FS | MDC1.S.1740: FS | VECA Electricians | 240 | 0 |  | ['956: FS'] | ['811: FS']
934 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull - JAZ to URS | 2020-12-03 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 3 | 3 |  |  |  |  | MDC1.S.1250: FS, MDC1.S.1410: FS, MDC1-2189: FS, MDC1-2132: FS, MDC1.S.1560: FS, MDC1-1996: FS | MDC1.S.1700: FS, MDC1.S.1760: FS, MDC1.S.1640: FS | VECA Electricians | 240 | 0 |  | ['1162: FS', '1073: FS', '1226: FS', '1135: FS', '957: FS', '1134: FS'] | ['844: FS', '771: FS', '884: FS']
935 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -3 East UPMS | 2020-12-01 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 1 | 1 |  |  |  |  | MDC1.S.1510: FS, MDC1.S.1520: FS | MDC1.S.1850: FF, MDC1.S.1850: FS, MDC1.S.1840: FS, MDC1.S.1660: FS | VECA Electricians | 360 | 0 |  | ['992: FS', '978: FS'] | ['601: FF', '601: FS', '611: FS', '881: FS']
936 | Not Started | MDC1-BL.5.3.1.4.13.2 | Task Dependent | IDF Backbone Install | 2020-11-17 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 25 | 25 |  |  |  |  | MDC1.C1.C4180: FS, MDC1.C1.C2230: FS | MDC1.C1.C4330: FS | LINX- TELECOM | 1440 | 0 |  | ['1040: FS', '1061: FS'] | ['834: FS']
937 | Not Started | MDC1-BL.4.10.2.1.3 | Finish Milestone | Pad Ready for MER COLO-3 Cell-3 |  | 2020-12-07 17:00 |  |  | 2020-12-07 17:00 |  | 0 | 0 | 0 | 0 | 51 | 51 |  |  |  |  | MDC1.C3.C3050: FS 5 | MDC1.C3.C3200: FS |  | 0 | 0 |  | ['973: FS 5'] | ['612: FS']
938 | Not Started | MDC1-BL.4.10.2.1.3 | Finish Milestone | Pad Ready for MER COLO-3 Cell-4 |  | 2020-12-07 17:00 |  |  | 2020-12-07 17:00 |  | 0 | 0 | 0 | 0 | 56 | 56 |  |  |  |  | MDC1.C3.C4050: FS 5 | MDC1.C3.C4270: FS |  | 0 | 0 |  | ['975: FS 5'] | ['582: FS']
939 | Not Started | MDC1-BL.3.1 | Finish Milestone | Grant County Permanent Power Required for CX |  | 2020-12-07 08:00 |  |  | 2020-12-07 08:00 |  | 0 | 0 | 0 | 0 | 30 | 30 | Finish On or After | 2020-12-07 08:00 |  |  | MDC1.C1.C1300: FS | MDC1.AD.Cx2000: FS, MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS, MDC1.S.1840: FS, MDC1.S.1850: FS |  | 0 | 0 |  | ['983: FS'] | ['640: FS', '645: FS', '30: FS', '611: FS', '601: FS']
940 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2020-11-20 07:00 | 2020-12-04 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C2270: FS | MDC1.C1.C2390: FS, MDC1.C1.C2420: FS, MDC1.C1.C4340: FS |  | 0 | 0 |  | ['1024: FS'] | ['860: FS', '796: FS', '835: FS']
941 | Not Started | MDC1-BL.5.3.1.4.13.1 | Task Dependent | PDU's Installation | 2020-12-02 07:00 | 2020-12-04 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 30 | 30 |  |  |  |  | MDC1.C1.C4210: FS, MDC1.C1.C4130: FS, MDC1.C1.E1450: FS, MDC1.C1.E1460: FS | MDC1.C1.C4390: FS, MDC1.C1.C4360: FS, MDC1.C1.C4310: FS, MDC1.C1.C4300: FS | VECA Electricians | 180 | 0 |  | ['960: FS', '1131: FS', '191: FS', '192: FS'] | ['737: FS', '777: FS', '859: FS', '873: FS']
942 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-12-01 07:00 | 2020-12-04 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 12 | 12 |  |  |  |  | MDC1.C4.C1020: FS | MDC1.C4.C1040: FS, MDC1.C4.E1000: FS | CSI, VECA Electricians | 480 | 0 |  | ['976: FS'] | ['901: FS', '117: FS']
943 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-12-01 07:00 | 2020-12-04 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 12 | 12 |  |  |  |  | MDC1.C4.C2020: FS | MDC1.C4.C2040: FS, MDC1.C4.E1030: FS | CSI, VECA Electricians | 480 | 0 |  | ['977: FS'] | ['902: FS', '122: FS']
944 | Not Started | MDC1-BL.5.3.1.4.10.2 | Task Dependent | IDF Backbone Install | 2020-11-13 07:00 | 2020-12-04 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 23 | 23 |  |  |  |  | MDC1.C1.C3190: FS, MDC1.C1.C1240: FS | MDC1.C1.C3330: FS | LINX- TELECOM | 1440 | 0 |  | ['1048: FS', '1060: FS'] | ['851: FS']
945 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2020-11-30 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 6 | 6 |  |  |  |  | MDC1.C1.C3050: FS, MDC1.C1.C3080: FS, MDC1.C1.C3210: FS, MDC1.C1.C1280: FS | MDC1.C1.C3350: FS, MDC1.C1.C3410: FS, MDC1.C1.C3390: FS | SURE STEEL | 160 | 0 |  | ['1220: FS', '1179: FS', '981: FS', '1026: FS'] | ['828: FS', '736: FS', '758: FS']
946 | Not Started | MDC1-BL.5.3.9.3.2.2 | Task Dependent | Datahall Finishes | 2020-11-19 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 41 | 41 |  |  |  |  | MDC1.C2.C3110: SS 6 | MDC1.C2.C3290: FS | PCI | 400 | 0 |  | ['1001: SS 6'] | ['717: FS']
947 | Not Started | MDC1-BL.5.3.9.4.6.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-17 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 63 | 63 |  |  |  |  | MDC1.C2.C3090: FS | MDC1.C2.C3300: FS, MDC1.C2.Cx3020: FS | VECA Electricians | 240 | 0 |  | ['1042: FS'] | ['708: FS', '321: FS']
948 | Not Started | MDC1-BL.5.3.9.4.2.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-11-17 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C2.C3120: SS 5 | MDC1.C2.Cx3030: FS, MDC1.C2.Cx3040: FS, MDC1.M2010: FS, MDC1.C2.Cx2050: FS | TCM | 720 | 0 |  | ['986: SS 5'] | ['305: FS', '286: FS', '280: FS', '462: FS']
949 | Not Started | MDC1-BL.5.3.9.4.3.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-11-17 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 71 | 71 |  |  |  |  | MDC1.C2.C2170: SS 5 | MDC1.C2.Cx2000: FS | TCM | 720 | 0 |  | ['987: SS 5'] | ['500: FS']
950 | Not Started | MDC1-BL.5.3.9.3.4.2 | Task Dependent | Datahall Finishes | 2020-11-19 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 41 | 41 |  |  |  |  | MDC1.C2.C4090: SS 6 | MDC1.C2.C4240: FS | PCI | 400 | 0 |  | ['1002: SS 6'] | ['718: FS']
951 | Not Started | MDC1-BL.5.3.9.4.8.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-17 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C2.C4070: FS | MDC1.C2.C4410: FS, MDC1.C2.Cx3020: FS, MDC1.C2.Cx2030: FS | VECA Electricians | 240 | 0 |  | ['1043: FS'] | ['503: FS', '321: FS', '464: FS']
952 | Not Started | MDC1-BL.5.1.3.1.1.2 | Task Dependent | Vault - Set South Vault along UPM to Vault | 2020-12-01 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 2 | 2 |  |  |  |  | MDC1.S.1340: FS, MDC1.C3.C4050: FS | MDC1.S.1770: FS, MDC1.S.1620: FS | VECA Electricians | 180 | 0 |  | ['1112: FS', '975: FS'] | ['763: FS', '916: FS']
953 | Not Started | MDC1-BL.5.3.1.4.9.3 | Task Dependent | Fire Alarm System | 2020-11-18 07:00 | 2020-12-02 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 111 | 111 |  |  |  |  | MDC1.C1.C1270: FS | MDC1.M1010: FS, MDC1-C1.P1900: FS | VECA Electricians | 600 | 0 |  | ['1034: FS'] | ['344: FS', '566: FS']
954 | Not Started | MDC1-BL.5.3.1.4.10.1 | Task Dependent | PDU's Installation | 2020-11-30 07:00 | 2020-12-02 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 28 | 28 |  |  |  |  | MDC1.C1.C3220: FS, MDC1.C1.C3120: FS, MDC1.C1.E1430: FS, MDC1.C1.E1440: FS | MDC1.C1.C3360: FS, MDC1.C1.C3400: FS, MDC1.C1.C3320: FS, MDC1.C1.C3310: FS | VECA Electricians | 180 | 0 |  | ['982: FS', '1130: FS', '187: FS', '188: FS'] | ['794: FS', '759: FS', '867: FS', '885: FS']
955 | Not Started | MDC1-BL.5.3.1.4.11.3 | Task Dependent | Fire Alarm System | 2020-11-18 07:00 | 2020-12-02 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 111 | 111 |  |  |  |  | MDC1.C1.C2250: FS, MDC1.C1.C2250: FF | MDC1.M1010: FS, MDC1-C1.P1900: FS | VECA Electricians | 600 | 0 |  | ['1035: FS', '1035: FF'] | ['344: FS', '566: FS']
956 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - south vault (along UMS duct run) to UMS | 2020-11-18 07:00 | 2020-12-02 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.S.1470: FS | MDC1.S.1730: FS, MDC1.S.1650: FS, MDC1.S.1630: FS, MDC1.S.1590: FS | VECA Electricians | 600 | 0 |  | ['1038: FS'] | ['810: FS', '880: FS', '898: FS', '933: FS']
957 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-3 Cell 2- Cell - 4 | 2020-12-01 07:00 | 2020-12-02 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 3 | 3 |  |  |  |  | MDC1.S.1220: FS, MDC1.S.1440: FF, MDC1.S.1440: FS, MDC1.C3.C2040: FS, MDC1.C3.C4040: FS, MDC1.S.1520: FS, MDC1-1996: FS | MDC1.S.1660: FS, MDC1.S.1750: FF, MDC1.S.1750: FS, MDC1.S.1600: FS | VECA Electricians | 120 | 0 |  | ['1177: FS', '1058: FF', '1058: FS', '1075: FS', '999: FS', '978: FS', '1134: FS'] | ['881: FS', '793: FF', '793: FS', '934: FS']
958 | Not Started | MDC1-BL.5.3.8.3.2.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-11-23 07:00 | 2020-12-01 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 29 | 29 |  |  |  |  | MDC1.C3.C1090: FS | MDC1.C3.C1210: FS, MDC1.C4.C1140: FS, MDC1.C3.C3180: FS | TCM, VECA Electricians | 800 | 0 |  | ['996: FS'] | ['690: FS', '627: FS', '653: FS']
959 | Not Started | MDC1-BL.5.3.8.3.4.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-11-23 07:00 | 2020-12-01 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 29 | 29 |  |  |  |  | MDC1.C3.C2090: FF, MDC1.C3.C2090: FS | MDC1.C3.C2240: FS, MDC1.C4.C2140: FS, MDC1.C3.C4220: FS | TCM, VECA Electricians | 800 | 0 |  | ['997: FF', '997: FS'] | ['691: FS', '631: FS', '654: FS']
960 | Not Started | MDC1-BL.5.3.1.4.13.1 | Task Dependent | Power Bus Installation | 2020-11-17 07:00 | 2020-12-01 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 30 | 30 |  |  |  |  | MDC1.C1.C4180: FS | MDC1.C1.C4220: FS, MDC1.C1.Cx2050: FS, MDC1.C1.E1450: FS | VECA Electricians | 1200 | 0 |  | ['1040: FS'] | ['941: FS', '587: FS', '191: FS']
961 | Not Started | MDC1-BL.5.1.9 | Task Dependent | Telecom-RNG Fiber underground installation | 2020-09-28 07:00 | 2020-12-01 17:00 |  |  |  |  | 0 | 0 | 50 | 50 | 79 | 79 |  |  |  |  | MDC1.S.1160: FS | MDC1.S.1830: FS | LINX- TELECOM | 5000 | 0 |  | ['1215: FS'] | ['652: FS']
962 | Not Started | MDC1-BL.5.3.1.3.5.2 | Task Dependent | Mechanical Corridor Finishes | 2020-11-05 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 118 | 118 |  |  |  |  | MDC1.C1.C1210: FS, MDC1.C1.C1120: FS | MDC1.C1.C1470: FS, MDC1.C1.C1380: FS, MDC1.C1.C1370: FS | PCI | 180 | 0 |  | ['1081: FS', '1198: FS'] | ['661: FS', '865: FS', '864: FS']
963 | Not Started | MDC1-BL.5.3.1.4.5.4 | Task Dependent | Controls Installation | 2020-11-05 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 40 | 40 |  |  |  |  | MDC1.C1.C1220: FS, MDC1.C1.C1190: FS | MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS, MDC1-C1.P1800: SS | VECA Electricians | 720 | 0 |  | ['1082: FS', '1146: FS'] | ['645: FS', '30: FS', '30: SS']
964 | Not Started | MDC1-BL.5.3.1.4.9.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 28 | 28 |  |  |  |  | MDC1.C1.C1240: FS, MDC1.C1.C1200: FS | MDC1.C1.C1390: FS, MDC1.C1.C1430: SS 6, MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS | LINX- TELECOM | 1440 | 0 |  | ['1060: FS', '1109: FS'] | ['866: FS', '776: SS 6', '645: FS', '30: FS']
965 | Not Started | MDC1-BL.5.3.1.4.9.3 | Task Dependent | Controls Installation | 2020-11-18 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 40 | 40 |  |  |  |  | MDC1.C1.C1270: FS | MDC1.C1.C1450: FF, MDC1.C1.C1450: FS, MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS | VECA Electricians | 720 | 0 |  | ['1034: FS'] | ['714: FF', '714: FS', '645: FS', '30: FS']
966 | Not Started | MDC1-BL.5.3.1.4.6.4 | Task Dependent | Controls Installation | 2020-11-05 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 51 | 51 |  |  |  |  | MDC1.C1.C3170: FS | MDC1.C1.Cx2030: FS | VECA Electricians | 720 | 0 |  | ['1086: FS'] | ['596: FS']
967 | Not Started | MDC1-BL.5.3.1.3.7.2 | Task Dependent | Mechanical Corridor Finishes | 2020-11-05 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 106 | 106 |  |  |  |  | MDC1.C1.C2190: FS, MDC1.C1.C2110: SS | MDC1.C1.C2470: FS, MDC1.C1.C2360: FS, MDC1.C1.C2350: FS | PCI | 180 | 0 |  | ['1087: FS', '1199: SS'] | ['662: FS', '869: FS', '868: FS']
968 | Not Started | MDC1-BL.5.3.1.4.7.4 | Task Dependent | Controls Installation | 2020-11-05 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 45 | 45 |  |  |  |  | MDC1.C1.C2200: FS, MDC1.C1.C2220: FS | MDC1.C1.Cx2010: FS | VECA Electricians | 720 | 0 |  | ['1088: FS', '1090: FS'] | ['623: FS']
969 | Not Started | MDC1-BL.5.3.1.4.11.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C2230: FS, MDC1.C1.C2180: FS | MDC1.C1.Cx2010: FF 6, MDC1.C1.C2370: FS | LINX- TELECOM | 1440 | 0 |  | ['1061: FS', '1110: FS'] | ['623: FF 6', '870: FS']
970 | Not Started | MDC1-BL.5.3.1.4.11.3 | Task Dependent | Controls Installation | 2020-11-18 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 45 | 45 |  |  |  |  | MDC1.C1.C2250: FS | MDC1.C1.C2400: FS, MDC1.C1.Cx2010: FS | VECA Electricians | 720 | 0 |  | ['1035: FS'] | ['821: FS', '623: FS']
971 | Not Started | MDC1-BL.5.3.9.4.4.4 | Task Dependent | Fire Alarm Installation | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 72 | 72 |  |  |  |  | MDC1.C2.C4060: FS, MDC1.C2.C4040: FS, MDC1.C2.C4050: FS, MDC1-2527: FS | MDC1.C2.C4400: FS, MDC1-C2.P1900: FS | VECA Electricians | 240 | 0 |  | ['1053: FS', '1125: FS', '1096: FS', '1325: FS'] | ['502: FS', '31: FS']
972 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 64 | 64 |  |  |  |  | MDC1.C3.C1050: FS, MDC1.C3.E1040: FS, MDC1.C3.E1050: FS | MDC1.C3.C1380: FS, MDC1.C3.C1360: FS, MDC1.C3.C1420: FS, MDC1.C3.C1200: FS, MDC1.C3.C1400: FS | VECA Electricians | 480 | 0 |  | ['1054: FS', '169: FS', '170: FS'] | ['514: FS', '527: FS', '440: FS', '768: FS', '476: FS']
973 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 51 | 51 |  |  |  |  | MDC1.C3.C3010: FS | MDC1.C3.C3230: FS, MDC1.C3.C3080: FS, MDC1.C3.E1260: FS 5, MDC1.C3.C3200: FS, MDC1.C3.E1220: FS, MDC1.C3.C3350: SS, MDC1.C3.C3110: SS, MDC1.C3.C3370: SS, MDC1.C3.Cx2030: SS | CSI, VECA Electricians | 1440 | 0 |  | ['1055: FS'] | ['591: FS', '874: FS', '937: FS 5', '612: FS', '171: FS', '442: SS', '788: SS', '399: SS', '352: SS']
974 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 64 | 64 |  |  |  |  | MDC1.C3.C2050: FS, MDC1.C3.E1060: FS, MDC1.C3.E1070: FS | MDC1.C3.C2380: FS, MDC1.C3.C2350: FS, MDC1.C3.C2440: FS, MDC1.C3.C2190: FS, MDC1.C3.C2390: FS | VECA Electricians | 480 | 0 |  | ['1056: FS', '173: FS', '174: FS'] | ['485: FS', '528: FS', '420: FS', '799: FS', '477: FS']
975 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C4000: FS | MDC1.C3.C4070: SS 6, MDC1.C3.C4290: FS, MDC1.C3.C4100: FS, MDC1.C3.E1270: FS 5, MDC1.C3.C4270: FS, MDC1.C3.E1240: FS, MDC1.S.1580: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1057: FS'] | ['931: SS 6', '563: FS', '875: FS', '938: FS 5', '582: FS', '175: FS', '952: FS']
976 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Electrical Underground Rough-In | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C3010: FS, MDC1.C4.CS1060: FS | MDC1.C4.C3020: FS, MDC1-1958: SS, MDC1.C4.C1030: FS, MDC1.C4.C1060: FS | VECA Electricians | 960 | 0 |  | ['1055: FS', '1178: FS'] | ['877: FS', '236: SS', '942: FS', '876: FS']
977 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Electrical Underground Rough-In | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C4000: FS, MDC1.C4.CS1060: FS | MDC1.C4.C2060: FS, MDC1.C4.C4020: FS, MDC1.C4.C2030: FS, MDC1.S.1670: FS | VECA Electricians | 960 | 0 |  | ['1057: FS', '1178: FS'] | ['878: FS', '879: FS', '943: FS', '863: FS']
978 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull Cross Overs- COLO-3 CELL-3 to CELL-4 | 2020-11-25 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 1 | 1 |  |  |  |  | MDC1.S.1220: FS, MDC1.S.1420: FS, MDC1.C3.C3040: FS, MDC1.C3.C4040: FS, MDC1.S.1510: FS, MDC1-1996: FS | MDC1.S.1660: FS, MDC1.S.1610: FS, MDC1.S.1710: FS, MDC1.S.1560: FS | VECA Electricians | 120 | 0 |  | ['1177: FS', '1067: FS', '998: FS', '999: FS', '992: FS', '1134: FS'] | ['881: FS', '935: FS', '808: FS', '957: FS']
979 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -2 WEST UPMS | 2020-11-20 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 34 | 34 |  |  |  |  | MDC1.S.1440: FS, MDC1.S.1360: FS, MDC1.S.1420: FS, MDC1.S.1490: FS | MDC1.S.1850: FF, MDC1.S.1850: FS, MDC1.S.1840: FS | VECA Electricians | 360 | 0 |  | ['1058: FS', '1108: FS', '1067: FS', '1025: FS'] | ['601: FF', '601: FS', '611: FS']
980 | Not Started | MDC1-BL.5.3.2.3.2 | Task Dependent | Finishes | 2020-10-28 07:00 | 2020-11-25 17:00 |  |  |  |  | 0 | 0 | 24 | 24 | 44 | 44 |  |  |  |  | MDC1AD-1016: FS, MDC1AD-1024: FS | MDC1AD-1027: FS, MDC1AD-1025: FS, MDC1AD-1026: FS | TCM, PCI | 2160 | 0 |  | ['1129: FS', '1156: FS'] | ['845: FS', '675: FS', '846: FS']
981 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Lift & Set MER in Place | 2020-11-20 07:00 | 2020-11-25 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C1.E1380: FS, MDC1.C1.E1220: FS, MDC1.C1.C3050: FS, MDC1.C1.C2270: FS | MDC1.C1.C3300: FS, MDC1.C1.C3250: FS, MDC1.C1.C4270: FS | VECA Electricians | 120 | 0 |  | ['42: FS', '1204: FS', '1220: FS', '1024: FS'] | ['895: FS', '945: FS', '903: FS']
982 | Not Started | MDC1-BL.5.3.1.4.10.1 | Task Dependent | Power Bus Installation | 2020-11-13 07:00 | 2020-11-25 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 28 | 28 |  |  |  |  | MDC1.C1.C3190: FS, MDC1.C1.C1260: FS | MDC1.C1.C3240: FS, MDC1.C1.E1430: FS | VECA Electricians | 1200 | 0 |  | ['1048: FS', '1049: FS'] | ['954: FS', '187: FS']
983 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2020-11-12 08:00 | 2020-11-25 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C1250: FS | MDC1-P1050: FS, MDC1.C1.C1360: FS, MDC1.C1.C1410: FS |  | 0 | 0 |  | ['1051: FS'] | ['939: FS', '899: FS', '831: FS']
984 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2020-11-20 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 6 | 6 |  |  |  |  | MDC1.C1.C2050: FS, MDC1.C1.C2270: FS | MDC1.C1.C2390: FS, MDC1.C1.C2430: FS, MDC1.C1.C2420: FS, MDC1.C1.C4280: FS | SURE STEEL | 160 | 0 |  | ['1264: FS', '1024: FS'] | ['860: FS', '773: FS', '796: FS', '871: FS']
985 | Not Started | MDC1-BL.5.3.9.4.1.4 | Task Dependent | Fire Alarm Installation | 2020-11-10 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 64 | 64 |  |  |  |  | MDC1.C2.C1120: FS, MDC1.C2.C1080: FS | MDC1.C2.C1450: FS | VECA Electricians | 240 | 0 |  | ['1064: FS', '1122: FS'] | ['568: FS']
986 | Not Started | MDC1-BL.5.3.9.4.2.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-11-10 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 49 | 49 |  |  |  |  | MDC1.C2.C3070: FS, MDC1.C2.E1220: FS, MDC1.C2.E1230: FS | MDC1.C2.C3430: FS, MDC1.C2.C3150: SS 5, MDC1.C2.C3180: FS, MDC1.C2.C3440: FS | TCM | 720 | 0 |  | ['1065: FS', '135: FS', '136: FS'] | ['576: FS', '948: SS 5', '886: FS', '535: FS']
987 | Not Started | MDC1-BL.5.3.9.4.3.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-11-10 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 34 | 34 |  |  |  |  | MDC1.C2.C2110: FS, MDC1.C2.E1240: FS, MDC1.C2.E1250: FS | MDC1.C2.C2410: FS, MDC1.C2.C2180: SS 5, MDC1.C2.C2230: FS, MDC1.C2.C2430: FS | TCM | 720 | 0 |  | ['1066: FS', '137: FS', '138: FS'] | ['642: FS', '949: SS 5', '887: FS', '590: FS']
988 | Not Started | MDC1-BL.5.3.8.4.1.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-11-20 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 54 | 54 |  |  |  |  | MDC1.C3.C1060: FS | MDC1.C3.C1160: FS, MDC1.C3.E1180: FS | SURE STEEL | 160 | 0 |  | ['1020: FS'] | ['888: FS', '139: FS']
989 | Not Started | MDC1-BL.5.3.8.4.3.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-11-20 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 54 | 54 |  |  |  |  | MDC1.C3.C2060: FS | MDC1.C3.C2160: FS, MDC1.C3.E1200: FS | SURE STEEL | 160 | 0 |  | ['1021: FS'] | ['889: FS', '141: FS']
990 | Not Started | MDC1-BL.5.3.6.3.5.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-11-10 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 86 | 86 |  |  |  |  | MDC1.C4.CS1090: FS | MDC1.C4.C1130: FS, MDC1.C4.C3010: FS, MDC1.C4.C1200: FS, MDC1.C4.C1240: FS, MDC1.C4.C1050: FS | PCI | 480 | 0 |  | ['1062: FS'] | ['682: FS', '892: FS', '551: FS', '494: FS', '891: FS']
991 | Not Started | MDC1-BL.5.3.6.3.7.1 | Task Dependent | Frame & Hang Wall Partitions - Mechanical Corridor | 2020-11-10 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 86 | 86 |  |  |  |  | MDC1.C4.CS1090: FS | MDC1.C4.C2130: FS, MDC1.C4.C4010: FS, MDC1.C4.C2200: FS, MDC1.C4.C2230: FS, MDC1.C4.C2050: FS | PCI | 480 | 0 |  | ['1062: FS'] | ['683: FS', '894: FS', '553: FS', '496: FS', '893: FS']
992 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-3 - CELL-1 to Cell-3 | 2020-11-23 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 1 | 1 |  |  |  |  | MDC1.C3.C3040: FS, MDC1.C3.C1040: FS, MDC1-1996: FS | MDC1.S.1610: FS, MDC1.S.1520: FS | VECA Electricians | 120 | 0 |  | ['998: FS', '1074: FS', '1134: FS'] | ['935: FS', '978: FS']
993 | Not Started | MDC1-BL.5.3.2.4.5.4 | Task Dependent | Fire Alarm Installation | 2020-11-09 07:00 | 2020-11-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 42 | 42 |  |  |  |  | MDC1-1964: FS, MDC1-1963: FS | MDC1-1976: FS | VECA Electricians | 240 | 0 |  | ['1071: FS', '1217: FS'] | ['684: FS']
994 | Not Started | MDC1-BL.5.3.9.4.9.1 | Task Dependent | HAC Installation | 2020-11-09 07:00 | 2020-11-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C1110: FS | MDC1.C2.C1230: FS, MDC1.C2.C1270: FS | TCM | 480 | 0 |  | ['1069: FS'] | ['896: FS', '829: FS']
995 | Not Started | MDC1-BL.5.3.9.4.11.1 | Task Dependent | HAC Installation | 2020-11-09 07:00 | 2020-11-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C2100: FS | MDC1.C2.C2220: FS | TCM | 480 | 0 |  | ['1070: FS'] | ['897: FS']
996 | Not Started | MDC1-BL.5.3.8.3.1.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-11-17 07:00 | 2020-11-21 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 29 | 29 |  |  |  |  | MDC1.C2.C3090: FS, MDC1.C2.C3030: FS, MDC1.C3.CS1090: FS, MDC1-C3.P1500: FS | MDC1.C3.C3060: FS, MDC1.C3.C1210: FS | TCM, VECA Electricians | 800 | 0 |  | ['1042: FS', '1141: FS', '1140: FS', '16: FS'] | ['958: FS', '690: FS']
997 | Not Started | MDC1-BL.5.3.8.3.3.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-11-17 07:00 | 2020-11-21 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 29 | 29 |  |  |  |  | MDC1.C2.C4070: FS, MDC1.C2.C4020: FS | MDC1.C3.C4060: FF, MDC1.C3.C2240: FS, MDC1.C3.C4060: FS | TCM, VECA Electricians | 800 | 0 |  | ['1043: FS', '1142: FS'] | ['959: FF', '691: FS', '959: FS']
998 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-11-18 07:00 | 2020-11-21 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 1 | 1 |  |  |  |  | MDC1.C3.C3020: FS, MDC1.C3.E1080: FS, MDC1.C3.E1090: FS | MDC1.S.1640: FS, MDC1.S.1630: FS, MDC1.S.1510: FS, MDC1.S.1520: FS | VECA Electricians | 80 | 0 |  | ['1036: FS', '111: FS', '112: FS'] | ['884: FS', '898: FS', '992: FS', '978: FS']
999 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-11-18 07:00 | 2020-11-21 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 3 | 3 |  |  |  |  | MDC1.C3.C4010: FS, MDC1.C3.E1100: FS, MDC1.C3.E1110: FS | MDC1.S.1640: FS, MDC1.S.1520: FS, MDC1.S.1560: FS | VECA Electricians | 80 | 0 |  | ['1037: FS', '115: FS', '116: FS'] | ['884: FS', '978: FS', '957: FS']
1000 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | PULL- URS to COLO-2 | 2020-11-18 07:00 | 2020-11-21 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 13 | 13 |  |  |  |  | MDC1.C2.C4030: FS, MDC1.C2.C2020: FS, MDC1.C2.C3040: FS, MDC1.C2.C1030: FS, MDC1.S.1390: FS, MDC1.S.1280: FS, MDC1.S.1110: FS, MDC1.S.1480: FS, MDC1.S.1480: FF, MDC1-1996: FS | MDC1.S.1790: FS, MDC1.S.1640: FS | VECA Electricians | 240 | 0 |  | ['1139: FS', '1195: FS', '1138: FS', '1194: FS', '1080: FS', '1137: FS', '1251: FS', '1039: FS', '1039: FF', '1134: FS'] | ['765: FS', '884: FS']
1001 | Not Started | MDC1-BL.5.3.9.3.2.1 | Task Dependent | Hang Wall Partitions | 2020-11-11 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 13 | 13 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C2.C3090: SS 6 | MDC1.C2.C3130: SS 6, MDC1.C2.C3170: FS | PCI | 600 | 0 |  | ['1208: FS', '1042: SS 6'] | ['946: SS 6', '914: FS']
1002 | Not Started | MDC1-BL.5.3.9.3.4.1 | Task Dependent | Hang Wall Partitions | 2020-11-11 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 13 | 13 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C2.C4070: SS 6 | MDC1.C2.C4110: SS 6, MDC1.C2.C4140: FS | PCI | 600 | 0 |  | ['1208: FS', '1043: SS 6'] | ['950: SS 6', '915: FS']
1003 | Not Started | MDC1-BL.5.3.8.3.5.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-11-06 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C1030: FS | MDC1.C3.C1140: FS, MDC1.C3.C1130: FS, MDC1.C3.C3090: FS, MDC1.C3.C1120: FS, MDC1.C3.E1140: FS | TCM, VECA Electricians | 1360 | 0 |  | ['1078: FS'] | ['906: FS', '905: FS', '823: FS', '904: FS', '69: FS']
1004 | Not Started | MDC1-BL.5.3.8.4.5.4 | Task Dependent | Fire Riser Installation | 2020-11-06 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C3.C1030: FS | MDC1.C3.C1150: FS |  | 0 | 0 |  | ['1078: FS'] | ['907: FS']
1005 | Not Started | MDC1-BL.5.3.8.3.6.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-11-06 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 79 | 79 |  |  |  |  | MDC1.C3.CS1090: FS, MDC1.C3.C1030: FS | MDC1.C3.C3070: FS, MDC1.C3.C3160: FS, MDC1.C3.C3210: FS | PCI | 480 | 0 |  | ['1140: FS', '1078: FS'] | ['908: FS', '655: FS', '597: FS']
1006 | Not Started | MDC1-BL.5.3.8.3.7.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-11-06 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C2030: FS | MDC1.C3.C2140: FS, MDC1.C3.C2130: FS, MDC1.C3.C4110: FS, MDC1.C3.C2120: FS, MDC1.C3.E1150: FS | TCM, VECA Electricians | 1360 | 0 |  | ['1079: FS'] | ['911: FS', '910: FS', '826: FS', '909: FS', '71: FS']
1007 | Not Started | MDC1-BL.5.3.8.4.7.4 | Task Dependent | Fire Riser Installation | 2020-11-06 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C3.C2030: FS | MDC1.C3.C2150: FS |  | 0 | 0 |  | ['1079: FS'] | ['912: FS']
1008 | Not Started | MDC1-BL.5.3.8.3.8.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-11-06 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 79 | 79 |  |  |  |  | MDC1.C3.CS1090: FS, MDC1.C3.C2030: FS | MDC1.C3.C4200: FS, MDC1.C3.C4240: FS, MDC1.C3.C4080: FS | PCI | 480 | 0 |  | ['1140: FS', '1079: FS'] | ['657: FS', '599: FS', '913: FS']
1009 | Not Started | MDC1-BL.5.3.1.4.5.2 | Task Dependent | Hydronic Piping Installation | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 57 | 57 |  |  |  |  | MDC1.C1.C1230: FS | MDC1.C1.Cx2000: FF, MDC1-C1.P1800: FS | TCM | 480 | 0 |  | ['1083: FS'] | ['645: FF', '30: FS']
1010 | Not Started | MDC1-BL.5.3.1.3.6.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C1210: FS, MDC1.C1.CS1110: FS, MDC1.C1.C1170: FS, MDC1-2105: FS | MDC1.C1.C3290: FS, MDC1.C1.C3280: FS, MDC1.C1.C3270: FS, MDC1.C1.E1390: FS | TCM, VECA Electricians | 1360 | 0 |  | ['1081: FS', '1241: FS', '1144: FS', '1227: FS'] | ['919: FS', '918: FS', '917: FS', '62: FS']
1011 | Not Started | MDC1-BL.5.3.1.4.7.2 | Task Dependent | Hydronic Piping Installation | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 57 | 57 |  |  |  |  | MDC1.C1.C2210: FS | MDC1.C1.Cx2000: FF, MDC1-C1.P1800: FS | TCM | 480 | 0 |  | ['1089: FS'] | ['645: FF', '30: FS']
1012 | Not Started | MDC1-BL.5.3.1.3.8.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C2190: FS, MDC1.C1.CS1110: FS, MDC1.C1.C2160: FS, MDC1-2105: FS | MDC1.C1.C4250: FS, MDC1.C1.C4240: FS, MDC1.C1.C4230: FS, MDC1.C1.C4230: SS 5, MDC1.C1.E1400: FS | TCM, VECA Electricians | 1360 | 0 |  | ['1087: FS', '1241: FS', '1148: FS', '1227: FS'] | ['922: FS', '921: FS', '920: FS', '920: SS 5', '64: FS']
1013 | Not Started | MDC1-BL.5.3.1.4.8.4 | Task Dependent | Fire Alarm System | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 43 | 43 |  |  |  |  | MDC1.C1.C4160: FS | MDC1.C1.C4290: FS | VECA Electricians | 240 | 0 |  | ['1091: FS'] | ['872: FS']
1014 | Not Started | MDC1-BL.5.3.9.3.5.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C1100: FS | MDC1.C2.C1200: FS, MDC1.C2.C3190: FS, MDC1.C2.C1200: SS 5, MDC1.C2.E1260: FS | TCM, VECA Electricians | 1360 | 0 |  | ['1092: FS'] | ['923: FS', '837: FS', '923: SS 5', '65: FS']
1015 | Not Started | MDC1-BL.5.3.9.4.5.4 | Task Dependent | Fire Riser Installation | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C2.C1100: FS | MDC1.C2.C1220: FS |  | 0 | 0 |  | ['1092: FS'] | ['925: FS']
1016 | Not Started | MDC1-BL.5.3.9.3.6.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C2.C1100: FS | MDC1.C2.C3350: FS, MDC1.C2.C3400: FS, MDC1.C2.C3160: FS | PCI | 480 | 0 |  | ['1208: FS', '1092: FS'] | ['663: FS', '604: FS', '926: FS']
1017 | Not Started | MDC1-BL.5.3.9.3.7.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C2080: FS | MDC1.C2.C2190: FS, MDC1.C2.C4150: FS, MDC1.C2.C2190: SS 5, MDC1.C2.E1270: FS | TCM, VECA Electricians | 1360 | 0 |  | ['1094: FS'] | ['927: FS', '840: FS', '927: SS 5', '67: FS']
1018 | Not Started | MDC1-BL.5.3.9.4.7.4 | Task Dependent | Fire Riser Installation | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C2.C2080: FS | MDC1.C2.C2210: FS |  | 0 | 0 |  | ['1094: FS'] | ['929: FS']
1019 | Not Started | MDC1-BL.5.3.9.3.8.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 43 | 43 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C2.C2080: FS | MDC1.C2.C4300: FS, MDC1.C2.C4340: FS, MDC1.C2.C4130: FS | PCI | 480 | 0 |  | ['1208: FS', '1094: FS'] | ['664: FS', '606: FS', '930: FS']
1020 | Not Started | MDC1-BL.5.3.8.4.1.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C3.C1050: SS 6, MDC1.C3.C1000: FS, MDC1.C2.C1060: FS | MDC1.C3.C1100: FS, MDC1.C4.C1070: FS, MDC1.C4.C1070: FF, MDC1-C3.P1700: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1054: SS 6', '1202: FS', '1151: FS'] | ['988: FS', '842: FS', '842: FF', '39: FS']
1021 | Not Started | MDC1-BL.5.3.8.4.3.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C3.C2050: SS 6, MDC1.C3.C2020: FS | MDC1.C3.C2100: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1056: SS 6', '1097: FS'] | ['989: FS']
1022 | Not Started | MDC1-BL.5.3.8.4.4.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C3.C2020: FS | MDC1.C3.C4070: FS | TCM | 720 | 0 |  | ['1097: FS'] | ['931: FS']
1023 | Not Started | MDC1-BL.5.3.6.4.3.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 74 | 74 |  |  |  |  | MDC1.C4.C3000: FS | MDC1.C4.C2070: FS, MDC1.C4.C4000: FS | TCM | 720 | 0 |  | ['1098: FS'] | ['843: FS', '932: FS']
1024 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Lift & Set MER in Place | 2020-11-13 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C1.C2050: FS, MDC1.C1.E1150: FS, MDC1.C1.E1330: FS, MDC1.C1.C1250: FS | MDC1.C1.C2340: FS, MDC1.C1.C2280: FS, MDC1.C1.C3210: FS | VECA Electricians | 120 | 0 |  | ['1264: FS', '1250: FS', '43: FS', '1051: FS'] | ['940: FS', '984: FS', '981: FS']
1025 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -2 East UPMS | 2020-11-12 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 34 | 34 |  |  |  |  | MDC1.S.1400: FS, MDC1.S.1420: FS, MDC1.S.1450: FS | MDC1.S.1850: FS, MDC1.S.1840: FS, MDC1.S.1530: FS | VECA Electricians | 360 | 0 |  | ['1076: FS', '1067: FS', '1059: FS'] | ['601: FS', '611: FS', '979: FS']
1026 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2020-11-12 08:00 | 2020-11-19 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 5 | 5 |  |  |  |  | MDC1.C1.C1250: FS | MDC1.C1.C1360: FS, MDC1.C1.C1420: FS, MDC1.C1.C1410: FS, MDC1.C1.C3250: FS | SURE STEEL | 160 | 0 |  | ['1051: FS'] | ['899: FS', '818: FS', '831: FS', '945: FS']
1027 | Not Started | MDC1-BL.5.3.2.4.2 | Task Dependent | Domestic Water Piping | 2020-10-28 07:00 | 2020-11-18 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 50 | 50 |  |  |  |  | MDC1AD-1016: FS | MDC1AD-1022: FS | TCM | 360 | 0 |  | ['1129: FS'] | ['883: FS']
1028 | Not Started | MDC1-BL.5.3.9.3.1.2 | Task Dependent | Datahall Finishes | 2020-11-06 07:00 | 2020-11-18 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 57 | 57 |  |  |  |  | MDC1.C2.C1110: SS 6 | MDC1.C2.C1300: FS | PCI | 400 | 0 |  | ['1069: SS 6'] | ['797: FS']
1029 | Not Started | MDC1-BL.5.3.9.4.5.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-04 07:00 | 2020-11-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 63 | 63 |  |  |  |  | MDC1.C2.C1090: FS | MDC1.C2.C1350: FS, MDC1.C2.C1320: FS, MDC1.C2.Cx3020: FS | VECA Electricians | 240 | 0 |  | ['1100: FS'] | ['705: FS', '784: FS', '321: FS']
1030 | Not Started | MDC1-BL.5.3.9.3.3.2 | Task Dependent | Datahall Finishes | 2020-11-06 07:00 | 2020-11-18 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 51 | 51 |  |  |  |  | MDC1.C2.C2100: SS 6 | MDC1.C2.C2280: FS | PCI | 400 | 0 |  | ['1070: SS 6'] | ['798: FS']
1031 | Not Started | MDC1-BL.5.3.9.4.7.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-04 07:00 | 2020-11-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 63 | 63 |  |  |  |  | MDC1.C2.C2070: FS | MDC1.C2.C2440: FS, MDC1.C2.C2320: FS, MDC1.C2.Cx3020: FS | VECA Electricians | 240 | 0 |  | ['1101: FS'] | ['555: FS', '787: FS', '321: FS']
1032 | Not Started | MDC1-BL.4.10.2.1.3 | Finish Milestone | Pad Ready for MER COLO-3 Cell-1 |  | 2020-11-18 17:00 |  |  | 2020-11-18 17:00 |  | 0 | 0 | 0 | 0 | 52 | 52 |  |  |  |  | MDC1.C3.C1050: FS 5 | MDC1.C3.C1230: FS |  | 0 | 0 |  | ['1054: FS 5'] | ['659: FS']
1033 | Not Started | MDC1-BL.4.10.2.1.3 | Finish Milestone | Pad Ready for MER COLO-3 Cell-2 |  | 2020-11-18 17:00 |  |  | 2020-11-18 17:00 |  | 0 | 0 | 0 | 0 | 57 | 57 |  |  |  |  | MDC1.C3.C2050: FS 5 | MDC1.C3.C2260: FS |  | 0 | 0 |  | ['1056: FS 5'] | ['635: FS']
1034 | Not Started | MDC1-BL.5.3.1.4.9.1 | Task Dependent | PDU's Installation | 2020-11-13 07:00 | 2020-11-17 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 27 | 27 |  |  |  |  | MDC1.C1.C1260: FS, MDC1.C1.C1140: FS, MDC1.C1.E1340: FS, MDC1.C1.E1350: FS | MDC1.C1.C1450: FS, MDC1.C1.C1350: FS, MDC1.C1.C1340: FS, MDC1.C1.C1400: FS | VECA Electricians | 180 | 0 |  | ['1049: FS', '1172: FS', '185: FS', '186: FS'] | ['714: FS', '953: FS', '965: FS', '861: FS']
1035 | Not Started | MDC1-BL.5.3.1.4.11.1 | Task Dependent | PDU's Installation | 2020-11-13 07:00 | 2020-11-17 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 32 | 32 |  |  |  |  | MDC1.C1.C2240: FS, MDC1.C1.C2130: FS, MDC1.C1.E1360: FS, MDC1.C1.E1370: FS | MDC1.C1.C2380: FS, MDC1.C1.C2400: FS, MDC1.C1.C2330: FS, MDC1.C1.C2330: FF, MDC1.C1.C2320: FS | VECA Electricians | 180 | 0 |  | ['1050: FS', '1175: FS', '189: FS', '190: FS'] | ['862: FS', '821: FS', '955: FS', '955: FF', '970: FS']
1036 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-11-12 07:00 | 2020-11-17 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 1 | 1 |  |  |  |  | MDC1.C3.C3010: FS | MDC1.C3.C3040: FS, MDC1.C3.E1080: FS | CSI, VECA Electricians | 480 | 0 |  | ['1055: FS'] | ['998: FS', '111: FS']
1037 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-11-12 07:00 | 2020-11-17 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 3 | 3 |  |  |  |  | MDC1.C3.C4000: FS | MDC1.C3.C4040: FS, MDC1.C3.E1100: FS | CSI, VECA Electricians | 480 | 0 |  | ['1057: FS'] | ['999: FS', '115: FS']
1038 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - Vault to UMS- UMS to JAZ run | 2020-11-09 07:00 | 2020-11-17 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1.S.1210: FS, MDC1.S.1410: FS, MDC1-2133: FS, MDC1.S.1170: FS, MDC1.S.1370: FS | MDC1.S.1680: FS, MDC1.S.1550: FS | VECA Electricians | 420 | 0 |  | ['1187: FS', '1073: FS', '1136: FS', '1225: FS', '1103: FS'] | ['858: FS', '956: FS']
1039 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | PULL- URS to COLO-1 | 2020-11-12 07:00 | 2020-11-17 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 13 | 13 |  |  |  |  | MDC1.C1.C4040: FS, MDC1.C1.C2040: FS, MDC1.C1.C3040: FS, MDC1-1963: FS, MDC1.S.1390: FS, MDC1.S.1110: FS, MDC1.S.1260: FS, MDC1.S.1100: FS, MDC1.S.1310: FS, MDC1.S.1440: FS, MDC1-1996: FS | MDC1.S.1790: FS, MDC1.S.1500: FS, MDC1.S.1500: FF | VECA Electricians | 240 | 0 |  | ['1236: FS', '1271: FS', '1235: FS', '1217: FS', '1080: FS', '1251: FS', '1155: FS', '1255: FS', '1114: FS', '1058: FS', '1134: FS'] | ['765: FS', '1000: FS', '1000: FF']
1040 | Not Started | MDC1-BL.5.3.1.4.13.1 | Task Dependent | Cable Tray Installation | 2020-11-02 07:00 | 2020-11-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 17 | 17 |  |  |  |  | MDC1.C1.C2180: FS, MDC1.C1.C4140: FS, MDC1-2106: FS | MDC1.C1.C4260: FS, MDC1.C2.C2220: FS, MDC1.C1.C4210: FS, MDC1.C1.C4330: FS, MDC1.C1.C4380: FS | VECA Electricians | 1440 | 0 |  | ['1110: FS', '1119: FS', '1169: FS'] | ['936: FS', '897: FS', '960: FS', '834: FS', '750: FS']
1041 | Not Started | MDC1-BL.5.3.9.4.1.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-11-02 07:00 | 2020-11-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C2.C1120: SS 5 | MDC1.C2.Cx2010: FS | TCM | 720 | 0 |  | ['1064: SS 5'] | ['498: FS']
1042 | Not Started | MDC1-BL.5.3.9.3.2.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-11-04 07:00 | 2020-11-16 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 13 | 13 |  |  |  |  | MDC1.C2.C1090: FS, MDC1.C2.C3030: FS | MDC1.C2.C3250: FS, MDC1.C2.C3140: FS, MDC1.C3.C1090: FS, MDC1.C2.C3110: SS 6, MDC1.C2.E1340: FS | VECA Electricians | 1200 | 0 |  | ['1100: FS', '1141: FS'] | ['752: FS', '947: FS', '996: FS', '1001: SS 6', '82: FS']
1043 | Not Started | MDC1-BL.5.3.9.3.4.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-11-04 07:00 | 2020-11-16 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 13 | 13 |  |  |  |  | MDC1.C2.C2070: FS, MDC1.C2.C4020: FS | MDC1.C2.C4190: FS, MDC1.C2.C4120: FS, MDC1.C3.C2090: FS, MDC1.C2.C4090: SS 6 | VECA Electricians | 1200 | 0 |  | ['1101: FS', '1142: FS'] | ['754: FS', '951: FS', '997: FS', '1002: SS 6']
1044 | Not Started | MDC1-BL.5.3.2.4.5.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-10-31 07:00 | 2020-11-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 71 | 71 |  |  |  |  | MDC1-1964: SS 5 | MDC1.AD.Cx2000: FS | TCM | 720 | 0 |  | ['1071: SS 5'] | ['640: FS']
1045 | Not Started | MDC1-BL.5.3.2.4.4 | Task Dependent | Set Mechanical Equipment | 2020-10-28 07:00 | 2020-11-13 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 35 | 35 |  |  |  |  | MDC1AD-1016: FS | MDC1AD-1021: FS | TCM | 300 | 0 |  | ['1129: FS'] | ['900: FS']
1046 | Not Started | MDC1-BL.5.1.3.1.2.5 | Task Dependent | Duct Bank - Builing to South Vault- URS Run | 2020-11-06 07:00 | 2020-11-13 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 15 | 15 |  |  |  |  | MDC1.S.1390: FS, MDC1.C3.C1010: FS | MDC1.S.1770: FS, MDC1.S.1640: FS, MDC1.S.1620: FS |  | 0 | 0 |  | ['1080: FS', '1126: FS'] | ['763: FS', '884: FS', '916: FS']
1047 | Not Started | MDC1-BL.5.3.1.4.2.4 | Task Dependent | Fire Alarm Installation | 2020-10-30 07:00 | 2020-11-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 46 | 46 |  |  |  |  | MDC1.C1.C3130: FS, MDC1.C1.C3080: FS | MDC1.C1.C3450: FS | VECA Electricians | 240 | 0 |  | ['1117: FS', '1179: FS'] | ['669: FS']
1048 | Not Started | MDC1-BL.5.3.1.4.10.1 | Task Dependent | Cable Tray Installation | 2020-10-30 07:00 | 2020-11-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C1.C3140: FS, MDC1-2106: FS | MDC1.C1.C3260: FS, MDC1.C1.C3220: FS, MDC1.C1.C3360: FS, MDC1.C1.C3330: FS, MDC1.C1.C3380: FS | VECA Electricians | 1440 | 0 |  | ['1118: FS', '1169: FS'] | ['944: FS', '982: FS', '794: FS', '851: FS', '761: FS']
1049 | Not Started | MDC1-BL.5.3.1.4.9.1 | Task Dependent | Power Bus Installation | 2020-11-02 07:00 | 2020-11-12 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 27 | 27 |  |  |  |  | MDC1.C1.C1200: FS | MDC1.C1.C1270: FS, MDC1.C1.C3220: FS, MDC1.C1.E1340: FS | VECA Electricians | 1200 | 0 |  | ['1109: FS'] | ['1034: FS', '982: FS', '185: FS']
1050 | Not Started | MDC1-BL.5.3.1.4.11.1 | Task Dependent | Power Bus Installation | 2020-11-02 07:00 | 2020-11-12 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 32 | 32 |  |  |  |  | MDC1.C1.C2180: FS | MDC1.C1.C2250: FS, MDC1.C1.E1360: FS | VECA Electricians | 1200 | 0 |  | ['1110: FS'] | ['1035: FS', '189: FS']
1051 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Lift & Set MER in Place | 2020-11-06 08:00 | 2020-11-12 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C1.E1320: FS, MDC1.C1.E1140: FS, MDC1.C1.C1050: FS, MDC1-C1.P1600: FS, MDC1.S.1030: FS, MDC1.S.1040: FS, MDC1.S.1120: FS, MDC1.S.1130: FS, MDC1.S.1300: FS | MDC1.C1.C1280: FS, MDC1.C1.C1300: FS, MDC1.C1.C2270: FS | VECA Electricians | 120 | 0 |  | ['3: FS', '1249: FS', '1261: FS', '34: FS', '1316: FS', '1302: FS', '1196: FS', '1197: FS', '1113: FS'] | ['1026: FS', '983: FS', '1024: FS']
1052 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-10-29 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 59 | 59 |  |  |  |  | MDC1.C2.C3050: FS, MDC1.C2.E1160: FS, MDC1.C2.E1170: FS | MDC1.C2.C3380: FS, MDC1.C2.C3430: FS, MDC1.C2.C3450: FS, MDC1.C2.C3180: FS, MDC1.C2.C3440: FS | VECA Electricians | 480 | 0 |  | ['1123: FS', '163: FS', '164: FS'] | ['613: FS', '576: FS', '499: FS', '886: FS', '535: FS']
1053 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-10-29 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 64 | 64 |  |  |  |  | MDC1.C2.C4040: FS, MDC1.C2.E1180: FS, MDC1.C2.E1190: FS | MDC1.C2.C4370: FS, MDC1.C2.C4380: FS, MDC1.C2.C4390: FS, MDC1.C2.C4100: FS, MDC1.C2.C4400: FS | VECA Electricians | 480 | 0 |  | ['1125: FS', '167: FS', '168: FS'] | ['577: FS', '556: FS', '501: FS', '971: FS', '502: FS']
1054 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-10-29 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C3.C1010: FS, MDC1.C2.C1040: FS | MDC1.C3.C1060: SS 6, MDC1.C3.C1110: FS, MDC1-C3.P1600: FS, MDC1.C3.E1120: FS 5, MDC1.C3.C1230: FS, MDC1.C3.E1040: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1126: FS', '1181: FS'] | ['1020: SS 6', '972: FS', '38: FS', '1032: FS 5', '659: FS', '169: FS']
1055 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Electrical Underground Rough-In | 2020-10-29 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C1010: FS | MDC1.C3.C3050: FS, MDC1.C3.C3020: FS, MDC1.C4.C1020: FS, MDC1.S.1620: FS | VECA Electricians | 960 | 0 |  | ['1126: FS'] | ['973: FS', '1036: FS', '976: FS', '916: FS']
1056 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-10-29 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C3.C2000: FS | MDC1.C3.C2060: SS 6, MDC1.C3.C2290: FS, MDC1.C3.C2110: FS, MDC1.C3.E1130: FS 5, MDC1.C3.C2260: FS, MDC1.C3.E1060: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1127: FS'] | ['1021: SS 6', '615: FS', '974: FS', '1033: FS 5', '635: FS', '173: FS']
1057 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Electrical Underground Rough-In | 2020-10-29 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C2000: FS | MDC1.C3.C4050: FS, MDC1.C3.C4010: FS, MDC1.C4.C2020: FS | VECA Electricians | 960 | 0 |  | ['1127: FS'] | ['975: FS', '1037: FS', '977: FS']
1058 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-2 Cell 2- Cell - 4 | 2020-11-10 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 13 | 13 |  |  |  |  | MDC1.C2.C4030: FS, MDC1.C2.C2020: FS, MDC1.S.1050: FS, MDC1.S.1360: FF, MDC1.S.1360: FS, MDC1.C2.C2020: FF, MDC1.C2.C4030: FF, MDC1.S.1420: FS, MDC1-1996: FS | MDC1.S.1530: FS, MDC1.S.1560: FF, MDC1.S.1560: FS, MDC1.S.1480: FS | VECA Electricians | 120 | 0 |  | ['1139: FS', '1195: FS', '1293: FS', '1108: FF', '1108: FS', '1195: FF', '1139: FF', '1067: FS', '1134: FS'] | ['979: FS', '957: FF', '957: FS', '1039: FS']
1059 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -1 East UPMS | 2020-11-05 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 34 | 34 |  |  |  |  | MDC1.S.1290: FS, MDC1.S.1380: FS | MDC1.S.1850: FF, MDC1.S.1850: FS, MDC1.S.1840: FS, MDC1.S.1490: FS | VECA Electricians | 360 | 0 |  | ['1128: FS', '1099: FS'] | ['601: FF', '601: FS', '611: FS', '1025: FS']
1060 | Not Started | MDC1-BL.5.3.1.4.9.2 | Task Dependent | IDF Backbone Install | 2020-10-26 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 24 | 24 |  |  |  |  | MDC1.C1.C1200: SS 6 | MDC1.C1.C1330: FS, MDC1.C1.C3260: FS | LINX- TELECOM | 1440 | 0 |  | ['1109: SS 6'] | ['964: FS', '944: FS']
1061 | Not Started | MDC1-BL.5.3.1.4.11.2 | Task Dependent | IDF Backbone Install | 2020-10-26 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 28 | 28 |  |  |  |  | MDC1.C1.C2180: SS 6 | MDC1.C1.C2310: FS, MDC1.C1.C4260: FS | LINX- TELECOM | 1440 | 0 |  | ['1110: SS 6'] | ['969: FS', '936: FS']
1062 | Not Started | MDC1-BL.5.7.6.7.1.2 | Task Dependent | Slab on Grade | 2020-10-29 07:00 | 2020-11-09 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 68 | 68 |  |  |  |  | MDC1.C4.CS1080: FF, MDC1.C3.CS1090: FS, A1170: FS, MDC1-C4.P1400: FS | MDC1.C4.C4010: FS, MDC1.C4.C2010: FS, MDC1.C4.C3010: FS, MDC1.C4.C1010: FS, MDC1.C4.C4190: FS, MDC1.C4.C2220: FS, MDC1.C4.C3190: FS, MDC1.C4.C1220: FS, MDC1.C4.C1140: FS, MDC1-C4.P1500: FS | CSI | 800 | 0 |  | ['1121: FF', '1140: FS', '2: FS', '21: FS'] | ['894: FS', '991: FS', '892: FS', '990: FS', '506: FS', '549: FS', '505: FS', '548: FS', '627: FS', '20: FS']
1063 | Not Started | MDC1-BL.5.3.1.4.4.4 | Task Dependent | Fire Alarm Installation | 2020-10-27 07:00 | 2020-11-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C1.C4120: FS, MDC1.C1.C4090: FS | MDC1.C1.C4450: FS | VECA Electricians | 240 | 0 |  | ['1132: FS', '1180: FS'] | ['647: FS']
1064 | Not Started | MDC1-BL.5.3.9.4.1.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-10-27 07:00 | 2020-11-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C2.C1070: FS, MDC1.C2.E1140: FS, MDC1.C2.E1150: FS, MDC1-C2.P1700: FS | MDC1.C2.C1430: FS, MDC1.C2.C1130: SS 5, MDC1.C2.C1190: FS, MDC1.C2.C1450: FS | TCM | 720 | 0 |  | ['1133: FS', '133: FS', '134: FS', '37: FS'] | ['618: FS', '1041: SS 5', '985: FS', '568: FS']
1065 | Not Started | MDC1-BL.5.3.9.4.2.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-11-05 07:00 | 2020-11-09 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 49 | 49 |  |  |  |  | MDC1.C2.C3060: FS | MDC1.C2.C3120: FS, MDC1.C2.E1220: FS | SURE STEEL | 160 | 0 |  | ['1093: FS'] | ['986: FS', '135: FS']
1066 | Not Started | MDC1-BL.5.3.9.4.3.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-11-05 07:00 | 2020-11-09 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 34 | 34 |  |  |  |  | MDC1.C2.C2090: FS | MDC1.C2.C2170: FS, MDC1.C2.E1240: FS | SURE STEEL | 160 | 0 |  | ['1095: FS'] | ['987: FS', '137: FS']
1067 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull Cross Overs- COLO-2 CELL-3 to CELL-4 | 2020-11-07 07:00 | 2020-11-09 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 13 | 13 |  |  |  |  | MDC1.S.1220: FS, MDC1.S.1050: FS, MDC1.S.1290: FS, MDC1.C2.C2020: FS, MDC1.C2.C4030: FS, MDC1.S.1400: FS, MDC1-1996: FS | MDC1.S.1530: FS, MDC1.S.1490: FS, MDC1.S.1520: FS, MDC1.S.1440: FS | VECA Electricians | 120 | 0 |  | ['1177: FS', '1293: FS', '1128: FS', '1195: FS', '1139: FS', '1076: FS', '1134: FS'] | ['979: FS', '1025: FS', '978: FS', '1058: FS']
1068 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -1 WEST UPMS | 2020-11-03 07:00 | 2020-11-09 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 48 | 48 |  |  |  |  | MDC1.S.1360: FS, MDC1.S.1330: FS, MDC1.S.1290: FS | MDC1.S.1850: FF, MDC1.S.1850: FS, MDC1.S.1840: FS | VECA Electricians | 360 | 0 |  | ['1108: FS', '1116: FS', '1128: FS'] | ['601: FF', '601: FS', '611: FS']
1069 | Not Started | MDC1-BL.5.3.9.3.1.1 | Task Dependent | Hang Wall Partitions | 2020-10-30 07:00 | 2020-11-07 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 11 | 11 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C2.C1090: SS 6 | MDC1.C2.C1140: SS 6, MDC1.C2.C1180: FS | PCI | 600 | 0 |  | ['1208: FS', '1100: SS 6'] | ['1028: SS 6', '994: FS']
1070 | Not Started | MDC1-BL.5.3.9.3.3.1 | Task Dependent | Hang Wall Partitions | 2020-10-30 07:00 | 2020-11-07 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 11 | 11 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C2.C2070: SS 6 | MDC1.C2.C2120: SS 6, MDC1.C2.C2160: FS | PCI | 600 | 0 |  | ['1208: FS', '1101: SS 6'] | ['1030: SS 6', '995: FS']
1071 | Not Started | MDC1-BL.5.3.2.4.5.2 | Task Dependent | Set Exterior Mechanical CFCI Equipment | 2020-10-26 07:00 | 2020-11-07 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 42 | 42 |  |  |  |  | MDC1-1970: FS, MDC1-2016: FS 6 | MDC1-1971: SS 5, MDC1-1975: FS, MDC1-1976: FS | VECA Electricians | 480 | 0 |  | ['1230: FS', '1077: FS 6'] | ['1044: SS 5', '993: FS', '684: FS']
1072 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Set MV Gear (UMS) | 2020-11-04 07:00 | 2020-11-07 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 49 | 49 |  |  |  |  | MDC1.S.1370: FS, MDC1-2503: FS, MDC1-2509: FS, MDC1-1996: FS | MDC1.S.1850: FS | VECA Electricians | 240 | 0 |  | ['1103: FS', '217: FS', '223: FS', '1134: FS'] | ['601: FS']
1073 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - Vault To JAZ - URS to JAZ run | 2020-10-31 07:00 | 2020-11-07 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1.S.1320: FS, MDC1.S.1320: FF | MDC1.S.1600: FS, MDC1.S.1470: FS | VECA Electricians | 420 | 0 |  | ['1115: FS', '1115: FF'] | ['934: FS', '1038: FS']
1074 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-11-03 07:00 | 2020-11-06 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 13 | 13 |  |  |  |  | MDC1.C3.C1020: FS, MDC1.C3.E1000: FS, MDC1.C3.E1010: FS | MDC1.S.1640: FS, MDC1.S.1630: FS, MDC1.S.1510: FS | VECA Electricians | 80 | 0 |  | ['1105: FS', '109: FS', '110: FS'] | ['884: FS', '898: FS', '992: FS']
1075 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-11-03 07:00 | 2020-11-06 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 19 | 19 |  |  |  |  | MDC1.C3.C2010: FS, MDC1.C3.E1020: FS, MDC1.C3.E1030: FS | MDC1.S.1640: FS, MDC1.S.1560: FS | VECA Electricians | 80 | 0 |  | ['1106: FS', '113: FS', '114: FS'] | ['884: FS', '957: FS']
1076 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-2- CELL-1 to Cell-3 | 2020-11-05 07:00 | 2020-11-06 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 13 | 13 |  |  |  |  | MDC1.C2.C3040: FS, MDC1.C2.C1030: FS, MDC1.C2.C1030: FF, MDC1.C2.C3040: FF, MDC1.S.1380: FS, MDC1-1996: FS | MDC1.S.1490: FS, MDC1.S.1420: FS | VECA Electricians | 120 | 0 |  | ['1138: FS', '1194: FS', '1194: FF', '1138: FF', '1099: FS', '1134: FS'] | ['1025: FS', '1067: FS']
1077 | In Progress | MDC1-BL.4.14.2 | Task Dependent | Water treatment Skids Procurement | 2020-04-27 08:00 | 2020-11-06 12:00 | 2020-04-07 |  |  |  | 42.86 | 83 | 110 | 193 | 56 | 56 |  |  |  |  | MDC1-2002: FS 7 | MDC1-1964: FS 6 |  | 0 | 0 |  | ['58: FS 7'] | ['1071: FS 6']
1078 | Not Started | MDC1-BL.5.3.8.3.5.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-10-22 07:00 | 2020-11-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.CS1090: FS | MDC1.C3.C3030: FS, MDC1.C3.C1070: FS, MDC1.C3.C1250: FS, MDC1.C3.C1290: FS, MDC1.C3.C1080: FS | PCI | 480 | 0 |  | ['1140: FS'] | ['1005: FS', '1003: FS', '637: FS', '578: FS', '1004: FS']
1079 | Not Started | MDC1-BL.5.3.8.3.7.1 | Task Dependent | Frame & Hang Wall Partitions - Mechanical Corridor | 2020-10-22 07:00 | 2020-11-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.CS1090: FS | MDC1.C3.C2070: FS, MDC1.C3.C4030: FS, MDC1.C3.C2200: FS, MDC1.C3.C2220: FS, MDC1.C3.C2080: FS | PCI | 480 | 0 |  | ['1140: FS'] | ['1006: FS', '1008: FS', '779: FS', '697: FS', '1007: FS']
1080 | Not Started | MDC1-BL.5.1.3.1.2.5 | Task Dependent | Duct Bank - Building to North Vault URS run | 2020-10-29 07:00 | 2020-11-05 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 15 | 15 |  |  |  |  | MDC1.S.1240: FS, MDC1.S.1280: FS, MDC1.C3.C1010: FS | MDC1.S.1480: FS, MDC1.S.1500: FS, MDC1.S.1460: FS |  | 0 | 0 |  | ['1168: FS', '1137: FS', '1126: FS'] | ['1039: FS', '1000: FS', '1046: FS']
1081 | Not Started | MDC1-BL.5.3.1.3.5.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C1170: FS, MDC1.C1.C1120: FS, MDC1.C1.C1170: SS 5 | MDC1.C1.C1310: FS, MDC1.C1.C3200: FS | VECA Electricians | 960 | 0 |  | ['1144: FS', '1198: FS', '1144: SS 5'] | ['962: FS', '1010: FS']
1082 | Not Started | MDC1-BL.5.3.1.4.5.1 | Task Dependent | VFD'S Installation & Wiring | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 40 | 40 |  |  |  |  | MDC1.C1.C1170: FS | MDC1.C1.C1320: FS, MDC1.C1.C1470: FS, MDC1.C1.Cx3020: FS | VECA Electricians | 240 | 0 |  | ['1144: FS'] | ['963: FS', '661: FS', '436: FS']
1083 | Not Started | MDC1-BL.5.3.1.4.5.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 57 | 57 |  |  |  |  | MDC1.C1.C1170: FS, MDC1.C1.E1280: FS, MDC1.C1.E1300: FS | MDC1.C1.C1290: FS | TCM | 480 | 0 |  | ['1144: FS', '61: FS', '77: FS'] | ['1009: FS']
1084 | Not Started | MDC1-BL.5.3.1.4.2.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 69 | 69 |  |  |  |  | MDC1.C1.C3130: SS 5 | MDC1.C1.Cx2030: FS | TCM | 720 | 0 |  | ['1117: SS 5'] | ['596: FS']
1085 | Not Started | MDC1-BL.5.3.1.4.6.4 | Task Dependent | Fire Riser Installation | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 51 | 51 |  |  |  |  | MDC1.C1.C3110: FS | MDC1.C1.C3170: SS |  | 0 | 0 |  | ['1147: FS'] | ['1086: SS']
1086 | Not Started | MDC1-BL.5.3.1.4.6.4 | Task Dependent | Fire Alarm System | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 51 | 51 |  |  |  |  | MDC1.C1.C3160: SS | MDC1.C1.C3230: FS | VECA Electricians | 240 | 0 |  | ['1085: SS'] | ['966: FS']
1087 | Not Started | MDC1-BL.5.3.1.3.7.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C2160: FS, MDC1.C1.C2160: SS 5 | MDC1.C1.C2290: FS, MDC1.C1.C4190: FS | VECA Electricians | 960 | 0 |  | ['1148: FS', '1148: SS 5'] | ['967: FS', '1012: FS']
1088 | Not Started | MDC1-BL.5.3.1.4.7.1 | Task Dependent | VFD'S Installation & Wiring | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 45 | 45 |  |  |  |  | MDC1.C1.C2160: FS | MDC1.C1.C2300: FS, MDC1.C1.C2470: FS, MDC1.C1.Cx3020: FS | VECA Electricians | 240 | 0 |  | ['1148: FS'] | ['968: FS', '662: FS', '436: FS']
1089 | Not Started | MDC1-BL.5.3.1.4.7.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 57 | 57 |  |  |  |  | MDC1.C1.C2160: FS, MDC1.C1.E1290: FS, MDC1.C1.E1310: FS | MDC1.C1.C2260: FS | TCM | 480 | 0 |  | ['1148: FS', '63: FS', '79: FS'] | ['1011: FS']
1090 | Not Started | MDC1-BL.5.3.1.4.7.4 | Task Dependent | Fire Alarm System | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 45 | 45 |  |  |  |  | MDC1.C1.C2170: FS | MDC1.C1.C2300: FS | VECA Electricians | 240 | 0 |  | ['1149: FS'] | ['968: FS']
1091 | Not Started | MDC1-BL.5.3.1.4.8.4 | Task Dependent | Fire Riser Installation | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 43 | 43 |  |  |  |  | MDC1.C1.C4110: FS | MDC1.C1.C4200: FS |  | 0 | 0 |  | ['1150: FS'] | ['1013: FS']
1092 | Not Started | MDC1-BL.5.3.9.3.5.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C1.C3110: FS | MDC1.C2.C1160: FS, MDC1.C2.C3100: FS, MDC1.C2.C1310: FS, MDC1.C2.C1360: FS, MDC1.C2.C1170: FS | PCI | 480 | 0 |  | ['1208: FS', '1147: FS'] | ['1014: FS', '1016: FS', '783: FS', '706: FS', '1015: FS']
1093 | Not Started | MDC1-BL.5.3.9.4.2.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 49 | 49 |  |  |  |  | MDC1.C2.C3050: SS 6, MDC1.C2.C3000: FS | MDC1.C2.C3070: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1123: SS 6', '1201: FS'] | ['1065: FS']
1094 | Not Started | MDC1-BL.5.3.9.3.7.1 | Task Dependent | Frame & Hang Wall Partitions - Mechanical Corridor | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C1.C4110: FS | MDC1.C2.C4080: FS, MDC1.C2.C2140: FS, MDC1.C2.C2300: FS, MDC1.C2.C2360: SS 6, MDC1.C2.C2150: FS | PCI | 480 | 0 |  | ['1208: FS', '1150: FS'] | ['1019: FS', '1017: FS', '785: FS', '709: SS 6', '1018: FS']
1095 | Not Started | MDC1-BL.5.3.9.4.3.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 34 | 34 |  |  |  |  | MDC1.C2.C2030: SS 6, MDC1.C2.C2050: FS | MDC1.C2.C2110: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1183: SS 6', '1152: FS'] | ['1066: FS']
1096 | Not Started | MDC1-BL.5.3.9.4.4.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 70 | 70 |  |  |  |  | MDC1.C2.C2050: FS | MDC1.C2.C4380: FS, MDC1.C2.C4100: FS, MDC1.C2.C4400: FS, MDC1.C2.Cx3030: FS, MDC1.C2.Cx2030: FS | TCM | 720 | 0 |  | ['1152: FS'] | ['556: FS', '971: FS', '502: FS', '305: FS', '464: FS']
1097 | Not Started | MDC1-BL.5.3.8.4.3.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C3.C3000: FS | MDC1.C3.C2060: FS, MDC1.C3.C4020: FS | TCM | 720 | 0 |  | ['1153: FS'] | ['1021: FS', '1022: FS']
1098 | Not Started | MDC1-BL.5.3.6.4.2.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 74 | 74 |  |  |  |  | MDC1.C4.C1000: FS | MDC1.C4.C3070: FS, MDC1.C4.C2000: FS | TCM | 720 | 0 |  | ['1154: FS'] | ['755: FS', '1023: FS']
1099 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-1 - CELL-1 to Cell-3 | 2020-11-03 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 13 | 13 |  |  |  |  | MDC1.C2.C1030: FS, MDC1.C2.C3040: FS, MDC1.C1.C3040: FS, MDC1.C1.C1040: FS, MDC1.C1.C3040: FF, MDC1.S.1360: FS, MDC1.S.1310: FS, MDC1-1996: FS | MDC1.S.1450: FS, MDC1.S.1400: FS | VECA Electricians | 120 | 0 |  | ['1194: FS', '1138: FS', '1235: FS', '1270: FS', '1235: FF', '1108: FS', '1114: FS', '1134: FS'] | ['1059: FS', '1076: FS']
1100 | Not Started | MDC1-BL.5.3.9.3.1.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-10-22 07:00 | 2020-11-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 11 | 11 |  |  |  |  | MDC1.C2.C3030: FS, MDC1.C2.C1050: FS | MDC1.C2.C1210: FS, MDC1.C2.C1150: FS, MDC1.C2.C3090: FS, MDC1.C2.C1110: SS 6 | VECA Electricians | 1200 | 0 |  | ['1141: FS', '1170: FS'] | ['924: FS', '1029: FS', '1042: FS', '1069: SS 6']
1101 | Not Started | MDC1-BL.5.3.9.3.3.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-10-22 07:00 | 2020-11-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 11 | 11 |  |  |  |  | MDC1.C2.C4020: FS, MDC1.C2.C2040: FS | MDC1.C2.C2200: FS, MDC1.C2.C2130: FS, MDC1.C2.C4070: FS, MDC1.C2.C2100: SS 6 | VECA Electricians | 1200 | 0 |  | ['1142: FS', '1171: FS'] | ['928: FS', '1031: FS', '1043: FS', '1070: SS 6']
1102 | Not Started | MDC1-BL.4.10.2.1.2 | Finish Milestone | Pad Ready for MER COLO-2 Cell-3 |  | 2020-11-03 17:00 |  |  | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 41 | 41 |  |  |  |  | MDC1.C2.C3050: FS 5 | MDC1.C2.C3230: FS |  | 0 | 0 |  | ['1123: FS 5'] | ['770: FS']
1103 | Not Started | MDC1-BL.5.1.3.1.1.1 | Task Dependent | Set UMS vault | 2020-10-27 08:00 | 2020-11-03 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 5 | 5 |  |  |  |  | MDC1-2133: FS, MDC1.S.1170: FS, MDC1-2190: FS | MDC1.S.1570: FS, MDC1.S.1680: FS, MDC1.S.1470: FS, MDC1-2503: FS | VECA Electricians | 480 | 0 |  | ['1136: FS', '1225: FS', '1248: FS'] | ['1072: FS', '858: FS', '1038: FS', '217: FS']
1104 | Not Started | MDC1-BL.4.10.2.1.2 | Finish Milestone | Pad Ready for MER COLO-2 Cell-4 |  | 2020-11-03 08:00 |  |  | 2020-11-03 08:00 |  | 0 | 0 | 0 | 0 | 69 | 69 |  |  |  |  | MDC1.C2.C4040: FS 4 | MDC1.C2.C4220: FS |  | 0 | 0 |  | ['1125: FS 4'] | ['734: FS']
1105 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-10-29 07:00 | 2020-11-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 13 | 13 |  |  |  |  | MDC1.C3.C1010: FS | MDC1.C3.C1040: FS, MDC1.C3.E1000: FS | CSI, VECA Electricians | 480 | 0 |  | ['1126: FS'] | ['1074: FS', '109: FS']
1106 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-10-29 07:00 | 2020-11-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 19 | 19 |  |  |  |  | MDC1.C3.C2000: FS | MDC1.C3.C2040: FS, MDC1.C3.E1020: FS | CSI, VECA Electricians | 480 | 0 |  | ['1127: FS'] | ['1075: FS', '113: FS']
1107 | Not Started | MDC1-BL.5.1.3.1.2.4 | Task Dependent | Duct Bank - COLO-4 UPM to UPM | 2020-10-29 07:00 | 2020-11-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 40 | 40 |  |  |  |  | MDC1.S.1220: FS, MDC1.C4.CS1030: FS, MDC1.C4.CS1050: FS, MDC1.C4.CS1070: FS | MDC1.S.1750: FS, MDC1.S.1710: FS |  | 0 | 0 |  | ['1177: FS', '1281: FS', '1238: FS', '1120: FS'] | ['793: FS', '808: FS']
1108 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-1 Cell 2- Cell - 4 | 2020-10-31 07:00 | 2020-11-02 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 13 | 13 |  |  |  |  | MDC1.C1.C2040: FS, MDC1.C1.C4040: FS, MDC1.S.1020: FS, MDC1.S.1330: FS, MDC1.S.1330: FF, MDC1-1996: FS | MDC1.S.1530: FS, MDC1.S.1430: FS, MDC1.S.1440: FF, MDC1.S.1440: FS, MDC1.S.1380: FS | VECA Electricians | 120 | 0 |  | ['1271: FS', '1236: FS', '1307: FS', '1116: FS', '1116: FF', '1134: FS'] | ['979: FS', '1068: FS', '1058: FF', '1058: FS', '1099: FS']
1109 | Not Started | MDC1-BL.5.3.1.4.9.1 | Task Dependent | Cable Tray Installation | 2020-10-17 07:00 | 2020-10-31 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 24 | 24 |  |  |  |  | MDC1.C1.C1150: FS, MDC1-2105: FS, MDC1-2106: FS | MDC1.C1.C1240: SS 6, MDC1.C1.C1260: FS, MDC1.C1.C1330: FS | VECA Electricians | 1440 | 0 |  | ['1165: FS', '1227: FS', '1169: FS'] | ['1060: SS 6', '1049: FS', '964: FS']
1110 | Not Started | MDC1-BL.5.3.1.4.11.1 | Task Dependent | Cable Tray Installation | 2020-10-17 07:00 | 2020-10-31 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 17 | 17 |  |  |  |  | MDC1.C1.C2150: FS, MDC1.C1.C2130: FS, MDC1-2106: FS | MDC1.C1.C2230: SS 6, MDC1.C1.C4180: FS, MDC1.C1.C2310: FS, MDC1.C1.C2240: FS, MDC1.C1.C2380: FS | VECA Electricians | 1440 | 0 |  | ['1166: FS', '1175: FS', '1169: FS'] | ['1061: SS 6', '1040: FS', '969: FS', '1050: FS', '862: FS']
1111 | Not Started | MDC1-BL.5.3.1.4.4.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-10-17 07:00 | 2020-10-31 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 76 | 76 |  |  |  |  | MDC1.C1.C4120: SS 5 | MDC1.C1.Cx2050: FS | TCM | 720 | 0 |  | ['1132: SS 5'] | ['587: FS']
1112 | Not Started | MDC1-BL.5.1.3.1.1.2 | Task Dependent | Vault - Set South Vault Along Vault to URS run | 2020-10-29 07:00 | 2020-10-31 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 23 | 23 |  |  |  |  | MDC1.S.1240: FS, MDC1.C3.C2000: FS | MDC1.S.1580: FS | VECA Electricians | 180 | 0 |  | ['1168: FS', '1127: FS'] | ['952: FS']
1113 | Not Started | MDC1-BL.5.1.4 | Task Dependent | Aggregate Road Base | 2020-09-24 07:00 | 2020-10-30 17:00 |  |  |  |  | 0 | 0 | 30 | 30 | 5 | 5 | Finish On or Before | 2020-11-23 17:00 |  |  | MDC1.S.1130: FS, MDC1.C4.CS1050: FS | MDC1.S.1880: FS, MDC1.S.1900: FS, MDC1.S.1870: FS, MDC1.C1.C1250: FS, MDC1.S.1860: FS | Advantage | 4000 | 0 |  | ['1197: FS', '1238: FS'] | ['297: FS', '257: FS', '348: FS', '1051: FS', '453: FS']
1114 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Set MV Gear (URS) | 2020-10-27 07:00 | 2020-10-30 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 15 | 15 |  |  |  |  | MDC1-2004: FS, MDC1.S.1170: FS, MDC1-2504: FS, MDC1-2510: FS, MDC1-1996: FS | MDC1.S.1840: FS, MDC1.S.1480: FS, MDC1.S.1380: FS | VECA Electricians | 240 | 0 |  | ['1193: FS', '1225: FS', '218: FS', '224: FS', '1134: FS'] | ['611: FS', '1039: FS', '1099: FS']
1115 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - URS to vault - URS to JAZ run | 2020-10-22 07:00 | 2020-10-30 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1.S.1270: FS, MDC1.S.1230: FS, MDC1.S.1270: FF | MDC1.S.1410: FS, MDC1.S.1410: FF | VECA Electricians | 420 | 0 |  | ['1143: FS', '1167: FS', '1143: FF'] | ['1073: FS', '1073: FF']
1116 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM Admin to COLO-1 Cell -2 | 2020-10-29 07:00 | 2020-10-30 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 13 | 13 |  |  |  |  | MDC1.S.1290: FS, MDC1.C1.C3040: FS, MDC1-1963: FS, MDC1.S.1100: FS, MDC1.S.1290: FF, MDC1-1996: FS | MDC1.S.1430: FS, MDC1.S.1360: FS, MDC1.S.1360: FF | VECA Electricians | 120 | 0 |  | ['1128: FS', '1235: FS', '1217: FS', '1255: FS', '1128: FF', '1134: FS'] | ['1068: FS', '1108: FS', '1108: FF']
1117 | Not Started | MDC1-BL.5.3.1.4.2.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-10-15 07:00 | 2020-10-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1.C1.C3100: FS, MDC1.C1.E1260: FS, MDC1.C1.E1270: FS | MDC1.C1.C3390: FS, MDC1.C1.C3150: SS 5, MDC1.C1.C3180: FS, MDC1.C1.C3450: FS | TCM | 720 | 0 |  | ['1174: FS', '127: FS', '128: FS'] | ['758: FS', '1084: SS 5', '1047: FS', '669: FS']
1118 | Not Started | MDC1-BL.5.3.1.4.10.1 | Task Dependent | HAC Installation | 2020-10-15 07:00 | 2020-10-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C1.C3090: FS | MDC1.C1.C3190: FS | TCM | 480 | 0 |  | ['1173: FS'] | ['1048: FS']
1119 | Not Started | MDC1-BL.5.3.1.4.13.1 | Task Dependent | HAC Installation | 2020-10-15 07:00 | 2020-10-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 19 | 19 |  |  |  |  | MDC1.C1.C4100: FS | MDC1.C1.C4180: FS | TCM | 480 | 0 |  | ['1176: FS'] | ['1040: FS']
1120 | Not Started | MDC1-BL.5.7.6.7.1.2 | Task Dependent | MEP Undeground Rough-In (Interior) | 2020-10-10 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 40 | 40 |  |  |  |  | MDC1.C3.CS1070: FF, MDC1.C4.CS1010: FS, MDC1.C3.CS1070: FS, MDC1.C4.CS1050: FS | MDC1.C4.CS1080: FF, MDC1-C4.P1400: FS, MDC1.S.1350: FS | TCM, VECA Electricians | 2100 | 0 |  | ['1189: FF', '1305: FS', '1189: FS', '1238: FS'] | ['1121: FF', '21: FS', '1107: FS']
1121 | Not Started | MDC1-BL.5.7.6.7.1.2 | Task Dependent | Aggregate Base Course | 2020-10-21 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 78 | 78 |  |  |  |  | MDC1.C4.CS1070: FF, MDC1.C4.CS1050: FS | MDC1.C4.CS1090: FF | CSI | 600 | 0 |  | ['1120: FF', '1238: FS'] | ['1062: FF']
1122 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-10-14 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 60 | 60 |  |  |  |  | MDC1.C2.C1040: FS, MDC1.C2.E1040: FS, MDC1.C2.E1050: FS | MDC1.C2.C1410: FS, MDC1.C2.C1430: FS, MDC1.C2.C1460: FS, MDC1.C2.C1190: FS, MDC1.C2.C1450: FS | VECA Electricians | 480 | 0 |  | ['1181: FS', '161: FS', '162: FS'] | ['660: FS', '618: FS', '544: FS', '985: FS', '568: FS']
1123 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-10-14 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 41 | 41 |  |  |  |  | MDC1.C2.C3010: FS | MDC1.C2.C3060: SS 6, MDC1.C2.C3270: FS, MDC1.C2.C3080: FS, MDC1.C2.E1210: FS 5, MDC1.C2.C3230: FS, MDC1.C2.E1160: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1182: FS'] | ['1093: SS 6', '732: FS', '1052: FS', '1102: FS 5', '770: FS', '163: FS']
1124 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-10-14 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 56 | 56 |  |  |  |  | MDC1.C2.C2030: FS, MDC1.C2.E1060: FS, MDC1.C2.E1070: FS | MDC1.C2.C2420: FS, MDC1.C2.C2410: FS, MDC1.C2.C2460: FS, MDC1.C2.C2230: FS, MDC1.C2.C2430: FS | VECA Electricians | 480 | 0 |  | ['1183: FS', '165: FS', '166: FS'] | ['636: FS', '642: FS', '545: FS', '887: FS', '590: FS']
1125 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-10-14 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 49 | 49 |  |  |  |  | MDC1.C2.C4000: FS | MDC1.C2.C4250: FS, MDC1.C2.C4060: FS, MDC1.C2.E1200: FS 4, MDC1.C2.C4220: FS, MDC1.C2.E1180: FS, MDC1.C2.C4380: FS, MDC1.C2.C4100: FS, MDC1.C2.C4400: FS, MDC1.C2.Cx3030: FS, MDC1.C2.Cx2030: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1184: FS'] | ['710: FS', '1053: FS', '1104: FS 4', '734: FS', '167: FS', '556: FS', '971: FS', '502: FS', '305: FS', '464: FS']
1126 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Electrical Underground Rough-In | 2020-10-14 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C3010: FS, MDC1.C3.CS1060: FS | MDC1.C3.C1050: FS, MDC1.C3.C3010: FS, MDC1-1957: SS, MDC1.C3.C1020: FS, MDC1.S.1390: FS, MDC1.S.1460: FS | VECA Electricians | 960 | 0 |  | ['1182: FS', '1233: FS'] | ['1054: FS', '1055: FS', '247: SS', '1105: FS', '1080: FS', '1046: FS']
1127 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Electrical Underground Rough-In | 2020-10-14 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C4000: FS, MDC1.C3.CS1060: FS | MDC1.C3.C2050: FS, MDC1.C3.C2010: FS, MDC1.C3.C4000: FS, MDC1.S.1340: FS | VECA Electricians | 960 | 0 |  | ['1184: FS', '1233: FS'] | ['1056: FS', '1106: FS', '1057: FS', '1112: FS']
1128 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull Cross Overs- COLO-1 CELL-3 to CELL-4 | 2020-10-27 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 13 | 13 |  |  |  |  | MDC1.C1.C4040: FS, MDC1.C1.C3040: FS, MDC1.S.1020: FS, MDC1-1996: FS | MDC1.S.1330: FS, MDC1.S.1430: FS, MDC1.S.1450: FS, MDC1.S.1420: FS, MDC1.S.1330: FF | VECA Electricians | 120 | 0 |  | ['1236: FS', '1235: FS', '1307: FS', '1134: FS'] | ['1116: FS', '1068: FS', '1059: FS', '1067: FS', '1116: FF']
1129 | Not Started | MDC1-BL.5.3.2.3.1 | Task Dependent | Hang Wall Partitions | 2020-10-06 07:00 | 2020-10-27 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 8 | 8 |  |  |  |  | MDC1.AD.CS1100: FS, MDC1-2101: FS, MDC1AD-1017: FS | MDC1AD-1018: FS, MDC1AD-1019: FS, MDC1AD-1020: FS, MDC1AD-1021: FS, MDC1AD-1021.1: FS, MDC1-2505: FS, MDC1-2506: FS, MDC1-2507: FS, MDC1-2508: FS | PCI | 900 | 0 |  | ['1279: FS', '1313: FS', '1203: FS'] | ['980: FS', '882: FS', '1027: FS', '900: FS', '1045: FS', '219: FS', '220: FS', '221: FS', '222: FS']
1130 | Not Started | MDC1-BL.5.3.1.3.2.2 | Task Dependent | Datahall Finishes | 2020-10-15 07:00 | 2020-10-27 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 52 | 52 |  |  |  |  | MDC1.C1.CS1120: FS, MDC1.C1.C3090: FS | MDC1.C1.C3240: FS | PCI | 400 | 0 |  | ['1231: FS', '1173: FS'] | ['954: FS']
1131 | Not Started | MDC1-BL.5.3.1.3.4.2 | Task Dependent | Datahall Finishes | 2020-10-15 07:00 | 2020-10-27 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 56 | 56 |  |  |  |  | MDC1.C1.CS1120: FS, MDC1.C1.C4100: FS | MDC1.C1.C4220: FS | PCI | 400 | 0 |  | ['1231: FS', '1176: FS'] | ['941: FS']
1132 | Not Started | MDC1-BL.5.3.1.4.4.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-10-12 07:00 | 2020-10-26 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C1.C4080: FS, MDC1.C1.E1240: FS, MDC1.C1.E1250: FS | MDC1.C1.C4410: FS, MDC1.C1.C4150: SS 5, MDC1.C1.C4170: FS, MDC1.C1.C4450: FS | TCM | 720 | 0 |  | ['1186: FS', '131: FS', '132: FS'] | ['715: FS', '1111: SS 5', '1063: FS', '647: FS']
1133 | Not Started | MDC1-BL.5.3.9.4.1.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-10-21 07:00 | 2020-10-26 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 50 | 50 |  |  |  |  | MDC1.C2.C1060: FS | MDC1.C2.C1120: FS, MDC1.C2.E1140: FS | SURE STEEL | 160 | 0 |  | ['1151: FS'] | ['1064: FS', '133: FS']
1134 | Not Started | MDC1-BL.4.11.5.1 | Task Dependent | MV Wire Procurement | 2020-08-04 08:00 | 2020-10-26 17:00 |  |  |  |  | 0 | 0 | 84 | 84 | 15 | 15 |  |  |  |  | MDC1-2002: FS, MDC1-2134: FS | MDC1.C2.Cx2010: FS, MDC1.S.1290: FS, MDC1.S.1330: FS, MDC1.S.1360: FS, MDC1.S.1310: FS, MDC1.S.1380: FS, MDC1.S.1400: FS, MDC1.S.1420: FS, MDC1.S.1440: FS, MDC1.S.1480: FS, MDC1.S.1500: FS, MDC1.S.1510: FS, MDC1.S.1520: FS, MDC1.S.1570: FS, MDC1.S.1560: FS, MDC1.S.1730: FS, MDC1.S.1650: FS, MDC1.S.1630: FS, MDC1.S.1600: FS, MDC1.S.1640: FS, MDC1.S.1680: FS, MDC1.S.1710: FS, MDC1.S.1720: FS, MDC1.S.1740: FS, MDC1.S.1750: FS, MDC1.S.1770: FS |  | 0 | 0 |  | ['58: FS', '1309: FS'] | ['498: FS', '1128: FS', '1116: FS', '1108: FS', '1114: FS', '1099: FS', '1076: FS', '1067: FS', '1058: FS', '1039: FS', '1000: FS', '992: FS', '978: FS', '1072: FS', '957: FS', '810: FS', '880: FS', '898: FS', '934: FS', '884: FS', '858: FS', '808: FS', '809: FS', '811: FS', '793: FS', '763: FS']
1135 | Not Started | MDC1-BL.4.11.5.4 | Task Dependent | MV Wire Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | 2020-08-04 08:00 | 2020-10-26 17:00 |  |  |  |  | 0 | 0 | 84 | 84 | 42 | 42 |  |  |  |  | MDC1-2134: FS | MDC1.S.1600: FS |  | 0 | 0 |  | ['1309: FS'] | ['934: FS']
1136 | Not Started | MDC1-BL.4.11.5.4 | Task Dependent | UMS Vault Procurement DRB#1 | 2020-08-04 08:00 | 2020-10-26 17:00 |  |  |  |  | 0 | 0 | 84 | 84 | 5 | 5 |  |  |  |  | MDC1-2134: FS, MDC1-2527: FS | MDC1.S.1370: FS, MDC1.S.1680: FS, MDC1.S.1470: FS |  | 0 | 0 |  | ['1309: FS', '1325: FS'] | ['1103: FS', '858: FS', '1038: FS']
1137 | Not Started | MDC1-BL.5.1.3.1.2.5 | Task Dependent | Duct Bank COLO-2 UPM to Vault | 2020-10-21 07:00 | 2020-10-26 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 17 | 17 |  |  |  |  | MDC1.S.1240: FS, MDC1.S.1260: FS | MDC1.S.1500: FS, MDC1.S.1390: FS |  | 0 | 0 |  | ['1168: FS', '1155: FS'] | ['1000: FS', '1080: FS']
1138 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-10-19 07:00 | 2020-10-22 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 21 | 21 |  |  |  |  | MDC1.C2.C3020: FS, MDC1.C2.E1080: FS, MDC1.C2.E1090: FS | MDC1.S.1500: FS, MDC1.S.1380: FS, MDC1.S.1400: FS, MDC1.S.1400: FF | VECA Electricians | 80 | 0 |  | ['1160: FS', '103: FS', '104: FS'] | ['1000: FS', '1099: FS', '1076: FS', '1076: FF']
1139 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-10-19 07:00 | 2020-10-22 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 25 | 25 |  |  |  |  | MDC1.C2.C4010: FS, MDC1.C2.E1100: FS, MDC1.C2.E1110: FS | MDC1.S.1500: FS, MDC1.S.1440: FS, MDC1.S.1420: FS, MDC1.S.1440: FF | VECA Electricians | 80 | 0 |  | ['1161: FS', '107: FS', '108: FS'] | ['1000: FS', '1058: FS', '1067: FS', '1058: FF']
1140 | Not Started | MDC1-BL.5.7.5.7.1.2 | Task Dependent | Slab on Grade | 2020-10-10 07:00 | 2020-10-21 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 49 | 49 |  |  |  |  | MDC1.C3.CS1080: FF, MDC1.C2.CS1090: FS, MDC1-C3.P1400: FS | MDC1.C3.C4030: FS, MDC1.C3.C2030: FS, MDC1.C3.C3030: FS, MDC1.C3.C1030: FS, MDC1.C3.C4230: FS, MDC1.C3.C2250: FS, MDC1.C3.C3190: FS, MDC1.C3.C1220: FS, MDC1.C4.CS1090: FS, MDC1.C3.C1090: FS, MDC1-C3.P1500: FS | CSI | 800 | 0 |  | ['1163: FF', '1208: FS', '17: FS'] | ['1008: FS', '1079: FS', '1005: FS', '1078: FS', '639: FS', '677: FS', '638: FS', '676: FS', '1062: FS', '996: FS', '16: FS']
1141 | Not Started | MDC1-BL.5.3.9.3.2.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-10-16 07:00 | 2020-10-21 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1.C2.C1050: FS | MDC1.C2.C1090: FS, MDC1.C3.C1090: FS, MDC1.C2.C3090: FS | TCM, VECA Electricians | 800 | 0 |  | ['1170: FS'] | ['1100: FS', '996: FS', '1042: FS']
1142 | Not Started | MDC1-BL.5.3.9.3.4.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-10-16 07:00 | 2020-10-21 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1.C2.C2040: FS | MDC1.C2.C2070: FS, MDC1.C3.C2090: FS, MDC1.C2.C4070: FS | TCM, VECA Electricians | 800 | 0 |  | ['1171: FS'] | ['1101: FS', '997: FS', '1043: FS']
1143 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - COLO-3 UPM to Vault UMS Run | 2020-10-17 07:00 | 2020-10-21 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.S.1230: FS | MDC1.S.1630: FS, MDC1.S.1320: FS, MDC1.S.1320: FF | VECA Electricians | 240 | 0 |  | ['1167: FS'] | ['898: FS', '1115: FS', '1115: FF']
1144 | Not Started | MDC1-BL.5.3.1.3.5.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C1120: FS, MDC1.C1.CS1110: FS, MDC1-C1.P1500: FS | MDC1.C1.C1230: FS, MDC1.C1.C1220: FS, MDC1.C1.C1210: FS, MDC1.C1.C1210: SS 5, MDC1.C1.C3200: FS, MDC1.C1.E1280: FS | TCM, VECA Electricians | 1360 | 0 |  | ['1198: FS', '1241: FS', '8: FS'] | ['1083: FS', '1082: FS', '1081: FS', '1081: SS 5', '1010: FS', '61: FS']
1145 | Not Started | MDC1-BL.5.3.1.4.5.4 | Task Dependent | Fire Riser Installation | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C1.C1120: FS | MDC1.C1.C1190: SS |  | 0 | 0 |  | ['1198: FS'] | ['1146: SS']
1146 | Not Started | MDC1-BL.5.3.1.4.5.4 | Task Dependent | Fire Alarm System | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C1.C1180: SS | MDC1.C1.C1320: FS | VECA Electricians | 240 | 0 |  | ['1145: SS'] | ['963: FS']
1147 | Not Started | MDC1-BL.5.3.1.3.6.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.CS1110: FS, MDC1.C1.C1120: FS | MDC1.C2.C1100: FS, MDC1.C1.C3370: SS, MDC1.C1.C3430: FS, MDC1.C1.C3160: FS | PCI | 480 | 0 |  | ['1241: FS', '1198: FS'] | ['1092: FS', '781: SS', '701: FS', '1085: FS']
1148 | Not Started | MDC1-BL.5.3.1.3.7.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C2110: FS, MDC1.C1.CS1110: FS | MDC1.C1.C2210: FS, MDC1.C1.C2200: FS, MDC1.C1.C2190: FS, MDC1.C1.C2190: SS 5, MDC1.C1.C4190: FS, MDC1.C1.E1290: FS | TCM, VECA Electricians | 1360 | 0 |  | ['1199: FS', '1241: FS'] | ['1089: FS', '1088: FS', '1087: FS', '1087: SS 5', '1012: FS', '63: FS']
1149 | Not Started | MDC1-BL.5.3.1.4.7.4 | Task Dependent | Fire Riser Installation | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 45 | 45 |  |  |  |  | MDC1.C1.C2110: FS | MDC1.C1.C2220: FS |  | 0 | 0 |  | ['1199: FS'] | ['1090: FS']
1150 | Not Started | MDC1-BL.5.3.1.3.8.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.CS1110: FS, MDC1.C1.C2110: FS | MDC1.C2.C2080: FS, MDC1.C1.C4350: SS, MDC1.C1.C4420: FS, MDC1.C1.C4160: FS | PCI | 480 | 0 |  | ['1241: FS', '1199: FS'] | ['1094: FS', '782: SS', '703: FS', '1091: FS']
1151 | Not Started | MDC1-BL.5.3.9.4.1.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C2.C1040: SS 6, MDC1.C2.C1000: FS, MDC1.C1.C1060: FS | MDC1.C2.C1070: FS, MDC1.C3.C1060: FS, MDC1-C2.P1700: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1181: SS 6', '1246: FS', '1262: FS'] | ['1133: FS', '1020: FS', '37: FS']
1152 | Not Started | MDC1-BL.5.3.9.4.3.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 34 | 34 |  |  |  |  | MDC1.C2.C3000: FS | MDC1.C2.C2090: FS, MDC1.C2.C4050: FS | TCM | 720 | 0 |  | ['1201: FS'] | ['1095: FS', '1096: FS']
1153 | Not Started | MDC1-BL.5.3.8.4.2.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C3.C1000: FS | MDC1.C3.C2020: FS, MDC1.C3.C3350: FS, MDC1.C3.C3110: FS, MDC1.C3.C3370: FS, MDC1.C3.Cx2030: FS | TCM | 720 | 0 |  | ['1202: FS'] | ['1097: FS', '442: FS', '788: FS', '399: FS', '352: FS']
1154 | Not Started | MDC1-BL.5.3.6.4.1.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 74 | 74 |  |  |  |  | MDC1.C3.C1000: FS | MDC1.C4.C1070: FS, MDC1.C4.C3000: FS | TCM | 720 | 0 |  | ['1202: FS'] | ['842: FS', '1098: FS']
1155 | Not Started | MDC1-BL.5.1.3.1.2.5 | Task Dependent | Duct Back- Admin UPM to Vault | 2020-10-14 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 17 | 17 |  |  |  |  | MDC1.S.1190: FS, MDC1.S.1100: FS, MDC1.S.1100: FF, MDC1.C2.C2000: FS, MDC1.C2.C4000: FS | MDC1.S.1480: FS, MDC1.S.1280: FS |  | 0 | 0 |  | ['1214: FS', '1255: FS', '1255: FF', '1224: FS', '1184: FS'] | ['1039: FS', '1137: FS']
1156 | Not Started | MDC1-BL.5.3.2.3.3 | Task Dependent | MEP Overhead | 2020-09-21 07:00 | 2020-10-19 17:00 |  |  |  |  | 0 | 0 | 24 | 24 | 50 | 50 |  |  |  |  | MDC1-2008: FS, MDC1.AD.CS1100: FS, MDC1-2102: FS, MDC1-2103: FS, MDC1-2104: FS, MDC1-2109: FS 21 | MDC1AD-1025: FS, MDC1AD-1018: FS | VECA Electricians | 2400 | 0 |  | ['1216: FS', '1279: FS', '1312: FS', '1308: FS', '1290: FS', '1285: FS 21'] | ['675: FS', '980: FS']
1157 | Not Started | MDC1-BL.4.10.2.1.2 | Finish Milestone | Pad Ready for MER COLO-2 Cell-1 |  | 2020-10-19 17:00 |  |  | 2020-10-19 17:00 |  | 0 | 0 | 0 | 0 | 42 | 42 |  |  |  |  | MDC1.C2.C1040: FS 5 | MDC1.C2.C1250: FS |  | 0 | 0 |  | ['1181: FS 5'] | ['850: FS']
1158 | Not Started | MDC1-BL.4.10.2.1.2 | Finish Milestone | Pad Ready for MER COLO-2 Cell-2 |  | 2020-10-19 17:00 |  |  | 2020-10-19 17:00 |  | 0 | 0 | 0 | 0 | 48 | 48 |  |  |  |  | MDC1.C2.C2030: FS 5 | MDC1.C2.C2290: FS |  | 0 | 0 |  | ['1183: FS 5'] | ['807: FS']
1159 | Not Started | MDC1-BL.5.3.1.4.1.4 | Task Dependent | Fire Alarm Installation | 2020-10-05 07:00 | 2020-10-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 56 | 56 |  |  |  |  | MDC1.C1.C1110: FS, MDC1.C1.C1090: FS | MDC1.C1.C1440: FS | VECA Electricians | 240 | 0 |  | ['1207: FS', '1218: FS'] | ['716: FS']
1160 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-10-14 07:00 | 2020-10-17 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 21 | 21 |  |  |  |  | MDC1.C2.C3010: FS | MDC1.C2.C3040: FS, MDC1.C2.E1080: FS | CSI, VECA Electricians | 480 | 0 |  | ['1182: FS'] | ['1138: FS', '103: FS']
1161 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-10-14 07:00 | 2020-10-17 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 25 | 25 |  |  |  |  | MDC1.C2.C4000: FS | MDC1.C2.C4030: FS, MDC1.C2.E1100: FS | CSI, VECA Electricians | 480 | 0 |  | ['1184: FS'] | ['1139: FS', '107: FS']
1162 | Not Started | MDC1-BL.5.1.3.1.1.1 | Task Dependent | Set URS Vault | 2020-10-09 07:00 | 2020-10-17 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 21 | 21 |  |  |  |  | MDC1-2004: FS | MDC1.S.1600: FS, MDC1-2504: FS | VECA Electricians | 480 | 0 |  | ['1193: FS'] | ['934: FS', '218: FS']
1163 | Not Started | MDC1-BL.5.7.5.7.1.2 | Task Dependent | Aggregate Base Course | 2020-10-10 07:00 | 2020-10-16 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 53 | 53 |  |  |  |  | MDC1.C3.CS1070: FF, MDC1.C3.CS1050: FS, MDC1-C3.P1400: FS | MDC1.C3.CS1090: FF | CSI | 600 | 0 |  | ['1189: FF', '1276: FS', '17: FS'] | ['1140: FF']
1164 | Not Started | MDC1-BL.5.3.1.4.3.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-10-02 07:00 | 2020-10-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 78 | 78 |  |  |  |  | MDC1.C1.C2120: SS 5 | MDC1.C1.Cx2010: FS | TCM | 720 | 0 |  | ['1185: SS 5'] | ['623: FS']
1165 | Not Started | MDC1-BL.5.3.1.4.9.1 | Task Dependent | HAC Installation | 2020-10-02 07:00 | 2020-10-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 24 | 24 |  |  |  |  | MDC1.C1.C1100: FS | MDC1.C1.C1200: FS | TCM | 480 | 0 |  | ['1211: FS'] | ['1109: FS']
1166 | Not Started | MDC1-BL.5.3.1.4.11.1 | Task Dependent | HAC Installation | 2020-10-02 07:00 | 2020-10-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 17 | 17 |  |  |  |  | MDC1.C1.C2100: FS | MDC1.C1.C2180: FS | TCM | 480 | 0 |  | ['1212: FS'] | ['1110: FS']
1167 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - Vault to Vault along UMS duct Run - horseshoe | 2020-10-02 07:00 | 2020-10-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.S.1070: FS, MDC1.S.1140: FS, MDC1.S.1180: FS | MDC1.S.1270: FS, MDC1.S.1320: FS | VECA Electricians | 720 | 0 |  | ['1275: FS', '1237: FS', '1213: FS'] | ['1143: FS', '1115: FS']
1168 | Not Started | MDC1-BL.5.1.3.1.1.2 | Task Dependent | Vault - Set North Vault Along Vault to URS run | 2020-10-14 07:00 | 2020-10-16 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 20 | 20 |  |  |  |  | MDC1.S.1190: FS, MDC1.C2.C4000: FS | MDC1.S.1390: FS, MDC1.S.1280: FS, MDC1.S.1340: FS | VECA Electricians | 180 | 0 |  | ['1214: FS', '1184: FS'] | ['1080: FS', '1137: FS', '1112: FS']
1169 | Not Started | MDC1-BL.4.11.1.1 | Task Dependent | Design / Lead Time for Busway (OFCI Starline BOM Materials) | 2020-10-12 08:00 | 2020-10-16 16:00 |  |  |  |  | 0 | 0 | 5 | 5 | 21 | 21 | As Late As Possible |  |  |  | MDC1-2008: FS, MDC1-2003: FS | MDC1.C1.C1200: FS, MDC1.C1.C3190: FS, MDC1.C1.C2180: FS, MDC1.C1.C4180: FS |  | 0 | 0 |  | ['1216: FS', '59: FS'] | ['1109: FS', '1048: FS', '1110: FS', '1040: FS']
1170 | Not Started | MDC1-BL.5.3.9.3.1.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-10-10 07:00 | 2020-10-15 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1.C1.C3070: FS, MDC1.C1.C3010: FS, MDC1.C2.CS1090: FS, MDC1-C2.P1500: FS | MDC1.C2.C1090: FS, MDC1.C2.C3030: FS | TCM, VECA Electricians | 800 | 0 |  | ['1191: FS', '1257: FS', '1208: FS', '12: FS'] | ['1100: FS', '1141: FS']
1171 | Not Started | MDC1-BL.5.3.9.3.3.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-10-10 07:00 | 2020-10-15 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1.C1.C4070: FS, MDC1.C1.C4010: FS | MDC1.C2.C2070: FS, MDC1.C2.C4020: FS | TCM, VECA Electricians | 800 | 0 |  | ['1192: FS', '1258: FS'] | ['1101: FS', '1142: FS']
1172 | Not Started | MDC1-BL.5.3.1.3.1.2 | Task Dependent | Datahall Finishes | 2020-10-02 07:00 | 2020-10-14 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 51 | 51 |  |  |  |  | MDC1.C1.CS1120: FS, MDC1.C1.C1100: FS, MDC1-2529: FS | MDC1.C1.C1270: FS | PCI | 400 | 0 |  | ['1231: FS', '1211: FS', '1240: FS'] | ['1034: FS']
1173 | Not Started | MDC1-BL.5.3.1.3.2.1 | Task Dependent | Hang Wall Partitions | 2020-10-06 07:00 | 2020-10-14 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 23 | 23 |  |  |  |  | MDC1.C1.C3070: SS 6 | MDC1.C1.C3120: FS, MDC1.C1.C3140: FS | PCI | 600 | 0 |  | ['1191: SS 6'] | ['1130: FS', '1118: FS']
1174 | Not Started | MDC1-BL.5.3.1.4.2.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-10-10 07:00 | 2020-10-14 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 38 | 38 |  |  |  |  | MDC1.C1.C3060: FS | MDC1.C1.C3130: FS, MDC1.C1.E1260: FS | SURE STEEL | 160 | 0 |  | ['1190: FS'] | ['1117: FS', '127: FS']
1175 | Not Started | MDC1-BL.5.3.1.3.3.2 | Task Dependent | Datahall Finishes | 2020-10-02 07:00 | 2020-10-14 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 19 | 19 |  |  |  |  | MDC1.C1.CS1120: FS, MDC1.C1.C2100: FS | MDC1.C1.C2180: FS, MDC1.C1.C2250: FS | PCI | 400 | 0 |  | ['1231: FS', '1212: FS'] | ['1110: FS', '1035: FS']
1176 | Not Started | MDC1-BL.5.3.1.3.4.1 | Task Dependent | Hang Wall Partitions | 2020-10-06 07:00 | 2020-10-14 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 19 | 19 |  |  |  |  | MDC1.C1.CS1110: FS, MDC1.C1.C4070: SS 6 | MDC1.C1.C4130: FS, MDC1.C1.C4140: FS | PCI | 600 | 0 |  | ['1241: FS', '1192: SS 6'] | ['1131: FS', '1119: FS']
1177 | Not Started | MDC1-BL.5.1.3.1.2.4 | Task Dependent | Duct Bank - COLO-3 UPM to UPM | 2020-10-10 07:00 | 2020-10-14 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 32 | 32 |  |  |  |  | MDC1.S.1200: FS, MDC1.C3.CS1050: FS, MDC1.C4.CS1030: FS, MDC1.C3.CS1070: FS | MDC1.S.1560: FS, MDC1.S.1520: FS, MDC1.S.1420: FS, MDC1.S.1350: FS |  | 0 | 0 |  | ['1206: FS', '1276: FS', '1281: FS', '1189: FS'] | ['957: FS', '978: FS', '1067: FS', '1107: FS']
1178 | Not Started | MDC1-BL.5.7.6.7.2 | Task Dependent | Downspouts & Gutters | 2020-09-25 07:00 | 2020-10-13 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 24 | 24 |  |  |  |  | MDC1.C4.CS1050: FS, MDC1.C3.CS1060: FS, MDC1.C4.CS1040: SS, MDC1.C3.CS1040: SS, MDC1-C3.P1200: FS, MDC1.C2.CS1040: SS, MDC1.C1.CS1060: FS, MDC1.C2.CS1030: FS, MDC1.C2.CS1040: FS, MDC1.C3.CS1030: FS, MDC1.C3.CS1040: FS, MDC1.C4.CS1030: FS, MDC1.C4.CS1040: FS | MDC1.C4.C1020: FS, MDC1.C4.C2020: FS, MDC1.S.1900: FS, MDC1.S.1870: FS | SURE STEEL | 900 | 0 |  | ['1238: FS', '1233: FS', '1256: SS', '1283: SS', '26: FS', '1299: SS', '1324: FS', '1311: FS', '1299: FS', '1298: FS', '1283: FS', '1281: FS', '1256: FS'] | ['976: FS', '977: FS', '257: FS', '348: FS']
1179 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-09-29 07:00 | 2020-10-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 41 | 41 |  |  |  |  | MDC1.C1.C3050: FS, MDC1.C1.E1180: FS, MDC1.C1.E1190: FS | MDC1.C1.C3410: FS, MDC1.C1.C3390: FS, MDC1.C1.C3470: FS, MDC1.C1.C3180: FS, MDC1.C1.C3450: FS, MDC1.C1.C3250: FS | VECA Electricians | 480 | 0 |  | ['1220: FS', '155: FS', '156: FS'] | ['736: FS', '758: FS', '646: FS', '1047: FS', '669: FS', '945: FS']
1180 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-09-29 07:00 | 2020-10-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 58 | 58 |  |  |  |  | MDC1.C1.C4050: FS, MDC1.C1.E1200: FS, MDC1.C1.E1210: FS | MDC1.C1.C4440: FS, MDC1.C1.C4410: FS, MDC1.C1.C4470: FS, MDC1.C1.C4170: FS, MDC1.C1.C4450: FS | VECA Electricians | 480 | 0 |  | ['1222: FS', '159: FS', '160: FS'] | ['695: FS', '715: FS', '624: FS', '1063: FS', '647: FS']
1181 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-09-29 07:00 | 2020-10-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 42 | 42 |  |  |  |  | MDC1.C2.C1010: FS | MDC1.C2.C1060: SS 6, MDC1.C2.C1290: FS, MDC1.C3.C1050: FS, MDC1.C2.C1080: FS, MDC1-C2.P1600: FS, MDC1.C2.E1120: FS 5, MDC1.C2.C1250: FS, MDC1.C2.E1050: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1223: FS'] | ['1151: SS 6', '812: FS', '1054: FS', '1122: FS', '36: FS', '1157: FS 5', '850: FS', '162: FS']
1182 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Electrical Underground Rough-In | 2020-09-29 07:00 | 2020-10-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C1010: FS | MDC1.C2.C4000: SS, MDC1.C2.C3050: FS, MDC1.C2.C3020: FS, MDC1.C3.C1010: FS | VECA Electricians | 960 | 0 |  | ['1223: FS'] | ['1184: SS', '1123: FS', '1160: FS', '1126: FS']
1183 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-09-29 07:00 | 2020-10-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 46 | 46 |  |  |  |  | MDC1.C2.C2000: FS | MDC1.C2.C2090: SS 6, MDC1.C2.C2330: FS, MDC1.C2.C2060: FS, MDC1.C2.E1130: FS 5, MDC1.C2.C2290: FS, MDC1.C2.E1060: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1224: FS'] | ['1095: SS 6', '774: FS', '1124: FS', '1158: FS 5', '807: FS', '165: FS']
1184 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Electrical Underground Rough-In | 2020-09-29 07:00 | 2020-10-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C3010: SS | MDC1.C2.C4040: FS, MDC1.C2.C4010: FS, MDC1.C3.C2000: FS, MDC1.S.1260: FS, MDC1.S.1240: FS | VECA Electricians | 960 | 0 |  | ['1182: SS'] | ['1125: FS', '1161: FS', '1127: FS', '1155: FS', '1168: FS']
1185 | Not Started | MDC1-BL.5.3.1.4.3.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-09-26 07:00 | 2020-10-10 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 49 | 49 |  |  |  |  | MDC1.C1.C2070: FS, MDC1.C1.E1160: FS, MDC1.C1.E1170: FS | MDC1.C1.C2420: FS, MDC1.C1.C2140: SS 5, MDC1.C1.C2410: FS, MDC1.C1.C2450: FS | TCM | 720 | 0 |  | ['1232: FS', '129: FS', '130: FS'] | ['796: FS', '1164: SS 5', '813: FS', '694: FS']
1186 | Not Started | MDC1-BL.5.3.1.4.4.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-10-07 07:00 | 2020-10-10 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 48 | 48 |  |  |  |  | MDC1.C1.C4060: FS | MDC1.C1.C4120: FS, MDC1.C1.E1240: FS | SURE STEEL | 160 | 0 |  | ['1200: FS'] | ['1132: FS', '131: FS']
1187 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - JAZ to vault- UMS to JAZ run | 2020-10-02 07:00 | 2020-10-10 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 23 | 23 |  |  |  |  | MDC1.S.1170: FS, MDC1.S.1180: FS, MDC1-2131: FS, MDC1.S.1150: FS | MDC1.S.1680: FS, MDC1.S.1470: FS | VECA Electricians | 420 | 0 |  | ['1225: FS', '1213: FS', '1292: FS', '1234: FS'] | ['858: FS', '1038: FS']
1188 | Not Started | MDC1-BL.5.3.1.4.1.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-09-25 07:00 | 2020-10-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 79 | 79 |  |  |  |  | MDC1.C1.C1110: SS 5 | MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS | TCM | 720 | 0 |  | ['1207: SS 5'] | ['645: FS', '30: FS']
1189 | Not Started | MDC1-BL.5.7.5.7.1.2 | Task Dependent | MEP Undeground Rough-In (Interior) | 2020-09-22 07:00 | 2020-10-09 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 32 | 32 |  |  |  |  | MDC1.C2.CS1070: FS, MDC1.C3.CS1000: FS, MDC1.C3.CS1050: FS | MDC1.C4.CS1070: FF, MDC1.C3.CS1080: FF, MDC1.C4.CS1070: FS, MDC1-C3.P1400: FS, MDC1.S.1220: FS | TCM, VECA Electricians | 2100 | 0 |  | ['1242: FS', '1321: FS', '1276: FS'] | ['1120: FF', '1163: FF', '1120: FS', '17: FS', '1177: FS']
1190 | Not Started | MDC1-BL.5.3.1.4.2.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-09-25 07:00 | 2020-10-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1.C1.C3050: SS 6, MDC1.C1.C3030: SS 15 | MDC1.C1.C3100: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1220: SS 6', '1243: SS 15'] | ['1174: FS']
1191 | Not Started | MDC1-BL.5.3.1.3.2.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-09-28 07:00 | 2020-10-09 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 11 | 11 |  |  |  |  | MDC1.C1.C1080: FS, MDC1.C1.C3010: FS | MDC1.C2.C1050: FS, MDC1.C1.C3090: SS 6 | VECA Electricians | 1200 | 0 |  | ['1228: FS', '1257: FS'] | ['1170: FS', '1173: SS 6']
1192 | Not Started | MDC1-BL.5.3.1.3.4.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-09-28 07:00 | 2020-10-09 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 11 | 11 |  |  |  |  | MDC1.C1.C2080: FS, MDC1.C1.C4010: FS | MDC1.C2.C2040: FS, MDC1.C1.C4100: SS 6 | VECA Electricians | 1200 | 0 |  | ['1229: FS', '1258: FS'] | ['1171: FS', '1176: SS 6']
1193 | Not Started | MDC1-BL.4.11.5.1 | Task Dependent | URS Vault Procurement | 2020-07-17 08:00 | 2020-10-08 17:00 |  |  |  |  | 0 | 0 | 84 | 84 | 26 | 26 |  |  |  |  | MDC1-1997: FS, MDC1-2527: FS | MDC1.S.1310: FS, MDC1.C2.Cx2010: FS, MDC1.S.1250: FS |  | 0 | 0 |  | ['1346: FS', '1325: FS'] | ['1114: FS', '498: FS', '1162: FS']
1194 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-10-05 07:00 | 2020-10-08 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 33 | 33 |  |  |  |  | MDC1.C2.C1020: FS, MDC1.C2.E1000: FS, MDC1.C2.E1010: FS | MDC1.S.1500: FS, MDC1.S.1380: FS, MDC1.S.1400: FS, MDC1.S.1400: FF | VECA Electricians | 80 | 0 |  | ['1209: FS', '101: FS', '102: FS'] | ['1000: FS', '1099: FS', '1076: FS', '1076: FF']
1195 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-10-05 07:00 | 2020-10-08 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 37 | 37 |  |  |  |  | MDC1.C2.C2010: FS, MDC1.C2.E1020: FS, MDC1.C2.E1030: FS | MDC1.S.1500: FS, MDC1.S.1440: FS, MDC1.S.1420: FS, MDC1.S.1440: FF | VECA Electricians | 80 | 0 |  | ['1210: FS', '105: FS', '106: FS'] | ['1000: FS', '1058: FS', '1067: FS', '1058: FF']
1196 | In Progress | MDC1-BL.5.1.10 | Task Dependent | Site Water / Fire Loop | 2020-07-24 07:00 | 2020-10-07 17:00 | 2020-06-22 |  |  |  | 0 | 6 | 60 | 60 | 35 | 35 |  |  |  |  | MDC1-1997: FS, MDC1.S.1030: SS 30, MDC1.S.1130: SS 20 | MDC1.S.1910: FS, MDC1.C1.C1250: FS | Advantage | 3000 | 0 |  | ['1346: FS', '1316: SS 30', '1197: SS 20'] | ['260: FS', '1051: FS']
1197 | In Progress | MDC1-BL.5.1.10 | Task Dependent | Site Storm | 2020-06-29 07:00 | 2020-10-07 17:00 | 2020-06-15 |  |  |  | 13.75 | 11 | 69 | 80 | 5 | 5 |  |  |  |  | MDC1.S.1040: SS 30 | MDC1.S.1120: SS 20, MDC1.S.1300: FS, MDC1.C1.C1250: FS | Advantage | 4000 | 0 |  | ['1302: SS 30'] | ['1196: SS 20', '1113: FS', '1051: FS']
1198 | Not Started | MDC1-BL.5.3.1.3.5.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-09-22 07:00 | 2020-10-06 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1-C1.P1500: FS, MDC1.C1.CS1110: FS | MDC1.C1.C3110: FS, MDC1.C1.C1170: FS, MDC1.C1.C1210: FS, MDC1.C1.C1310: FS, MDC1.C1.C1370: FS, MDC1.C1.C1180: FS | PCI | 480 | 0 |  | ['8: FS', '1241: FS'] | ['1147: FS', '1144: FS', '1081: FS', '962: FS', '864: FS', '1145: FS']
1199 | Not Started | MDC1-BL.5.3.1.3.7.1 | Task Dependent | Frame & Hang Wall Partitions - Mechanical Corridor | 2020-09-22 07:00 | 2020-10-06 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.CS1110: FS | MDC1.C1.C4110: FS, MDC1.C1.C2160: FS, MDC1.C1.C2290: SS, MDC1.C1.C2350: FS, MDC1.C1.C2170: FS | PCI | 480 | 0 |  | ['1241: FS'] | ['1150: FS', '1148: FS', '967: SS', '868: FS', '1149: FS']
1200 | Not Started | MDC1-BL.5.3.1.4.4.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-09-22 07:00 | 2020-10-06 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C1.C4050: SS 6, MDC1.C1.C4030: FS | MDC1.C1.C4080: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1222: SS 6', '1245: FS'] | ['1186: FS']
1201 | Not Started | MDC1-BL.5.3.9.4.2.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-09-22 07:00 | 2020-10-06 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 34 | 34 |  |  |  |  | MDC1.C2.C1000: FS | MDC1.C2.C3060: FS, MDC1.C2.C2050: FS | TCM | 720 | 0 |  | ['1246: FS'] | ['1093: FS', '1152: FS']
1202 | Not Started | MDC1-BL.5.3.8.4.1.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-09-22 07:00 | 2020-10-06 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C2.C1000: FS | MDC1.C3.C1060: FS, MDC1.C3.C3000: FS, MDC1.C4.C1000: FS | TCM | 720 | 0 |  | ['1246: FS'] | ['1020: FS', '1153: FS', '1154: FS']
1203 | Not Started | MDC1-BL.5.3.2.3.1 | Task Dependent | MEP Rough-In / Wall & Ceiling | 2020-09-21 07:00 | 2020-10-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 8 | 8 |  |  |  |  | MDC1.AD.CS1100: FS, MDC1-C1.P1500: FS, MDC1-2104: FS, MDC1-2109: FS 21 | MDC1AD-1016: FS | PCI, TCM, VECA Electricians | 2880 | 0 |  | ['1279: FS', '8: FS', '1290: FS', '1285: FS 21'] | ['1129: FS']
1204 | Not Started | MDC1-BL.4.10.2.1.1 | Finish Milestone | Pad Ready for MER COLO-1 Cell-3 |  | 2020-10-05 17:00 |  |  | 2020-10-05 17:00 |  | 0 | 0 | 0 | 0 | 37 | 37 |  |  |  |  | MDC1.C1.C3050: FS 5 | MDC1.C1.C3210: FS |  | 0 | 0 |  | ['1220: FS 5'] | ['981: FS']
1205 | Not Started | MDC1-BL.4.10.2.1.1 | Finish Milestone | Pad Ready for MER COLO-1 Cell-4 |  | 2020-10-05 17:00 |  |  | 2020-10-05 17:00 |  | 0 | 0 | 0 | 0 | 46 | 46 |  |  |  |  | MDC1.C1.C4050: FS 5 | MDC1.C1.C4270: FS |  | 0 | 0 |  | ['1222: FS 5'] | ['903: FS']
1206 | Not Started | MDC1-BL.5.1.3.1.2.4 | Task Dependent | Duct Bank - South Cross over (URS to west Vault Run) | 2020-09-21 07:00 | 2020-10-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 36 | 36 |  |  |  |  | MDC1.S.1110: FF, MDC1.S.1110: FS | MDC1.S.1770: FS, MDC1.S.1640: FS, MDC1.S.1220: FS |  | 0 | 0 |  | ['1251: FF', '1251: FS'] | ['763: FS', '884: FS', '1177: FS']
1207 | Not Started | MDC1-BL.5.3.1.4.1.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-09-19 07:00 | 2020-10-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C1.C1070: FS, MDC1-C1.P1700: FS, MDC1.C1.E1120: FS, MDC1.C1.E1130: FS | MDC1.C1.C1130: SS 5, MDC1.C1.C1160: FS, MDC1.C1.C1440: FS, MDC1.C1.C1410: FS | TCM | 720 | 0 |  | ['1252: FS', '35: FS', '125: FS', '126: FS'] | ['1188: SS 5', '1159: FS', '716: FS', '831: FS']
1208 | Not Started | MDC1-BL.5.7.4.7.1.2 | Task Dependent | Slab on Grade | 2020-09-22 07:00 | 2020-10-02 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C2.CS1080: FF, MDC1.C1.CS1110: FS, A1170: FS, MDC1-C2.P1400: FS | MDC1.C2.C4080: FS, MDC1.C2.C2080: FS, MDC1.C2.C3100: FS, MDC1.C2.C1100: FS, MDC1.C2.C4090: FS, MDC1.C2.C2100: FS, MDC1.C2.C3110: FS, MDC1.C2.C1110: FS, MDC1.C3.CS1090: FS, MDC1.C2.C1050: FS, MDC1-C2.P1500: FS | CSI | 800 | 0 |  | ['1219: FF', '1241: FS', '2: FS', '13: FS'] | ['1019: FS', '1094: FS', '1016: FS', '1092: FS', '1002: FS', '1070: FS', '1001: FS', '1069: FS', '1140: FS', '1170: FS', '12: FS']
1209 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-09-29 07:00 | 2020-10-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 33 | 33 |  |  |  |  | MDC1.C2.C1010: FS | MDC1.C2.C1030: FS, MDC1.C2.E1000: FS | CSI, VECA Electricians | 480 | 0 |  | ['1223: FS'] | ['1194: FS', '101: FS']
1210 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-09-29 07:00 | 2020-10-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 37 | 37 |  |  |  |  | MDC1.C2.C2000: FS | MDC1.C2.C2020: FS, MDC1.C2.E1030: FS | CSI, VECA Electricians | 480 | 0 |  | ['1224: FS'] | ['1195: FS', '106: FS']
1211 | Not Started | MDC1-BL.5.3.1.3.1.1 | Task Dependent | Hang Wall Partitions | 2020-09-23 07:00 | 2020-10-01 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 24 | 24 |  |  |  |  | MDC1.C1.CS1110: FS, MDC1.C1.C1080: SS 6 | MDC1.C1.C1140: FS, MDC1.C1.C1150: FS | PCI | 600 | 0 |  | ['1241: FS', '1228: SS 6'] | ['1172: FS', '1165: FS']
1212 | Not Started | MDC1-BL.5.3.1.3.3.1 | Task Dependent | Hang Wall Partitions | 2020-09-23 07:00 | 2020-10-01 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 17 | 17 |  |  |  |  | MDC1.C1.CS1110: FS, MDC1.C1.C2080: SS 6 | MDC1.C1.C2130: FS, MDC1.C1.C2150: FS | PCI | 600 | 0 |  | ['1241: FS', '1229: SS 6'] | ['1175: FS', '1166: FS']
1213 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank- Building to URS - 2nd Half | 2020-09-24 07:00 | 2020-10-01 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1.S.1140: FS, MDC1.S.1140: FF, MDC1.C1.C3040: FS | MDC1.S.1770: FS, MDC1.S.1230: FS, MDC1.S.1210: FS | VECA Electricians | 420 | 0 |  | ['1237: FS', '1237: FF', '1235: FS'] | ['763: FS', '1167: FS', '1187: FS']
1214 | Not Started | MDC1-BL.5.1.3.1.1.2 | Task Dependent | Vault- Set North vault- Along UPM to Vault | 2020-09-29 07:00 | 2020-10-01 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 26 | 26 |  |  |  |  | MDC1.C2.C2000: FS, MDC1-2190: FS | MDC1.S.1240: FS, MDC1.S.1260: FS | VECA Electricians | 180 | 0 |  | ['1224: FS', '1248: FS'] | ['1168: FS', '1155: FS']
1215 | In Progress | MDC1-BL.5.1.9 | Task Dependent | Telecom-Communications Site Loop/Ductbank | 2020-06-29 08:00 | 2020-10-01 08:00 | 2020-06-25 |  |  |  | 4 | 3 | 72 | 75 | 79 | 79 |  |  |  |  | MDC1-1994: FS | MDC1.S.1540: FS, MDC1.S.1910: FS | VECA Electricians | 2500 | 0 |  | ['1348: FS'] | ['961: FS', '260: FS']
1216 | In Progress | MDC1-BL.4.11.1 | Task Dependent | BIM Modeling (Above ground) | 2020-08-02 08:00 | 2020-09-30 17:00 | 2020-06-15 |  |  |  | 0 | 14 | 60 | 60 | 10 | 10 |  |  |  |  | MDC1-2003: FS, MDC1-1999: FS | MDC1AD-1024: FS, MDC1-2106: FS, MDC1-2109: FF |  | 0 | 0 |  | ['59: FS', '1340: FS'] | ['1156: FS', '1169: FS', '1285: FF']
1217 | Not Started | MDC1-BL.5.3.2.4.5.1 | Task Dependent | Set Exterior Electrical OFCI Equipment | 2020-09-16 07:00 | 2020-09-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 36 | 36 |  |  |  |  | MDC1-1961: FS, MDC1-2000: FS | MDC1.S.1480: FS, MDC1.S.1330: FS, MDC1-1967: FS, MDC1-1968: FS, MDC1-1969: FS, MDC1-1975: FS, MDC1-1976: FS | VECA Electricians | 720 | 0 |  | ['1259: FS', '1334: FS'] | ['1039: FS', '1116: FS', '795: FS', '745: FS', '746: FS', '993: FS', '684: FS']
1218 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-09-15 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C1.C1050: FS, MDC1.C1.E1040: FS, MDC1.C1.E1050: FS | MDC1.C1.C1420: FS, MDC1.C1.C1410: FS, MDC1.C1.C1460: FS, MDC1.C1.C1160: FS, MDC1.C1.C1440: FS | VECA Electricians | 480 | 0 |  | ['1261: FS', '153: FS', '154: FS'] | ['818: FS', '831: FS', '689: FS', '1159: FS', '716: FS']
1219 | Not Started | MDC1-BL.5.7.4.7.1.2 | Task Dependent | Aggregate Base Course | 2020-09-22 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 18 | 18 |  |  |  |  | MDC1.C2.CS1070: FF, MDC1.C2.CS1050: FS, MDC1-C2.P1400: FS, MDC1.C2.CS1020: FS | MDC1.C2.CS1090: FF | CSI | 600 | 0 |  | ['1242: FF', '1296: FS', '13: FS', '1319: FS'] | ['1208: FF']
1220 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-09-15 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 37 | 37 |  |  |  |  | MDC1.C1.C3000: FS | MDC1.C1.C3060: SS 6, MDC1.C1.C3250: FS, MDC1.C1.C3080: FS, MDC1.C1.E1220: FS 5, MDC1.C1.C3210: FS, MDC1.C1.E1180: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1263: FS'] | ['1190: SS 6', '945: FS', '1179: FS', '1204: FS 5', '981: FS', '155: FS']
1221 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-09-15 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 59 | 59 |  |  |  |  | MDC1.C1.C2050: FS, MDC1.C1.E1060: FS, MDC1.C1.E1070: FS | MDC1.C1.C2430: FS, MDC1.C1.C2420: FS, MDC1.C1.C2460: FS, MDC1.C1.C2410: FS, MDC1.C1.C2450: FS | VECA Electricians | 480 | 0 |  | ['1264: FS', '157: FS', '158: FS'] | ['773: FS', '796: FS', '670: FS', '813: FS', '694: FS']
1222 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-09-15 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 46 | 46 |  |  |  |  | MDC1.C1.C4000: FS | MDC1.C1.C4060: SS 6, MDC1.C1.C4280: FS, MDC1.C1.C4090: FS, MDC1.C1.E1230: FS 5, MDC1.C1.C4270: FS, MDC1.C1.E1200: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1265: FS'] | ['1200: SS 6', '871: FS', '1180: FS', '1205: FS 5', '903: FS', '159: FS']
1223 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Electrical Underground Rough-In | 2020-09-15 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.C1000: FS, MDC1.C1.C3000: FS, MDC1.C2.CS1060: FS | MDC1.C2.C1040: FS, MDC1.C2.C3010: FS, MDC1-1956: SS, MDC1.C2.C1020: FS | VECA Electricians | 960 | 0 |  | ['1288: FS', '1263: FS', '1273: FS'] | ['1181: FS', '1182: FS', '281: SS', '1209: FS']
1224 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Electrical Underground Rough-In | 2020-09-15 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 26 | 26 |  |  |  |  | MDC1.C1.C4000: FS | MDC1.C2.C2030: FS, MDC1.C2.C2010: FS, MDC1.S.1260: FS, MDC1.S.1190: FS | VECA Electricians | 960 | 0 |  | ['1265: FS'] | ['1183: FS', '1210: FS', '1155: FS', '1214: FS']
1225 | Not Started | MDC1-BL.5.1.3.1.1.1 | Task Dependent | Vault- Set vault along UMS to Jaz run | 2020-09-25 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 26 | 26 |  |  |  |  | MDC1.S.1150: FS, MDC1-2190: FS | MDC1.S.1210: FS, MDC1.S.1310: FS, MDC1.S.1370: FS, MDC1.S.1680: FS, MDC1.S.1470: FS | VECA Electricians | 180 | 0 |  | ['1234: FS', '1248: FS'] | ['1187: FS', '1114: FS', '1103: FS', '858: FS', '1038: FS']
1226 | Not Started | MDC1-BL.4.11.5.4 | Task Dependent | JAZ Riser Support DRB#1 Procurement | 2020-07-21 08:00 | 2020-09-28 16:00 |  |  |  |  | 0 | 0 | 70 | 70 | 70 | 70 |  |  |  |  | MDC1-2140.2: FS | MDC1.S.1600: FS, MDC1.S.1680: FS |  | 0 | 0 |  | ['1322: FS'] | ['934: FS', '858: FS']
1227 | Not Started | MDC1-BL.4.11.1.1 | Task Dependent | Design / Lead Time for Electrical/Telecom (OFCI Telecom BOM Materials) | 2020-06-30 08:00 | 2020-09-27 16:00 |  |  |  |  | 0 | 0 | 90 | 90 | 50 | 50 |  |  |  |  | MDC1-2003: FS | MDC1.C1.C3200: FS, MDC1.C1.C4190: FS, MDC1.C1.C1200: FS |  | 0 | 0 |  | ['59: FS'] | ['1010: FS', '1012: FS', '1109: FS']
1228 | Not Started | MDC1-BL.5.3.1.3.1.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-09-16 07:00 | 2020-09-26 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 11 | 11 |  |  |  |  | MDC1.C1.C3010: FS, MDC1.C1.C1030: FS | MDC1.C1.C3070: FS, MDC1.C1.C1100: SS 6 | VECA Electricians | 1200 | 0 |  | ['1257: FS', '1268: FS'] | ['1191: FS', '1211: SS 6']
1229 | Not Started | MDC1-BL.5.3.1.3.3.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-09-16 07:00 | 2020-09-26 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 11 | 11 |  |  |  |  | MDC1.C1.C4010: FS, MDC1.C1.C2030: FS | MDC1.C1.C4070: FS, MDC1.C1.C2100: SS 6 | VECA Electricians | 1200 | 0 |  | ['1258: FS', '1269: FS'] | ['1192: FS', '1212: SS 6']
1230 | Not Started | MDC1-BL.5.3.2.4.5.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-09-23 07:00 | 2020-09-26 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 64 | 64 |  |  |  |  | MDC1-1962: FS, MDC1-2012: FS | MDC1-1964: FS | SURE STEEL | 160 | 0 |  | ['1239: FS', '1295: FS'] | ['1071: FS']
1231 | Not Started | MDC1-BL.5.7.1.1.3 | Task Dependent | Erect Interior Structural Steel | 2020-09-22 07:00 | 2020-09-26 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 23 | 23 |  |  |  |  | MDC1.C1.CS1110: FS, MDC1-2010: FS | MDC1.C1.C1140: FS, MDC1.C1.C3120: FS, MDC1.C1.C4130: FS, MDC1.C1.C2130: FS | SURE STEEL | 500 | 0 |  | ['1241: FS', '1247: FS'] | ['1172: FS', '1130: FS', '1131: FS', '1175: FS']
1232 | Not Started | MDC1-BL.5.3.1.4.3.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-09-22 07:00 | 2020-09-25 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 49 | 49 |  |  |  |  | MDC1.C1.C2060: FS | MDC1.C1.C2120: FS, MDC1.C1.E1160: FS | SURE STEEL | 160 | 0 |  | ['1244: FS'] | ['1185: FS', '129: FS']
1233 | Not Started | MDC1-BL.5.7.5.7.2 | Task Dependent | Downspouts & Gutters | 2020-09-05 07:00 | 2020-09-24 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 15 | 15 |  |  |  |  | MDC1.C3.CS1050: FS, MDC1.C2.CS1060: FS, MDC1.C3.CS1040: SS, MDC1-C3.P1200: FS, MDC1.C2.CS1040: SS, MDC1.C1.CS1060: FS, MDC1.C2.CS1030: FS, MDC1.C2.CS1040: FS, MDC1.C3.CS1030: FS, MDC1.C3.CS1040: FS | MDC1.C4.CS1060: FS, MDC1.C3.C1010: FS, MDC1.C3.C2000: FS | SURE STEEL | 900 | 0 |  | ['1276: FS', '1273: FS', '1283: SS', '26: FS', '1299: SS', '1324: FS', '1311: FS', '1299: FS', '1298: FS', '1283: FS'] | ['1178: FS', '1126: FS', '1127: FS']
1234 | Not Started | MDC1-BL.5.1.3.1.1.1 | Task Dependent | Vault- Set vault along URS to JAX run | 2020-09-22 07:00 | 2020-09-24 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 26 | 26 |  |  |  |  | MDC1.S.1070: FS, MDC1-2190: FS | MDC1.S.1170: FS, MDC1.S.1210: FS | VECA Electricians | 180 | 0 |  | ['1275: FS', '1248: FS'] | ['1225: FS', '1187: FS']
1235 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Set Electrical Equipment-UPM Cell -3 | 2020-09-19 07:00 | 2020-09-23 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.C1.C1040: FS, MDC1.C1.C3020: FS, MDC1.C1.E1080: FS, MDC1.C1.E1090: FS | MDC1.S.1480: FS, MDC1.S.1290: FS, MDC1.S.1330: FS, MDC1.S.1380: FS, MDC1.C1.Cx2030: FS, MDC1.S.1380: FF, MDC1.S.1730: FS, MDC1.S.1180: FS | VECA Electricians | 80 | 0 |  | ['1270: FS', '1253: FS', '95: FS', '96: FS'] | ['1039: FS', '1128: FS', '1116: FS', '1099: FS', '596: FS', '1099: FF', '810: FS', '1213: FS']
1236 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-09-19 07:00 | 2020-09-23 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 39 | 39 |  |  |  |  | MDC1.C1.C4020: FS, MDC1.C1.E1110: FS, MDC1.C1.E1100: FS | MDC1.S.1480: FS, MDC1.S.1360: FS, MDC1.S.1290: FS, MDC1.C1.Cx2050: FS, MDC1.S.1730: FS | VECA Electricians | 80 | 0 |  | ['1254: FS', '100: FS', '99: FS'] | ['1039: FS', '1108: FS', '1128: FS', '587: FS', '810: FS']
1237 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank- Building to URS - 1st Half | 2020-09-16 07:00 | 2020-09-23 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1.S.1090: FS | MDC1.S.1770: FS, MDC1.S.1180: FS, MDC1.S.1230: FS, MDC1.S.1180: FF | VECA Electricians | 420 | 0 |  | ['1260: FS'] | ['763: FS', '1213: FS', '1167: FS', '1213: FF']
1238 | Not Started | MDC1-BL.5.7.6.7.2 | Task Dependent | Roof Panels Installation | 2020-09-04 07:00 | 2020-09-22 17:00 |  |  |  |  | 0 | 0 | 14 | 14 | 6 | 6 |  |  |  |  | MDC1.C3.CS1050: FS, MDC1-C4.P1300: FS, MDC1.C4.CS1040: SF, MDC1.C3.CS1040: SF, MDC1-C3.P1200: FF, MDC1.C2.CS1040: SF, MDC1.C1.CS1060: FF, MDC1.C2.CS1030: FF, MDC1.C2.CS1040: FF, MDC1.C3.CS1030: FF, MDC1.C3.CS1040: FF, MDC1.C4.CS1030: FF, MDC1.C4.CS1040: FF | MDC1.C4.CS1060: FS, MDC1.C4.CS1080: FS, MDC1.C4.CS1070: FS, MDC1.S.1350: FS, MDC1.S.1300: FS, MDC1.S.1900: FS, MDC1.S.1870: FS, MDC1-2529: FS | SURE STEEL | 1680 | 0 |  | ['1276: FS', '29: FS', '1256: SF', '1283: SF', '26: FF', '1299: SF', '1324: FF', '1311: FF', '1299: FF', '1298: FF', '1283: FF', '1281: FF', '1256: FF'] | ['1178: FS', '1121: FS', '1120: FS', '1107: FS', '1113: FS', '257: FS', '348: FS', '1240: FS']
1239 | Not Started | MDC1-BL.5.3.2.4.5.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-09-08 07:00 | 2020-09-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 64 | 64 |  |  |  |  | MDC1-1961: SS 6, MDC1-1972: SS 15 | MDC1-1970: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1259: SS 6', '1287: SS 15'] | ['1230: FS']
1240 | Not Started | MDC1-BL.3.1 | Finish Milestone | Weather Tight |  | 2020-09-22 17:00 |  |  | 2020-09-22 17:00 |  | 0 | 0 | 0 | 0 | 59 | 59 |  |  |  |  | MDC1.C4.CS1050: FS, MDC1.C4.CS1040: FS | MDC1-C1.P1800: FS, MDC1.C1.C1140: FS |  | 0 | 0 |  | ['1238: FS', '1256: FS'] | ['30: FS', '1172: FS']
1241 | Not Started | MDC1-BL.5.7.1.1.2 | Task Dependent | Slab on Grade | 2020-09-09 07:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.CS1100: FS, MDC1.AD.CS1100: FS 4, A1170: FS, MDC1-1995: FS | MDC1.C1.C4110: FS, MDC1.C1.C3110: FS, MDC1.C1.C4100: FS, MDC1.C1.C2100: FS, MDC1.C1.C1100: FS, MDC1.C1.C2110: FS, MDC1.C1.C1120: FS, MDC1.C2.CS1090: FS, MDC1.C1.CS1120: FS, MDC1.C1.C1170: FS, MDC1.C1.C3200: FS, MDC1.C1.C2160: FS, MDC1.C1.C4190: FS, MDC1AD-1010: FS | CSI | 800 | 0 |  | ['1267: FS', '1279: FS 4', '2: FS', '1284: FS'] | ['1150: FS', '1147: FS', '1176: FS', '1212: FS', '1211: FS', '1199: FS', '1198: FS', '1208: FS', '1231: FS', '1144: FS', '1010: FS', '1148: FS', '1012: FS', '589: FS']
1242 | Not Started | MDC1-BL.5.7.4.7.1.2 | Task Dependent | MEP Undeground Rough-In (Interior) | 2020-09-02 07:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 14 | 14 |  |  |  |  | MDC1.C1.CS1090: FF, MDC1.C1.CS1090: FS, MDC1.C2.CS1020: FF, MDC1.C2.CS1050: FF | MDC1.C3.CS1070: FS, MDC1.C2.CS1080: FF, MDC1-C2.P1400: FS | TCM, VECA Electricians | 2100 | 0 |  | ['1280: FF', '1280: FS', '1319: FF', '1296: FF'] | ['1189: FS', '1219: FF', '13: FS']
1243 | Not Started | MDC1-BL.5.3.1.4.2.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-09-05 07:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1.C1.C3000: SS 6 | MDC1.C1.C3060: SS 15 | TCM | 720 | 0 |  | ['1263: SS 6'] | ['1190: SS 15']
1244 | Not Started | MDC1-BL.5.3.1.4.3.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-09-05 07:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 49 | 49 |  |  |  |  | MDC1.C1.C2050: SS 6, MDC1.C1.C2020: FS | MDC1.C1.C2070: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1264: SS 6', '1274: FS'] | ['1232: FS']
1245 | Not Started | MDC1-BL.5.3.1.4.4.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-09-05 07:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C1.C4000: SS 6, MDC1-2527: FS 10 | MDC1.C1.C4060: FS | TCM | 720 | 0 |  | ['1265: SS 6', '1325: FS 10'] | ['1200: FS']
1246 | Not Started | MDC1-BL.5.3.9.4.1.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-09-05 07:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 34 | 34 |  |  |  |  | MDC1.C1.C1020: FS | MDC1.C2.C1060: FS, MDC1.C2.C3000: FS, MDC1.C3.C1000: FS | TCM | 720 | 0 |  | ['1272: FS'] | ['1151: FS', '1201: FS', '1202: FS']
1247 | Not Started | MDC1-BL.4.13 | Task Dependent | Lead Time for COLO 1 Structural Interior Steel | 2020-06-30 08:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 83 | 83 | 28 | 28 |  |  |  |  | MDC1-2003: FS | MDC1.C1.CS1120: FS |  | 0 | 0 |  | ['59: FS'] | ['1231: FS']
1248 | Not Started | MDC1-BL.4.11.5.4 | Task Dependent | UPM to UMS Vaults Procurement DRB#1 | 2020-08-18 08:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 35 | 35 | 31 | 31 |  |  |  |  | MDC1-2140.2: FS, MDC1-2135: FS, MDC1-2134: FS | MDC1.S.1190: FS, MDC1.S.1150: FS, MDC1.S.1170: FS, MDC1.S.1370: FS |  | 0 | 0 |  | ['1322: FS', '1297: FS', '1309: FS'] | ['1214: FS', '1234: FS', '1225: FS', '1103: FS']
1249 | Not Started | MDC1-BL.4.10.2.1.1 | Finish Milestone | Pad Ready for MER COLO-1 Cell-1 |  | 2020-09-19 17:00 |  |  | 2020-09-19 17:00 |  | 0 | 0 | 0 | 0 | 38 | 38 |  |  |  |  | MDC1.C1.C1050: FS 5 | MDC1.C1.C1250: FS |  | 0 | 0 |  | ['1261: FS 5'] | ['1051: FS']
1250 | Not Started | MDC1-BL.4.10.2.1.1 | Finish Milestone | Pad Ready for MER COLO-1 Cell-2 |  | 2020-09-19 17:00 |  |  | 2020-09-19 17:00 |  | 0 | 0 | 0 | 0 | 44 | 44 |  |  |  |  | MDC1.C1.C2050: FS 5 | MDC1.C1.C2270: FS |  | 0 | 0 |  | ['1264: FS 5'] | ['1024: FS']
1251 | Not Started | MDC1-BL.5.1.3.1.2.4 | Task Dependent | Duct Bank - North Crossover (URS to west Vault Run) | 2020-09-04 07:00 | 2020-09-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 36 | 36 |  |  |  |  | MDC1.S.1050: FS, MDC1.C3.CS1050: FS | MDC1.S.1500: FS, MDC1.S.1480: FS, MDC1.S.1200: FF, MDC1.S.1200: FS |  | 0 | 0 |  | ['1293: FS', '1276: FS'] | ['1000: FS', '1039: FS', '1206: FF', '1206: FS']
1252 | Not Started | MDC1-BL.5.3.1.4.1.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-09-15 07:00 | 2020-09-18 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 48 | 48 |  |  |  |  | MDC1.C1.C1060: FS | MDC1.C1.C1110: FS, MDC1.C1.E1120: FS | SURE STEEL | 160 | 0 |  | ['1262: FS'] | ['1207: FS', '125: FS']
1253 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-09-15 07:00 | 2020-09-18 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.C1.C3000: FS | MDC1.C1.C3040: FS, MDC1.C1.E1080: FS | CSI, VECA Electricians | 480 | 0 |  | ['1263: FS'] | ['1235: FS', '95: FS']
1254 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-09-15 07:00 | 2020-09-18 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 39 | 39 |  |  |  |  | MDC1.C1.C4000: FS | MDC1.C1.C4040: FS, MDC1.C1.E1100: FS | CSI, VECA Electricians | 480 | 0 |  | ['1265: FS'] | ['1236: FS', '99: FS']
1255 | Not Started | MDC1-BL.5.1.3.1.2.5 | Task Dependent | Duct Bank Admin UPM to COLO-1 UPM | 2020-09-15 07:00 | 2020-09-18 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 37 | 37 |  |  |  |  | MDC1.AD.CS1080: FS, MDC1.C1.C4000: FS | MDC1.S.1330: FS, MDC1.S.1480: FS, MDC1.S.1260: FS, MDC1.S.1260: FF |  | 0 | 0 |  | ['1300: FS', '1265: FS'] | ['1116: FS', '1039: FS', '1155: FS', '1155: FF']
1256 | Not Started | MDC1-BL.5.7.6.7.2 | Task Dependent | Exterior Insulated Metal Panels Installation | 2020-09-02 07:00 | 2020-09-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 10 | 10 |  |  |  |  | MDC1.C4.CS1020: FS, MDC1.C3.CS1040: FS, MDC1.C3.CS1040: FF, MDC1-C4.P1200: FS, MDC1.C4.CS1030: FS | MDC1.C4.CS1060: SS, MDC1.C4.CS1050: SF, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF, MDC1-2529: FS | SURE STEEL | 840 | 0 |  | ['1291: FS', '1283: FS', '1283: FF', '28: FS', '1281: FS'] | ['1178: SS', '1238: SF', '1178: FS', '1238: FF', '1240: FS']
1257 | Not Started | MDC1-BL.5.3.1.3.2.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-09-09 07:00 | 2020-09-15 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1.C1.C1030: FS, MDC1-C1.P1500: FS | MDC1.C1.C1080: FS, MDC1.C2.C1050: FS, MDC1.C1.C3070: FS | TCM, VECA Electricians | 800 | 0 |  | ['1268: FS', '8: FS'] | ['1228: FS', '1170: FS', '1191: FS']
1258 | Not Started | MDC1-BL.5.3.1.3.4.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-09-09 07:00 | 2020-09-15 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1.C1.C2030: FS, MDC1-C1.P1500: FS | MDC1.C1.C2080: FS, MDC1.C2.C2040: FS, MDC1.C1.C4070: FS | TCM, VECA Electricians | 800 | 0 |  | ['1269: FS', '8: FS'] | ['1229: FS', '1171: FS', '1192: FS']
1259 | Not Started | MDC1-BL.5.3.2.4.5.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-08-31 07:00 | 2020-09-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 36 | 36 |  |  |  |  | MDC1-1965: FS | MDC1-1967: FS, MDC1-1962: SS 6, MDC1-1963: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1286: FS'] | ['795: FS', '1239: SS 6', '1217: FS']
1260 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct bank- COLO-2 UPM to north Valut | 2020-09-10 07:00 | 2020-09-15 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.S.1080: FS, MDC1.C1.C1010: FS, MDC1.C1.C1040: FS | MDC1.S.1140: FS | VECA Electricians | 240 | 0 |  | ['1266: FS', '1277: FS', '1270: FS'] | ['1237: FS']
1261 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-08-29 07:00 | 2020-09-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1.C1.CS1070: SS 7, MDC1.C1.C1000: FS | MDC1.C1.C1060: SS, MDC1.C1.C1090: FS, MDC1-C1.P1600: FS, MDC1.C1.E1140: FS 5, MDC1.C1.C1250: FS, MDC1.C1.E1040: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1315: SS 7', '1288: FS'] | ['1262: SS', '1218: FS', '34: FS', '1249: FS 5', '1051: FS', '153: FS']
1262 | Not Started | MDC1-BL.5.3.1.4.1.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-08-29 07:00 | 2020-09-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C1.C1050: SS | MDC1.C1.C1070: FS, MDC1.C2.C1060: FS, MDC1-C1.P1700: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1261: SS'] | ['1252: FS', '1151: FS', '35: FS']
1263 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Electrical Underground Rough-In | 2020-08-29 07:00 | 2020-09-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.C1000: FS, MDC1-2527: FS 10 | MDC1.C1.C3030: SS 6, MDC1.C1.C3050: FS, MDC1.C1.C3020: FS, MDC1.C2.C1010: FS | VECA Electricians | 960 | 0 |  | ['1288: FS', '1325: FS 10'] | ['1243: SS 6', '1220: FS', '1253: FS', '1223: FS']
1264 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-08-29 07:00 | 2020-09-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 44 | 44 |  |  |  |  | MDC1.C1.C2000: FS | MDC1.C1.C2060: SS 6, MDC1.C1.C2280: FS, MDC1.C1.C2090: FS, MDC1.C1.E1150: FS 5, MDC1.C1.C2270: FS, MDC1.C1.E1060: FS | CSI, VECA Electricians | 1440 | 0 |  | ['1289: FS'] | ['1244: SS 6', '984: FS', '1221: FS', '1250: FS 5', '1024: FS', '157: FS']
1265 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Electrical Underground Rough-In | 2020-08-29 07:00 | 2020-09-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 26 | 26 |  |  |  |  | MDC1.C1.C2000: FS, MDC1-2527: FS 10 | MDC1.C1.C4030: SS 6, MDC1.C1.C4050: FS, MDC1.C1.C4020: FS, MDC1.C2.C2000: FS, MDC1.S.1100: FS | VECA Electricians | 960 | 0 |  | ['1289: FS', '1325: FS 10'] | ['1245: SS 6', '1222: FS', '1254: FS', '1224: FS', '1255: FS']
1266 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct bank- COLO-1 UPM to north vault | 2020-09-02 07:00 | 2020-09-09 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 0 | 0 |  |  |  |  | MDC1.C1.C1000: FS, MDC1.S.1060: FS | MDC1.S.1090: FS | VECA Electricians | 360 | 0 |  | ['1288: FS', '1282: FS'] | ['1260: FS']
1267 | Not Started | MDC1-BL.5.7.1.1.2 | Task Dependent | Aggregate Base Course | 2020-09-02 07:00 | 2020-09-08 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C1.CS1090: FS, MDC1.C1.CS1070: FS | MDC1.C1.CS1110: FS | CSI | 500 | 0 |  | ['1280: FS', '1315: FS'] | ['1241: FS']
1268 | Not Started | MDC1-BL.5.3.1.3.1.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-09-02 07:00 | 2020-09-08 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1-C1.P1500: FS | MDC1.C1.C3010: FS, MDC1.C1.C1080: FS | TCM, VECA Electricians | 800 | 0 |  | ['8: FS'] | ['1257: FS', '1228: FS']
1269 | Not Started | MDC1-BL.5.3.1.3.3.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-09-02 07:00 | 2020-09-08 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1-C1.P1500: FS | MDC1.C1.C2080: FS, MDC1.C1.C4010: FS | TCM, VECA Electricians | 800 | 0 |  | ['8: FS'] | ['1229: FS', '1258: FS']
1270 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-09-03 07:00 | 2020-09-08 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 1 | 1 |  |  |  |  | MDC1.C1.C1010: FS, MDC1.C1.E1010: FS, MDC1.C1.E1000: FS | MDC1.C1.C3040: FS, MDC1.S.1380: FS, MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS, MDC1.S.1730: FS, MDC1.S.1090: FS | VECA Electricians | 80 | 0 |  | ['1277: FS', '94: FS', '93: FS'] | ['1235: FS', '1099: FS', '645: FS', '30: FS', '810: FS', '1260: FS']
1271 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-09-03 07:00 | 2020-09-08 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 55 | 55 |  |  |  |  | MDC1.C1.C2010: FS, MDC1.C1.E1020: FS, MDC1.C1.E1030: FS | MDC1.S.1480: FS, MDC1.S.1360: FS, MDC1.C1.Cx2010: FS, MDC1.S.1730: FS | VECA Electricians | 80 | 0 |  | ['1278: FS', '97: FS', '98: FS'] | ['1039: FS', '1108: FS', '623: FS', '810: FS']
1272 | Not Started | MDC1-BL.5.3.1.4.1.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-08-21 07:00 | 2020-09-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 34 | 34 |  |  |  |  | MDC1.C1.C1000: SS 6 | MDC1.C2.C1000: FS | TCM | 720 | 0 |  | ['1288: SS 6'] | ['1246: FS']
1273 | Not Started | MDC1-BL.5.7.4.7.2 | Task Dependent | Downspouts & Gutters | 2020-08-18 07:00 | 2020-09-04 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 6 | 6 |  |  |  |  | MDC1.C2.CS1050: FS, MDC1.C1.CS1080: FS, MDC1.C2.CS1040: SS, MDC1.C1.CS1060: FS, MDC1.C2.CS1030: FS, MDC1.C2.CS1040: FS | MDC1.C3.CS1060: FS, MDC1.C2.C1010: FS | SURE STEEL | 900 | 0 |  | ['1296: FS', '1301: FS', '1299: SS', '1324: FS', '1311: FS', '1299: FS'] | ['1233: FS', '1223: FS']
1274 | Not Started | MDC1-BL.5.3.1.4.3.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-08-21 07:00 | 2020-09-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 49 | 49 |  |  |  |  | MDC1.C1.C2000: SS 6 | MDC1.C1.C2060: FS | TCM | 720 | 0 |  | ['1289: SS 6'] | ['1244: FS']
1275 | Not Started | MDC1-BL.5.1.3.1.1.1 | Task Dependent | Vault- Set 2nd vault Along UMS Duct Run near COLO-2 | 2020-09-02 07:00 | 2020-09-04 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 21 | 21 |  |  |  |  | MDC1.S.1060: FS | MDC1.S.1230: FS, MDC1.S.1150: FS | VECA Electricians | 180 | 0 |  | ['1282: FS'] | ['1167: FS', '1234: FS']
1276 | Not Started | MDC1-BL.5.7.5.7.2 | Task Dependent | Roof Panels Installation | 2020-08-18 07:00 | 2020-09-03 17:00 |  |  |  |  | 0 | 0 | 14 | 14 | 6 | 6 |  |  |  |  | MDC1.C2.CS1050: FS, MDC1-C3.P1300: FS, MDC1-C3.P1200: FF, MDC1.C1.CS1060: FS, MDC1.C2.CS1030: FS, MDC1.C2.CS1040: FS, MDC1.C3.CS1030: FS | MDC1.C3.CS1060: FS, MDC1.C4.CS1050: FS, MDC1.C3.CS1080: FS, MDC1-C4.P1300: FS, MDC1.C3.CS1070: FS, MDC1.S.1110: FS, MDC1.S.1220: FS | SURE STEEL | 1680 | 0 |  | ['1296: FS', '27: FS', '26: FF', '1324: FS', '1311: FS', '1299: FS', '1298: FS'] | ['1233: FS', '1238: FS', '1163: FS', '29: FS', '1189: FS', '1251: FS', '1177: FS']
1277 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-08-29 07:00 | 2020-09-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 1 | 1 |  |  |  |  | MDC1.C1.C1000: FS | MDC1.C1.C1040: FS, MDC1.C1.E1000: FS, MDC1.S.1090: FS | CSI, VECA Electricians | 480 | 0 |  | ['1288: FS'] | ['1270: FS', '93: FS', '1260: FS']
1278 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-08-29 07:00 | 2020-09-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 55 | 55 |  |  |  |  | MDC1.C1.C2000: FS | MDC1.C1.C2040: FS, MDC1.C1.E1030: FS | CSI, VECA Electricians | 480 | 0 |  | ['1289: FS'] | ['1271: FS', '98: FS']
1279 | Not Started | MDC1-BL.5.7.3.1.2 | Task Dependent | Slab on Grade | 2020-08-20 07:00 | 2020-09-01 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 1 | 1 |  |  |  |  | MDC1.AD.CS1090: FS, MDC1-C1.P1400: FS | MDC1AD-1016: FS, MDC1AD-1017: FS, MDC1.C1.CS1110: FS 4, MDC1AD-1024: FS, MDC1-C1.P1500: FS | CSI | 800 | 0 |  | ['1294: FS', '9: FS'] | ['1129: FS', '1203: FS', '1241: FS 4', '1156: FS', '8: FS']
1280 | Not Started | MDC1-BL.5.7.1.1.2 | Task Dependent | MEP Undeground Rough-In (Interior) | 2020-08-14 07:00 | 2020-09-01 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 0 | 0 |  |  |  |  | MDC1.AD.CS1080: FS | MDC1.C2.CS1070: FF, MDC1.C1.CS1100: FS, MDC1.C2.CS1070: FS | TCM, VECA Electricians | 2100 | 0 |  | ['1300: FS'] | ['1242: FF', '1267: FS', '1242: FS']
1281 | Not Started | MDC1-BL.5.7.6.7.1.3 | Task Dependent | Secondary Steel | 2020-08-25 07:00 | 2020-09-01 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 10 | 10 |  |  |  |  | MDC1.C4.CS1020: FS | MDC1.C4.CS1040: FS, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF, MDC1.S.1220: FS, MDC1.S.1350: FS | SURE STEEL | 210 | 0 |  | ['1291: FS'] | ['1256: FS', '1178: FS', '1238: FF', '1177: FS', '1107: FS']
1282 | Not Started | MDC1-BL.5.1.3.1.1.1 | Task Dependent | Vault- set 1st Vault Along UMS Duct bank run | 2020-08-29 07:00 | 2020-09-01 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 0 | 0 |  |  |  |  | MDC1.C1.C1000: FS | MDC1.S.1070: FS, MDC1.S.1080: FS | VECA Electricians | 180 | 0 |  | ['1288: FS'] | ['1275: FS', '1266: FS']
1283 | Not Started | MDC1-BL.5.7.5.7.2 | Task Dependent | Exterior Insulated Metal Panels Installation | 2020-08-17 07:00 | 2020-08-31 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C3.CS1020: FS, MDC1.C2.CS1040: FS, MDC1-C3.P1200: FS, MDC1.C3.CS1030: FS | MDC1.C4.CS1040: FS, MDC1.C4.CS1040: FF, MDC1-C4.P1200: FS, MDC1.C3.CS1060: SS, MDC1-C4.P1200: SS, MDC1.C3.CS1060: FS, MDC1.C4.CS1060: SS, MDC1.C4.CS1050: SF, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF | SURE STEEL | 840 | 0 |  | ['1304: FS', '1299: FS', '26: FS', '1298: FS'] | ['1256: FS', '1256: FF', '28: FS', '1233: SS', '28: SS', '1233: FS', '1178: SS', '1238: SF', '1178: FS', '1238: FF']
1284 | In Progress | MDC1-BL.4.11.5.3 | Task Dependent | Site Temp Power Procurement & Infrastructure | 2020-06-29 08:00 | 2020-08-31 08:00 | 2020-06-15 |  |  |  | 44.2 | 11 | 28 | 50 | 9 | 9 |  |  |  |  | MDC1-2003: FS | MDC1.C1.CS1110: FS, MDC1.AD.CS1090: FS |  | 0 | 0 |  | ['59: FS'] | ['1241: FS', '1294: FS']
1285 | Not Started | MDC1-BL.4.11.1 | Finish Milestone | Admin/COLO-1 BIM Signoff |  | 2020-08-30 17:00 |  |  | 2020-08-30 17:00 |  | 0 | 0 | 0 | 0 | 9 | 9 | As Late As Possible |  |  |  | MDC1-2008: FF | MDC1AD-1017: FS 21, MDC1AD-1024: FS 21 |  | 0 | 0 |  | ['1216: FF'] | ['1203: FS 21', '1156: FS 21']
1286 | Not Started | MDC1-BL.5.3.2.4.5.1 | Task Dependent | Electrical Underground Rough-In | 2020-08-08 07:00 | 2020-08-29 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 36 | 36 |  |  |  |  | MDC1-1999: FS, MDC1.AD.CS1040: FS, MDC1.AD.CS1050: FS, MDC1-C1.P1200: FS, MDC1.AD.CS1070: FS, MDC1-2527: FS, MDC1-1993: FS | MDC1-1961: FS | VECA Electricians | 960 | 0 |  | ['1340: FS', '1326: FS', '1318: FS', '22: FS', '1303: FS', '1325: FS', '1310: FS'] | ['1259: FS']
1287 | Not Started | MDC1-BL.5.3.2.4.5.2 | Task Dependent | Mechanical Underground Rough-In | 2020-08-08 07:00 | 2020-08-29 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 73 | 73 |  |  |  |  | MDC1-1999: FS, MDC1.AD.CS1040: FS, MDC1.AD.CS1050: FS, MDC1-C1.P1200: FS, MDC1.AD.CS1070: FS, MDC1-2527: FS | MDC1-1962: SS 15 | TCM | 720 | 0 |  | ['1340: FS', '1326: FS', '1318: FS', '22: FS', '1303: FS', '1325: FS'] | ['1239: SS 15']
1288 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Electrical Underground Rough-In | 2020-08-14 07:00 | 2020-08-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.CS1080: FS, MDC1.C1.CS1060: FS 4, MDC1.C1.CS1070: FS 2, MDC1-2527: FS 20 | MDC1.C1.C1050: FS, MDC1.C2.C1010: FS, MDC1-1955: SS, MDC1.C1.C1020: SS 6, MDC1.C1.C3000: FS, MDC1.C1.C1010: FS, MDC1.S.1060: FS, MDC1.S.1080: FS | VECA Electricians | 960 | 0 |  | ['1301: FS', '1324: FS 4', '1315: FS 2', '1325: FS 20'] | ['1261: FS', '1223: FS', '345: SS', '1272: SS 6', '1263: FS', '1277: FS', '1282: FS', '1266: FS']
1289 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Electrical Underground Rough-In | 2020-08-14 07:00 | 2020-08-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 26 | 26 |  |  |  |  | MDC1.C1.CS1080: FS, MDC1.C1.CS1070: FS, MDC1-2527: FS 10 | MDC1.C1.C2020: SS 6, MDC1.C1.C2050: FS, MDC1.C1.C4000: FS, MDC1.C1.C2010: FS | VECA Electricians | 960 | 0 |  | ['1301: FS', '1315: FS', '1325: FS 10'] | ['1274: SS 6', '1264: FS', '1265: FS', '1278: FS']
1290 | In Progress | MDC1-BL.4.14.2 | Task Dependent | Design / Lead Time for Fire Alarm | 2020-06-29 08:00 | 2020-08-27 16:00 | 2020-06-22 |  |  |  | 0 | 7 | 60 | 60 | 32 | 32 |  |  |  |  | MDC1-2003: FS | MDC1AD-1017: FS, MDC1AD-1024: FS |  | 0 | 0 |  | ['59: FS'] | ['1203: FS', '1156: FS']
1291 | Not Started | MDC1-BL.5.7.6.7.1.3 | Task Dependent | Erect PEMB Steel | 2020-08-08 07:00 | 2020-08-24 17:00 |  |  |  |  | 0 | 0 | 13 | 13 | 10 | 10 |  |  |  |  | MDC1.C4.CS1010: FS, MDC1.C3.CS1020: FS, MDC1-C4.P1100: FS | MDC1.C4.CS1040: FS, MDC1.C4.CS1030: FS | SURE STEEL | 910 | 0 |  | ['1305: FS', '1304: FS', '19: FS'] | ['1256: FS', '1281: FS']
1292 | Not Started | MDC1-BL.4.11.5.4 | Task Dependent | MV Ductbanks Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | 2020-08-18 08:00 | 2020-08-24 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 67 | 67 |  |  |  |  | MDC1-2134: FS, MDC1-2135: FS | MDC1.S.1210: FS |  | 0 | 0 |  | ['1309: FS', '1297: FS'] | ['1187: FS']
1293 | Not Started | MDC1-BL.5.1.3.1.2.4 | Task Dependent | Duct Bank - COLO2- UPM to UPM | 2020-08-18 07:00 | 2020-08-21 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 46 | 46 |  |  |  |  | MDC1.S.1020: FS, MDC1.C3.CS1030: FS, MDC1.C2.CS1050: FS | MDC1.S.1440: FS, MDC1.S.1420: FS, MDC1.S.1110: FS |  | 0 | 0 |  | ['1307: FS', '1298: FS', '1296: FS'] | ['1058: FS', '1067: FS', '1251: FS']
1294 | Not Started | MDC1-BL.5.7.3.1.2 | Task Dependent | Aggregate Base Course | 2020-08-14 07:00 | 2020-08-19 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 1 | 1 |  |  |  |  | MDC1.AD.CS1080: FS, MDC1.AD.CS1060: FS, MDC1-2003: FS, MDC1-C1.P1400: FS, MDC1-1995: FS, MDC1.AD.CS1080: FF | MDC1.AD.CS1100: FS | CSI | 500 | 0 |  | ['1300: FS', '1314: FS', '59: FS', '9: FS', '1284: FS', '1300: FF'] | ['1279: FS']
1295 | Not Started | MDC1-BL.4.13 | Task Dependent | Lead Time for Admin/COLO 1 Yard Steel | 2020-06-30 08:00 | 2020-08-18 17:00 |  |  |  |  | 0 | 0 | 49 | 49 | 118 | 118 |  |  |  |  | MDC1-2003: FS | MDC1-1967: FS, MDC1-1970: FS |  | 0 | 0 |  | ['59: FS'] | ['795: FS', '1230: FS']
1296 | Not Started | MDC1-BL.5.7.4.7.2 | Task Dependent | Roof Panels Installation | 2020-07-31 07:00 | 2020-08-17 17:00 |  |  |  |  | 0 | 0 | 14 | 14 | 6 | 6 |  |  |  |  | MDC1.C1.CS1070: FS, MDC1-C2.P1300: FS, MDC1.C2.CS1030: FS | MDC1.C2.CS1060: FS, MDC1.C2.CS1080: FS, MDC1.C3.CS1050: FS, MDC1-C2.P1400: FS, MDC1-C3.P1300: FS, MDC1.C2.CS1070: FF, MDC1.S.1050: FS | SURE STEEL | 1680 | 0 |  | ['1315: FS', '25: FS', '1311: FS'] | ['1273: FS', '1219: FS', '1276: FS', '13: FS', '27: FS', '1242: FF', '1293: FS']
1297 | Not Started | MDC1-BL.4.11.5.4 | Task Dependent | Site- Neher Mcgrath Study DRB#1 JAZ to UMS/URS & UPM to UMS | 2020-08-04 08:00 | 2020-08-17 17:00 |  |  |  |  | 0 | 0 | 14 | 14 | 31 | 31 |  |  |  |  | MDC1-2134: FS | MDC1-2131: FS, MDC1-2190: FS |  | 0 | 0 |  | ['1309: FS'] | ['1292: FS', '1248: FS']
1298 | Not Started | MDC1-BL.5.7.5.7.1.3 | Task Dependent | Secondary Steel | 2020-08-08 07:00 | 2020-08-15 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 7 | 7 |  |  |  |  | MDC1.C3.CS1020: FS | MDC1.C3.CS1040: FS, MDC1.C3.CS1060: FS, MDC1.C3.CS1050: FS, MDC1-C4.P1200: FS, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF, MDC1.S.1050: FS | SURE STEEL | 210 | 0 |  | ['1304: FS'] | ['1283: FS', '1233: FS', '1276: FS', '28: FS', '1178: FS', '1238: FF', '1293: FS']
1299 | Not Started | MDC1-BL.5.7.4.7.2 | Task Dependent | Exterior Insulated Metal Panels Installation | 2020-07-31 07:00 | 2020-08-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 8 | 8 |  |  |  |  | MDC1.C2.CS1020: FS, MDC1.C1.CS1050: FS, MDC1-C2.P1200: FS, MDC1.C2.CS1030: FS | MDC1.C3.CS1040: FS, MDC1-C3.P1200: FS, MDC1.C2.CS1060: SS, MDC1-C3.P1200: SS, MDC1.C2.CS1060: FS, MDC1.C3.CS1060: SS, MDC1-C4.P1200: SS, MDC1.C3.CS1060: FS, MDC1.C3.CS1050: FS, MDC1-C4.P1200: FS, MDC1.C4.CS1060: SS, MDC1.C4.CS1050: SF, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF | SURE STEEL | 840 | 0 |  | ['1319: FS', '1323: FS', '24: FS', '1311: FS'] | ['1283: FS', '26: FS', '1273: SS', '26: SS', '1273: FS', '1233: SS', '28: SS', '1233: FS', '1276: FS', '28: FS', '1178: SS', '1238: SF', '1178: FS', '1238: FF']
1300 | Not Started | MDC1-BL.5.7.3.1.2 | Task Dependent | MEP Undeground Rough-In (Interior) | 2020-07-27 07:00 | 2020-08-13 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 0 | 0 |  |  |  |  | MDC1-1999: FS, MDC1.AD.CS1060: FS | MDC1.S.1100: FS, MDC1.AD.CS1090: FS, MDC1.C1.CS1090: FS, MDC1-C1.P1400: FS, MDC1.AD.CS1090: FF | TCM, VECA Electricians | 1330 | 0 |  | ['1340: FS', '1314: FS'] | ['1255: FS', '1294: FS', '1280: FS', '9: FS', '1294: FF']
1301 | Not Started | MDC1-BL.5.7.1.2.5 | Task Dependent | Downspouts & Gutters | 2020-07-27 07:00 | 2020-08-13 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 0 | 0 |  |  |  |  | MDC1.C1.CS1060: FS, MDC1.C1.CS1070: FS, MDC1.AD.CS1070: FF 2 | MDC1.C1.C2000: FS, MDC1.C1.C1000: FS, MDC1.C2.CS1060: FS | SURE STEEL | 900 | 0 |  | ['1324: FS', '1315: FS', '1303: FF 2'] | ['1289: FS', '1288: FS', '1273: FS']
1302 | In Progress | MDC1-BL.5.1.10 | Task Dependent | IWW System | 2020-05-26 07:00 | 2020-08-08 17:00 | 2020-05-18 |  |  |  | 43.33 | 33 | 34 | 60 | 5 | 5 |  |  |  |  | MDC1-1997: FS | MDC1.S.1130: SS 30, MDC1.C1.C1250: FS, MDC1.S.1900: FS, MDC1.S.1870: FS |  | 0 | 0 |  | ['1346: FS'] | ['1197: SS 30', '1051: FS', '257: FS', '348: FS']
1303 | Not Started | MDC1-BL.5.7.3.2 | Task Dependent | Downspouts & Gutters | 2020-07-27 07:00 | 2020-08-07 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.AD.CS1060: FS, MDC1.AD.CS1040: FS, MDC1.AD.CS1050: FS, MDC1-C1.P1200: FS | MDC1.C1.CS1080: FF 2, MDC1-1965: FS, MDC1-1972: FS | SURE STEEL | 900 | 0 |  | ['1314: FS', '1326: FS', '1318: FS', '22: FS'] | ['1301: FF 2', '1286: FS', '1287: FS']
1304 | Not Started | MDC1-BL.5.7.5.7.1.3 | Task Dependent | Erect PEMB Steel | 2020-07-23 07:00 | 2020-08-07 17:00 |  |  |  |  | 0 | 0 | 13 | 13 | 7 | 7 |  |  |  |  | MDC1.C3.CS1000: FS, MDC1.C2.CS1020: FS, MDC1-C3.P1100: FS | MDC1.C3.CS1040: FS, MDC1.C4.CS1020: FS, MDC1-C4.P1100: FS, MDC1.C3.CS1030: FS | SURE STEEL | 910 | 0 |  | ['1321: FS', '1319: FS', '15: FS'] | ['1283: FS', '1291: FS', '19: FS', '1298: FS']
1305 | Not Started | MDC1-BL.5.7.6.7.1.1 | Task Dependent | Interior Footings - Excavate/FRP/Backfill | 2020-07-25 07:00 | 2020-08-06 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 11 | 11 |  |  |  |  | MDC1.C4.CS1000: SS 10, MDC1-C4.P1000: FS | MDC1.C4.CS1020: FS, MDC1.C4.CS1070: FS | CSI, Advantage | 2000 | 0 |  | ['1317: SS 10', '18: FS'] | ['1291: FS', '1120: FS']
1306 | In Progress | MDC1-BL.4.11.5.1 | Task Dependent | Neher Mcgrath Study | 2020-07-02 08:00 | 2020-08-06 17:00 | 2020-06-22 |  |  |  | 28.57 | 7 | 25 | 35 | 51 | 51 |  |  |  |  | MDC1-1999: FS 3 | MDC1-1993: FS, MDC1.S.1020: FS |  | 0 | 0 |  | ['1340: FS 3'] | ['1310: FS', '1307: FS']
1307 | Not Started | MDC1-BL.5.1.3.1.2.4 | Task Dependent | Duct Bank - COLO1- UPM to UPM | 2020-07-31 07:00 | 2020-08-05 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 56 | 56 |  |  |  |  | MDC1-1997.1: FS, MDC1.AD.CS1060: FS, MDC1.C2.CS1030: FS | MDC1.S.1360: FS, MDC1.S.1290: FS, MDC1.S.1050: FS |  | 0 | 0 |  | ['1306: FS', '1314: FS', '1311: FS'] | ['1108: FS', '1128: FS', '1293: FS']
1308 | Not Started | MDC1-BL.4.14.2 | Task Dependent | Design / Lead Time for Fire Protection | 2020-07-06 08:00 | 2020-08-04 16:00 |  |  |  |  | 0 | 0 | 30 | 30 | 108 | 108 | Start On or After | 2020-07-06 |  |  | MDC1-2003: FS | MDC1AD-1024: FS |  | 0 | 0 |  | ['59: FS'] | ['1156: FS']
1309 | Not Started | MDC1-BL.4.11.5.4 | Task Dependent | DRB#1 BIM Modeling & Coordination DRB#1 JAZ to UMS/URS & UPM to UMS | 2020-07-21 08:00 | 2020-08-03 17:00 |  |  |  |  | 0 | 0 | 14 | 14 | 5 | 5 | Start On or After | 2020-07-21 |  |  | MDC1-2140.2: FS | MDC1-2133: FS, MDC1-2131: FS, MDC1-2135: FS, MDC1-2132: FS, MDC1-2190: FS, MDC1-1996: FS |  | 0 | 0 |  | ['1322: FS'] | ['1136: FS', '1292: FS', '1297: FS', '1135: FS', '1248: FS', '1134: FS']
1310 | Not Started | MDC1-BL.4.11.5.1 | Task Dependent | MV Ductbanks Procurement | 2020-07-25 08:00 | 2020-08-02 17:00 |  |  |  |  | 0 | 0 | 9 | 9 | 51 | 51 |  |  |  |  | MDC1-1997.1: FS | MDC1.C2.Cx2010: FS, MDC1-1965: FS |  | 0 | 0 |  | ['1306: FS'] | ['498: FS', '1286: FS']
1311 | Not Started | MDC1-BL.5.7.4.7.1.3 | Task Dependent | Secondary Steel | 2020-07-23 07:00 | 2020-07-30 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 6 | 6 |  |  |  |  | MDC1.C2.CS1020: FS | MDC1.C2.CS1040: FS, MDC1.C2.CS1060: FS, MDC1-C3.P1200: FS, MDC1.C3.CS1060: FS, MDC1.C3.CS1050: FS, MDC1-C4.P1200: FS, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF, MDC1.C2.CS1050: FS, MDC1.S.1020: FS | SURE STEEL | 210 | 0 |  | ['1319: FS'] | ['1299: FS', '1273: FS', '26: FS', '1233: FS', '1276: FS', '28: FS', '1178: FS', '1238: FF', '1296: FS', '1307: FS']
1312 | In Progress | MDC1-BL.4.14.2 | Task Dependent | Design / Lead Time for M&P overhead | 2020-06-29 08:00 | 2020-07-28 16:00 | 2020-06-22 |  |  |  | 0 | 7 | 58 | 30 | 86 | 86 |  |  |  |  | MDC1-2003: FS | MDC1AD-1024: FS |  | 0 | 0 |  | ['59: FS'] | ['1156: FS']
1313 | Not Started | MDC1-BL.4.13 | Task Dependent | Lead time for Drywall/Framing | 2020-06-30 08:00 | 2020-07-26 16:00 |  |  |  |  | 0 | 0 | 27 | 27 | 80 | 80 |  |  |  |  | MDC1-2003: FS | MDC1AD-1016: FS |  | 0 | 0 |  | ['59: FS'] | ['1129: FS']
1314 | Not Started | MDC1-BL.5.7.3.2 | Task Dependent | Roof Panels Installation | 2020-07-18 07:00 | 2020-07-25 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1-C1.P1300: FS, MDC1.AD.CS1040: FF, MDC1.AD.CS1050: SS 5, MDC1-C1.P1200: FF | MDC1.AD.CS1070: FS, MDC1.AD.CS1090: FS, MDC1.C1.CS1070: SS, MDC1-C1.P1400: FS, MDC1.AD.CS1080: FS, MDC1.S.1020: FS | SURE STEEL | 0 | 0 |  | ['23: FS', '1326: FF', '1318: SS 5', '22: FF'] | ['1303: FS', '1294: FS', '1315: SS', '9: FS', '1300: FS', '1307: FS']
1315 | Not Started | MDC1-BL.5.7.1.2.5 | Task Dependent | Roof Panels Installation | 2020-07-18 07:00 | 2020-07-25 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1.C1.CS1060: SS, MDC1.AD.CS1060: SS | MDC1.C1.C2000: FS, MDC1.C1.C1050: SS 7, MDC1.C1.CS1080: FS, MDC1.C1.CS1100: FS, MDC1.C2.CS1050: FS, MDC1-C2.P1300: FS, MDC1.C1.C1000: FS 2 | SURE STEEL | 0 | 0 |  | ['1324: SS', '1314: SS'] | ['1289: FS', '1261: SS 7', '1301: FS', '1267: FS', '1296: FS', '25: FS', '1288: FS 2']
1316 | In Progress | MDC1-BL.5.1.10 | Task Dependent | Site Sanitary | 2020-05-11 07:00 | 2020-07-24 17:00 | 2020-05-05 |  |  |  | 43.33 | 43 | 34 | 60 | 44 | 44 |  |  |  |  | MDC1-1997: FS | MDC1.S.1120: SS 30, MDC1.C1.C1250: FS | Advantage | 3000 | 0 |  | ['1346: FS'] | ['1196: SS 30', '1051: FS']
1317 | In Progress | MDC1-BL.5.7.6.7.1.1 | Task Dependent | Perimeter Foundations - Excavate/FRP/Backfill | 2020-07-06 07:00 | 2020-07-23 17:00 | 2020-06-23 |  |  |  | 33.33 | 5 | 10 | 15 | 11 | 11 |  |  |  |  | MDC1.C3.CS1010: FS, MDC1-C4.P1000: FS | MDC1.C4.CS1010: SS 10 | CSI, Advantage | 3000 | 0 |  | ['1330: FS', '18: FS'] | ['1305: SS 10']
1318 | Not Started | MDC1-BL.5.7.3.2 | Task Dependent | Exterior Insulated Metal Panels Installation | 2020-07-13 07:00 | 2020-07-22 17:00 |  |  |  |  | 0 | 0 | 9 | 9 | 0 | 0 |  |  |  |  | MDC1.AD.CS1030: SS 9, MDC1-2011: FS, MDC1-2013: SS 4, MDC1-2003: FS, MDC1-2003: FF, MDC1.AD.CS1040: FS | MDC1AD-1010: FS, MDC1.C1.CS1050: SS, MDC1.AD.CS1060: SS 5, MDC1.AD.CS1070: FS, MDC1.C1.CS1060: SS, MDC1-1965: FS, MDC1-1972: FS, MDC1-C1.P1300: SS 2 | SURE STEEL | 0 | 0 |  | ['1327: SS 9', '1335: FS', '1336: SS 4', '59: FS', '59: FF', '1326: FS'] | ['589: FS', '1323: SS', '1314: SS 5', '1303: FS', '1324: SS', '1286: FS', '1287: FS', '23: SS 2']
1319 | Not Started | MDC1-BL.5.7.4.7.1.3 | Task Dependent | Erect PEMB Steel | 2020-07-07 07:00 | 2020-07-22 17:00 |  |  |  |  | 0 | 0 | 13 | 13 | 6 | 6 |  |  |  |  | MDC1.C2.CS1010: FS, MDC1.C1.CS1030: FS, MDC1-C2.P1100: FS | MDC1.C2.CS1040: FS, MDC1.C3.CS1020: FS, MDC1-C3.P1100: FS, MDC1.C2.CS1030: FS, MDC1.C2.CS1070: FF, MDC1.C2.CS1080: FS, MDC1-C2.P1400: FS | SURE STEEL | 0 | 0 |  | ['1320: FS', '1328: FS', '11: FS'] | ['1299: FS', '1304: FS', '15: FS', '1311: FS', '1242: FF', '1219: FS', '13: FS']
1320 | Completed | MDC1-BL.5.7.4.7.1.1 | Task Dependent | Interior Footings - Excavate/FRP/Backfill | 2020-07-08 07:00 | 2020-07-20 17:00 | 2020-06-09 | 2020-06-20 |  |  | 100 | 10 | 0 | 10 | [6 empty] | MDC1.C2.CS1000: SS 10, MDC1.C1.CS1010: FS 20, MDC1-C2.P1000: FS | MDC1.C2.CS1020: FS, MDC1.C3.CS1000: FS | CSI, Advantage | 2000 | 0 |  | ['1329: SS 10', '1333: FS 20', '10: FS'] | ['1319: FS', '1321: FS']
1321 | In Progress | MDC1-BL.5.7.5.7.1.1 | Task Dependent | Interior Footings - Excavate/FRP/Backfill | 2020-07-08 07:00 | 2020-07-20 17:00 | 2020-06-24 |  |  |  | 10 | 4 | 9 | 10 | 17 | 17 |  |  |  |  | MDC1.C3.CS1010: SS 10, MDC1-C3.P1000: FS, MDC1.C2.CS1010: FS | MDC1.C3.CS1020: FS, MDC1.C3.CS1070: FS | CSI | 1000 | 0 |  | ['1330: SS 10', '14: FS', '1320: FS'] | ['1304: FS', '1189: FS']
1322 | Not Started | MDC1-BL.4.9.2 | Finish Milestone | CO- DRB# 1 - Approved |  | 2020-07-20 17:00 |  |  | 2020-07-20 17:00 |  | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | MDC1-2140.1: FS | MDC1-2134: FS, MDC1-2189: FS, MDC1-2190: FS |  | 0 | 0 |  | ['1344: FS'] | ['1309: FS', '1226: FS', '1248: FS']
1323 | Not Started | MDC1-BL.5.7.1.2.2 | Task Dependent | Exterior Insulated Metal Panels Installation - East Elevation | 2020-07-13 07:00 | 2020-07-18 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 5 | 5 |  |  |  |  | MDC1.C1.CS1030: FS, MDC1-C1.P1200: FS, MDC1-2003: FS, MDC1.C1.CS1040: FS, MDC1.AD.CS1040: FS, MDC1.AD.CS1050: SS | MDC1.C1.CS1060: SS, MDC1.C2.CS1040: FS, MDC1-C2.P1200: FS | SURE STEEL | 0 | 0 |  | ['1328: FS', '22: FS', '59: FS', '1331: FS', '1326: FS', '1318: SS'] | ['1324: SS', '1299: FS', '24: FS']
1324 | Not Started | MDC1-BL.5.7.1.2.4 | Task Dependent | Exterior Insulated Metal Panels Installation - West Elevation | 2020-07-13 07:00 | 2020-07-18 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 5 | 5 |  |  |  |  | MDC1.C1.CS1050: SS, MDC1.C1.CS1040: FS, MDC1.AD.CS1040: FS, MDC1.AD.CS1050: SS, MDC1-C1.P1200: FS | MDC1.C1.CS1080: FS, MDC1.C1.CS1070: SS, MDC1.C1.C1000: FS 4, MDC1.C2.CS1060: FS, MDC1-C3.P1200: FS, MDC1.C3.CS1060: FS, MDC1.C3.CS1050: FS, MDC1-C4.P1200: FS, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF | SURE STEEL | 0 | 0 |  | ['1323: SS', '1331: FS', '1326: FS', '1318: SS', '22: FS'] | ['1301: FS', '1315: SS', '1288: FS 4', '1273: FS', '26: FS', '1233: FS', '1276: FS', '28: FS', '1178: FS', '1238: FF']
1325 | Not Started | MDC1-BL.4.10.3 | Finish Milestone | MDC1 Deliery -OFCI release submittal release |  | 2020-07-17 07:00 |  |  | 2020-07-17 07:00 |  | 0 | 0 | 0 | 0 | 3 | 3 | Finish On or After | 2020-07-17 07:00 |  |  | MDC1.M1000: FS, MDC1-1999: FS | MDC1.C1.E1320: FS, MDC1.C1.E1330: FS, MDC1.C1.E1380: FS, MDC1.C1.E1470: FS, MDC1.C2.E1300: FS, MDC1.C2.E1310: FS, MDC1.C2.E1360: FS, MDC1.C2.E1410: FS, MDC1.C3.E1340: FS, MDC1.C3.E1350: FS, MDC1.C3.E1360: FS, MDC1.C3.E1370: FS, MDC1.C4.E1360: FS, MDC1.C4.E1370: FS, MDC1.C4.E1380: FS, MDC1.C4.E1390: FS, MDC1-2511: FS, MDC1.C1.E1300: FS, MDC1.C1.E1310: FS, MDC1.C1.E1410: FS, MDC1.C1.E1420: FS, MDC1.C2.E1280: FS, MDC1.C2.E1290: FS, MDC1.C2.E1320: FS, MDC1.C2.E1350: FS, MDC1.C3.E1160: FS, MDC1.C3.E1170: FS, MDC1.C3.E1320: FS, MDC1.C3.E1330: FS, MDC1.C4.E1280: FS, MDC1.C4.E1310: FS, MDC1.C4.E1340: FS, MDC1.C4.E1350: FS, MDC1.C1.E1010: FS, MDC1.C1.E1020: FS, MDC1.C1.E1090: FS, MDC1.C1.E1110: FS, MDC1.C2.E1010: FS, MDC1.C2.E1020: FS, MDC1.C2.E1090: FS, MDC1.C2.E1110: FS, MDC1.C3.E1010: FS, MDC1.C3.E1030: FS, MDC1.C3.E1090: FS, MDC1.C3.E1110: FS, MDC1.C4.E1010: FS, MDC1.C4.E1020: FS, MDC1.C4.E1090: FS, MDC1.C4.E1110: FS, MDC1.C1.E1130: FS, MDC1.C1.E1170: FS, MDC1.C1.E1250: FS, MDC1.C1.E1270: FS, MDC1.C2.E1150: FS, MDC1.C2.E1230: FS, MDC1.C2.E1250: FS, MDC1.C3.E1190: FS, MDC1.C3.E1210: FS, MDC1.C3.E1280: FS, MDC1.C4.E1150: FS, MDC1.C4.E1170: FS, MDC1.C4.E1250: FS, MDC1.C4.E1270: FS, MDC1.C1.E1050: FS, MDC1.C1.E1070: FS, MDC1.C1.E1190: FS, MDC1.C1.E1210: FS, MDC1.C2.E1040: FS, MDC1.C2.E1070: FS, MDC1.C2.E1170: FS, MDC1.C2.E1190: FS, MDC1.C3.E1050: FS, MDC1.C3.E1070: FS, MDC1.C3.E1230: FS, MDC1.C3.E1250: FS, MDC1.C4.E1050: FS, MDC1.C4.E1070: FS, MDC1.C4.E1190: FS, MDC1.C4.E1210: FS, MDC1.C1.E1350: FS, MDC1.C1.E1370: FS, MDC1.C1.E1440: FS, MDC1.C1.E1460: FS, MDC1.C2.E1380: FS, MDC1.C2.E1400: FS, MDC1.C2.E1430: FS, MDC1.C2.E1450: FS, MDC1.C3.E1390: FS, MDC1.C3.E1410: FS, MDC1.C3.E1430: FS, MDC1.C3.E1450: FS, MDC1.C4.E1410: FS, MDC1.C4.E1430: FS, MDC1.C4.E1450: FS, MDC1.C4.E1470: FS, MDC1-2511: SS, MDC1-2509: FS, MDC1-2510: FS, MDC1-2512: FS, MDC1-2513: FS, MDC1-2514: FS, MDC1-1965: FS, MDC1-1972: FS, MDC1.C1.C1000: FS 20, MDC1.C1.C3000: FS 10, MDC1.C1.C2000: FS 10, MDC1.C1.C4000: FS 10, MDC1.C1.C4030: FS 10, MDC1-2133: FS, MDC1-2004: FS, MDC1.C3.C3350: FS, MDC1.C3.C3110: FS, MDC1.C3.C3370: FS, MDC1.C3.Cx2030: FS, MDC1.C2.C4380: FS, MDC1.C2.C4100: FS, MDC1.C2.C4400: FS, MDC1.C2.Cx3030: FS, MDC1.C2.Cx2030: FS |  | 0 | 0 |  | ['1: FS', '1340: FS'] | ['3: FS', '43: FS', '42: FS', '44: FS', '45: FS', '46: FS', '47: FS', '48: FS', '49: FS', '51: FS', '50: FS', '52: FS', '53: FS', '55: FS', '54: FS', '56: FS', '225: FS', '77: FS', '79: FS', '78: FS', '80: FS', '81: FS', '83: FS', '66: FS', '84: FS', '85: FS', '87: FS', '86: FS', '88: FS', '73: FS', '91: FS', '90: FS', '92: FS', '94: FS', '97: FS', '96: FS', '100: FS', '102: FS', '105: FS', '104: FS', '108: FS', '110: FS', '114: FS', '112: FS', '116: FS', '118: FS', '121: FS', '120: FS', '124: FS', '126: FS', '130: FS', '132: FS', '128: FS', '134: FS', '136: FS', '138: FS', '140: FS', '142: FS', '143: FS', '146: FS', '150: FS', '148: FS', '152: FS', '154: FS', '158: FS', '156: FS', '160: FS', '161: FS', '166: FS', '164: FS', '168: FS', '170: FS', '174: FS', '172: FS', '176: FS', '180: FS', '184: FS', '178: FS', '182: FS', '186: FS', '190: FS', '188: FS', '192: FS', '194: FS', '198: FS', '196: FS', '200: FS', '202: FS', '206: FS', '204: FS', '208: FS', '210: FS', '214: FS', '212: FS', '216: FS', '225: SS', '223: FS', '224: FS', '226: FS', '227: FS', '228: FS', '1286: FS', '1287: FS', '1288: FS 20', '1263: FS 10', '1289: FS 10', '1265: FS 10', '1245: FS 10', '1136: FS', '1193: FS', '442: FS', '788: FS', '399: FS', '352: FS', '556: FS', '971: FS', '502: FS', '305: FS', '464: FS']
1326 | Not Started | MDC1-BL.5.7.3.1.3 | Task Dependent | Secondary Steel | 2020-07-02 07:00 | 2020-07-10 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1.AD.CS1030: FS | MDC1.AD.CS1050: FS, MDC1AD-1010: FS, MDC1.C1.CS1050: FS, MDC1.AD.CS1060: FF, MDC1.AD.CS1070: FS, MDC1.C1.CS1060: FS, MDC1-1965: FS, MDC1-1972: FS, MDC1-C1.P1300: FS | SURE STEEL | 0 | 0 |  | ['1327: FS'] | ['1318: FS', '589: FS', '1323: FS', '1314: FF', '1303: FS', '1324: FS', '1286: FS', '1287: FS', '23: FS']
1327 | In Progress | MDC1-BL.5.7.3.1.3 | Task Dependent | Erect PEMB Steel | 2020-06-29 07:00 | 2020-07-09 17:00 | 2020-06-22 |  |  |  | 66.67 | 6 | 3 | 9 | 0 | 0 |  |  |  |  | MDC1-1383: FS 1, MDC1-2002: FS, MDC1.S.1010: FS, MDC1-2111: FS | MDC1.AD.CS1050: SS 9, MDC1.C1.CS1030: SS 5, MDC1-C1.P1200: SS 12, MDC1-C1.P1100: SS, MDC1.AD.CS1040: FS | SURE STEEL | 910 | 0 |  | ['1338: FS 1', '58: FS', '1337: FS', '1332: FS'] | ['1318: SS 9', '1328: SS 5', '22: SS 12', '7: SS', '1326: FS']
1328 | In Progress | MDC1-BL.5.7.1.1.3 | Task Dependent | Erect PEMB Steel | 2020-06-29 07:00 | 2020-07-09 17:00 | 2020-06-26 |  |  |  | 33.33 | 2 | 6 | 9 | 6 | 6 |  |  |  |  | MDC1.C1.CS1010: FS, MDC1.AD.CS1030: SS 5, MDC1-C1.P1100: FS | MDC1.C1.CS1050: FS, MDC1.C2.CS1020: FS, MDC1-C2.P1100: FS, MDC1.C1.CS1040: SS 4 | SURE STEEL | 0 | 0 |  | ['1333: FS', '1327: SS 5', '7: FS'] | ['1323: FS', '1319: FS', '11: FS', '1331: SS 4']
1329 | Completed | MDC1-BL.5.7.4.7.1.1 | Task Dependent | Perimeter Foundations - Excavate/FRP/Backfill | 2020-06-22 07:00 | 2020-07-09 17:00 | 2020-05-11 | 2020-06-16 |  |  | 100 | 29 | 0 | 15 | [6 empty] | MDC1.C1.CS1000: SS 10, MDC1-C2.P1000: FS | MDC1.C2.CS1010: SS 10, MDC1.C3.CS1010: SS 10, MDC1-C3.P1000: FS | CSI, Advantage | 3000 | 0 |  | ['1343: SS 10', '10: FS'] | ['1320: SS 10', '1330: SS 10', '14: FS']
1330 | In Progress | MDC1-BL.5.7.5.7.1.1 | Task Dependent | Perimeter Foundations - Excavate/FRP/Backfill | 2020-06-22 07:00 | 2020-07-09 17:00 | 2020-06-16 |  |  |  | 0 | 10 | 16 | 15 | 11 | 11 |  |  |  |  | MDC1.C2.CS1000: SS 10 | MDC1.C3.CS1000: SS 10, MDC1.C4.CS1000: FS, MDC1-C4.P1000: FS | CSI, Advantage | 3000 | 0 |  | ['1329: SS 10'] | ['1321: SS 10', '1317: FS', '18: FS']
1331 | Not Started | MDC1-BL.5.7.1.1.3 | Task Dependent | Secondary Steel | 2020-07-01 07:00 | 2020-07-09 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 6 | 6 |  |  |  |  | MDC1.C1.CS1030: SS 4 | MDC1.C1.CS1050: FS, MDC1.C1.CS1060: FS | SURE STEEL | 0 | 0 |  | ['1328: SS 4'] | ['1323: FS', '1324: FS']
1332 | Completed | MDC1-BL.4.9.2 | Finish Milestone | Phase 1C1- MDC1 Commitment for steel crew |  | 2020-06-29 07:00 |  | 2020-06-11 | 2020-06-29 07:00 | 2020-06-11 | 100 | 0 | 0 | 0 |  |  | Finish On | 2020-06-04 17:00 |  |  | MDC1-2002: FS | MDC1.AD.CS1030: FS |  | 0 | 0 |  | ['58: FS'] | ['1327: FS']
1333 | Completed | MDC1-BL.5.7.1.1.1 | Task Dependent | Interior Footings - Excavate/FRP/Backfill | 2020-06-13 07:00 | 2020-06-25 17:00 | 2020-06-02 | 2020-06-12 |  |  | 100 | 9 | 0 | 10 | [6 empty] | MDC1.AD.CS1020: FF, MDC1-C1.P1000: FS | MDC1.C1.CS1030: FS, MDC1.C2.CS1010: FS 20 | CSI, Advantage | 2500 | 0 |  | ['1339: FF', '6: FS'] | ['1328: FS', '1320: FS 20']
1334 | In Progress | MDC1-BL.4.11.1 | Task Dependent | Electrical Long Lead Equipment Procurement (Cablebus, Panel Boards) | 2020-04-27 08:00 | 2020-06-21 17:00 | 2020-04-27 08:00 |  |  |  | 55.36 | 63 | 25 | 56 | 97 | 97 |  |  |  |  | MDC1-2002: FS | MDC1-1963: FS |  | 0 | 0 |  | ['58: FS'] | ['1217: FS']
1335 | In Progress | MDC1-BL.4.13 | Task Dependent | Lead Time for Wall & Roof Metal Panels | 2020-04-27 08:00 | 2020-06-21 17:00 | 2020-04-07 |  |  |  | 98.21 | 83 | 1 | 56 | 12 | 12 |  |  |  |  | MDC1-2002: FS 7 | MDC1.AD.CS1050: FS |  | 0 | 0 |  | ['58: FS 7'] | ['1318: FS']
1336 | In Progress | MDC1-BL.4.13 | Task Dependent | Lead Time for HM Ext. frames | 2020-04-27 08:00 | 2020-06-21 17:00 | 2020-04-07 |  |  |  | 80.36 | 83 | 11 | 56 | 13 | 13 |  |  |  |  | MDC1-2002: FS 7 | MDC1.AD.CS1050: SS 4 |  | 0 | 0 |  | ['58: FS 7'] | ['1318: SS 4']
1337 | Completed | MDC1-BL.5.1.1 | Task Dependent | Establish Access Roads / Laydown / Craft Parking / Temp Utilities | 2020-05-14 07:00 | 2020-06-19 17:00 | 2020-04-24 | 2020-05-23 |  |  | 100 | 24 | 0 | 30 | [6 empty] | MDC1.S.1000: SS 15 | MDC1-C1.P1100: FS, MDC1.AD.CS1030: FS |  | 0 | 0 |  | ['1347: SS 15'] | ['7: FS', '1327: FS']
1338 | Completed | MDC1-BL.4.13 | Task Dependent | Lead Time for PEMB | 2020-02-19 08:00 | 2020-06-18 17:00 | 2020-02-24 | 2020-06-18 |  |  | 100 | 115 | 0 | 121 | [6 empty] | A1170: FS, MDC1-2001: FS | MDC1.AD.CS1030: FS 1 |  | 0 | 0 |  | ['2: FS', '57: FS'] | ['1327: FS 1']
1339 | Completed | MDC1-BL.5.7.3.1.1 | Task Dependent | Interior Footings - Excavate/FRP/Backfill | 2020-06-05 07:00 | 2020-06-16 17:00 | 2020-06-02 | 2020-06-12 |  |  | 100 | 9 | 0 | 10 | [6 empty] | MDC1-1998: FF 10, MDC1-2002: FS, MDC1-1977: FS, MDC1.AD.CS1010: FS, MDC1.AD.CS1010: FF | MDC1.C1.CS1010: FF | CSI, Advantage | 2000 | 0 |  | ['1349: FF 10', '58: FS', '1345: FS', '1342: FS', '1342: FF'] | ['1333: FF']
1340 | Completed | MDC1-BL.4.11.1 | Task Dependent | BIM Modeling (Under ground) | 2020-05-05 08:00 | 2020-06-08 17:00 | 2020-05-05 08:00 | 2020-06-08 |  |  | 100 | 34 | 0 | 35 | [6 empty] | MDC1-1997: FS | MDC1-1965: FS, MDC1-1972: FS, MDC1.AD.CS1080: FS, MDC1-2008: FS, MDC1-1997.1: FS 3, MDC1-2527: FS |  | 0 | 0 |  | ['1346: FS'] | ['1286: FS', '1287: FS', '1300: FS', '1216: FS', '1306: FS 3', '1325: FS']
1341 | Completed | MDC1-BL.5.7.1.1.1 | Task Dependent | Perimeter Foundations - Waterproof Backfill | 2020-05-26 07:00 | 2020-06-06 17:00 | 2020-05-26 07:00 | 2020-06-17 |  |  | 100 | 18 | 0 | 10 | [6 empty] | MDC1.C1.CS1000: FS | MDC1-C2.P1000: FS | CSI | 100 | 0 |  | ['1343: FS'] | ['10: FS']
1342 | Completed | MDC1-BL.5.7.3.1.1 | Task Dependent | Perimeter Foundations - Waterproof/Backfill | 2020-06-01 07:00 | 2020-06-04 17:00 | 2020-05-27 | 2020-06-05 |  |  | 100 | 7 | 0 | 4 | [6 empty] | MDC1.AD.CS1000: FS | MDC1.AD.CS1020: FS, MDC1.AD.CS1020: FF | CSI | 40 | 0 |  | ['1350: FS'] | ['1339: FS', '1339: FF']
1343 | Completed | MDC1-BL.5.7.1.1.1 | Task Dependent | Perimeter Foundations - Excavate/FRP | 2020-05-15 07:00 | 2020-06-03 17:00 | 2020-05-04 | 2020-05-15 |  |  | 100 | 9 | 0 | 15 | [6 empty] | MDC1.AD.CS1000: FS | MDC1.C2.CS1000: SS 10, MDC1-C2.P1000: FS, MDC1.C1.CS1020: FS | CSI, Advantage | 3000 | 0 |  | ['1350: FS'] | ['1329: SS 10', '10: FS', '1341: FS']
1344 | In Progress | MDC1-BL.4.9.2 | Task Dependent | MDC1 Issue DRB #1 for Review | 2020-05-26 07:00 | 2020-06-01 17:00 | 2020-05-19 |  |  |  | 0 | 32 | 17 | 5 | 5 | 5 |  |  |  |  | MDC1-2002: FS | MDC1-2140.2: FS |  | 0 | 0 |  | ['58: FS'] | ['1322: FS']
1345 | Completed | MDC1-BL.4.13 | Task Dependent | Lead Time for Rebar (Footings & Walls) | 2020-04-27 08:00 | 2020-05-31 17:00 | 2020-03-30 | 2020-04-21 |  |  | 100 | 22 | 0 | 35 | [6 empty] | A1170: FS, MDC1-2002: FS | MDC1.AD.CS1000: FS, MDC1.AD.CS1020: FS |  | 0 | 0 |  | ['2: FS', '58: FS'] | ['1350: FS', '1339: FS']
1346 | Completed | MDC1-BL.4.11.5.1 | Task Dependent | Off-Site BIM Modeling & Coordination | 2020-04-27 08:00 | 2020-05-24 17:00 | 2020-04-14 | 2020-05-05 |  |  | 100 | 21 | 0 | 28 | [6 empty] | MDC1-2002: FS 7 | MDC1.S.1030: FS, MDC1.S.1120: FS, MDC1.S.1040: FS, MDC1-1999: FS, MDC1-2004: FS, MDC1-1994: FS |  | 0 | 0 |  | ['58: FS 7'] | ['1316: FS', '1196: FS', '1302: FS', '1340: FS', '1193: FS', '1348: FS']
1347 | Completed | MDC1-BL.5.1.2 | Task Dependent | Mobilization | 2020-04-27 07:00 | 2020-05-20 17:00 | 2020-04-06 | 2020-05-02 17:00 |  |  | 100 | 23 | 0 | 20 | [6 empty] | MDC1-2002: FS | MDC1.S.1010: SS 15, MDC1.P1010: SS -1 |  | 0 | 0 |  | ['58: FS'] | ['1337: SS 15', '4: SS -1']
1348 | Completed | MDC1-BL.4.11.5.1 | Task Dependent | Telecom DuctBank / Vaults Procurement | 2020-05-14 08:00 | 2020-05-18 17:00 | 2020-05-06 | 2020-06-20 |  |  | 100 | 45 | 0 | 5 | [6 empty] | MDC1-2002: FS, MDC1-1997: FS | MDC1.S.1160: FS |  | 0 | 0 |  | ['58: FS', '1346: FS'] | ['1215: FS']
1349 | Completed | MDC1-BL.4.11.1 | Task Dependent | Underground Grounding Procurement | 2020-04-27 08:00 | 2020-05-17 17:00 | 2020-04-07 | 2020-04-28 |  |  | 100 | 21 | 0 | 21 | [6 empty] | MDC1-2002: FS 7 | MDC1.AD.CS1020: FF 10 |  | 0 | 0 |  | ['58: FS 7'] | ['1339: FF 10']
1350 | Completed | MDC1-BL.5.7.3.1.1 | Task Dependent | Perimeter Foundations - Excavate/FRP | 2020-04-27 07:00 | 2020-05-14 17:00 | 2020-04-22 | 2020-05-20 |  |  | 100 | 23 | 0 | 15 | [6 empty] | MDC1-1977: FS, MDC1-2002: FS, MDC1-P1020: FS, MDC1-C1.P1000: FS | MDC1.C1.CS1000: FS, MDC1.AD.CS1010: FS | CSI, Advantage | 3000 | 0 |  | ['1345: FS', '58: FS', '5: FS', '6: FS'] | ['1343: FS', '1342: FS']